## FOR REFERENCE ONLY
THIS DOCUMENT IS FOR REFERENCE ONLY!
UNCONTROLLED DOCUMENT

## ROLES MATRIX
GROUP LEADS (GLS) / WORK CENTER LEADS (WCLS) | PROJECT COORDINATOR | WORK CONTROL DOCUMENT AUTHOR | SRF OPS SUBJECT MATTER EXPERTS (SMES) | SOTRs / TRs | ENGINEERS
PROJECT EXECUTION: | PROJECT EXECUTION: | PROJECT EXECUTION: | PROJECT EXECUTION: | PROJECT EXECUTION: | PROJECT EXECUTION:
DELIVER LAB SERVICE REQUEST PRODUCT OR DATA DIRECTLY TO THE REQUESTER | ASSIGNED BY SRF OPS DEPARTMENT HEAD TO MONITOR PROJECT STATUS |  | PROVIDE INPUT TO THE PROJECT COORDINATOR FOR DEVELOPMENT OF THE PROJECT EXECUTION PLAN
| WRITE PROJECT EXECUTION PLANS |  | WORKS WITH PROJECT COORDINATOR AND WCLS/GLS TO IDENTIFY THE WORK CONTROL DOCUMENTS NEEDE FOR THE PROJECT AND APPROPRIATE AUTHORS, REVIEWERS AND APPROVERS
| MAINTAIN PROJECT WCD REGISTER |  | RECEIVES CUSTOMER REQUIREMENTS FROM THE PROJECT COORDINATOR
COORDINATE DELIVERY OF COMPLETED PRODUCT
ENSURE PROJECT LESSONS LEARNED DONE
ENSURE PROJECT CLOSEOUT REPORT DONE
ENSURES SIGNATURES ARE OBTAINED AND PEP IS STORED/REVISED ACCORDINGLY
ENSURES ALL RELEVANT CUSTOMER REQUIREMENTS ARE PROVIDED TO TRs
WORKS WITH WCLS/GLS OR SMES TO IDENTIFY WCD NEEDED FOR PROJECT
WORKS WITH WCLS/GLS OR SMES TO IDENTIFY AUTHORS/REVIEWERS/APPROVERS
ENSURES CUSTOMER REQUIREMENTS ARE PROVIDED TO WCLs, GLs, AND SMEs
ENSSURES PROJECT WCD REGISTER IS CREATED AND UPDATED ACCORDINGLY
MAY NEED TO ENSURE THE PEP OR WCD LIST IS REVISED/ALIGNED WITH APPROVED SCOPE CHANGES
PRODUCES AUTHORIZATION FOR RELEASE FORM WHEN HARDWARE PRODUCTION ACTIVITES ARE COMPLETED AND APPROPRIATE SIGNATURES OBTAINED
CEBAF/MLP/WFO: COORDINATES PRODUCT AND DATA DELIVERS WITH CUSTOMER WHEN PRODUCT/DATA IS CONFIRMED COMPLETE BY PRODUCTION PROCESS.
UPON PROJECT COMPLETION - ENSURES ALL WCDs ARE CLOSED
UPON PROJECT COMPLETION - INFORM DOC/REC POs TO ARCHIVE FILES
UPON PROJECT COMPLETION - ENSURE ALL UNNECESSARY EXTERNAL ACCESS IS REMOVED
UPON PROJECT COMPLETION - PRODUCE A LESSONS LEARNED DOCUMENT USING TEMPLATE
UPON PROJECT COMPLETION - PRODUCE A PROJECT CLOSEOUT REPORT USING TEMPLATE
PRODUCTION: | PRODUCTION: | PRODUCTION: | PRODUCTION: | PRODUCTION: | PRODUCTION:
LOOK FOR IMPROVEMENTS THAT MAY BE INCORPORATED IN REVISIONS TO WCDs OR PROVIDED AS INPUTS TO ORGANIZATION KNOWLEDGE | PROJ COORD OR GL/WCL: ENSURE ALL WCDs ARE COMPLETE/REQUIRED DATA IF FILED/READY FOR CUSTOMER DELIVERY | The author of the Work Control Documents is responsible for submitting the document for review and approval as described in the Project Work Control Documents Register. | ATTEND Project-specific MEETINGS as needed/requested
ENSURES (WITH PROJ COORD) ALL WCDs ARE COMPLETE, REQUIRED DATA IS FILED OR READY FOR CUSTOMER | ORGANIZES A DOCUMENT REVIEW MEETING WHEN PRODUCTION IS COMPLETE, AS REQUIRED |  | Work Control Documents are developed by subject matter experts within each Work Center to contain all the customer requirements received from the Project Management Process.
WCLS: PARTICIPALTES IN SHORT, MEDIUM AND LONG TERM PLANNING AND EXECUTION | ATTENDS PROJECT SPECIFIC MEETING AND ORGANIZES A DOCUMENT REVIEW MEETING
GLS: ATTEND MEETING, AND ENSURE MANPOWER AND RESOURCES ARE AVAILABLE TO PERFORM THE WORK ACCORDING TO THE PLAN.
WCDs ARE DEVELOPED BY SUBJECT MATTER EXPERTS WITHIN EACH WORK CENTER TO CONTAIN ALL CUSTOMER REQUIREMENTS
WCD AUTHORS RESPONSIBLE FOR SUBMITTING DOCS FOR REVIEW/APPROVALS AND TO PROJ COORD FOR WCD REGISTER
ATTEND PROJECT SPECIFIC MEETINGS AS APPLICABLE
WORKS WITH PROJ COORD TO DETERMINE WHO IS NOTIFIED WHEN AN NCR IS INITIATED, WHO IS AUTHORIZED TO DISPOSITION
WORKS WITH PROJ COORD TO IDENTIFY THE DESIGNATED ENGINEERS WHO CAN EVALUATE AND RESOLVE NCRs
NONCONFORMANCE: | NONCONFORMANCE: | NONCONFORMANCE: | NONCONFORMANCE: | NONCONFORMANCE: | NONCONFORMANCE:
AT PROJECT START: WORKS WITH PROJ COORD TO DETERMINE WHO IS NOTIFIED WHEN AN NCR IS INITIATED, WHO IS AUTHORIZED TO DETERMINE THE RESOLUTION, AND WHO IS AUTHORIZED TO CLOSE THE NCR. | MAINTAINS PROJECT WCD REGISTER WHICH LISTS RESPONDING ENGRS TO ADDRESS NCRS |  |  | TECHNICAL REPRESENTATIVES: Coordinates the move, packaging, and shipping of parts determined to be unacceptable and returned to the vendor. | SRF Project Coordinator: Works with Group and Work Center Leads to identify the Designated Engineers who can evaluate and resolve NCRs.
AT PROJECT START: WORKS WITH PROJ COORD TO IDENTIFY THE DESIGNATED ENGINEERS WHO CAN EVALUATE AND RESOLVE NCRS. | AT PROJECT START WORKS WITH GLS/WCLS TO DETERMINE WHO ARE NCR INFO/NCR DISP/D3 NAMES |  |  |  | PROJECT COORDINATOR Maintains the project Work Control Document Register which lists Responding Engineers to address D3s.
| WORKS WITH GLS/WCLS TO IDENTIFY THE DESIGNATED ENGINEERS WHO CAN EVALUATE AND RESOLVE NCRS |  |  |  | After an NCR is initiated, Responding Engineers identify the cause of the nonconformance and determine the actions needed to resolve the issue
| MAINTAINS THE PROJECT WCD REGISTER |  |  |  | Responding Engineers verify the actions needed to resolve the nonconformance are complete and the product meets the requirements, then closes the NCR.
INVENTORY/TRACEABILITY: | INVENTORY/TRACEABILITY: | INVENTORY/TRACEABILITY: | INVENTORY/TRACEABILITY: | INVENTORY/TRACEABILITY: | INVENTORY/TRACEABILITY:
RESPONSIBLE FOR REQUESTING PARTS FROM INVENTORY |  |  |  | SOTR: Provides anticipated shipping schedule to ICC, ensures vendors provide all required
RESPONSIBLE FOR INFORMING INVENTORY STAFF WHEN PARTS PASS INSPECTION AND ARE ISSUED DIRECTLY TO PRODUCTION |  |  |  | Technical Representative (TR) - identify the critical parts where traceability is required in the SOW and/or Purchase Order
RETURN REJECTED PARTS TO INVENTORY |  |  |  | Inventory Representative - Verify an external unique identifier format is acceptable to PRIMeS database.
Subcontracting Officer Technical Representative (TR) - Ensures suppliers/vendors provide all documentation and follow SRF Inventory serialization requirements.
The Process Owner for Inventory and Traceability facilitates the decision of which parts and subassemblies are uniquely identified, and which travelers contain the identification to provide traceability throughout the production process. Parts such as cavities are identified and traced from receipt/disassembly to final delivery of a cryomodule. Parts such as elbows and feedthroughs may be identified from receipt/disassembly to inspection. Parts such as expendable fasteners, seals, and gaskets may not be serialized. This information is written into an Inventory and Traceability Plan for each project.
VENDOR MANAGEMENT: | VENDOR MANAGEMENT: | VENDOR MANAGEMENT: | VENDOR MANAGEMENT: | VENDOR MANAGEMENT: | VENDOR MANAGEMENT:
| SRF PROJECT LEAD: DETERMINES WHICH PROCUREMENTS WILL NEED TO ADHERE TO THE PROGRAM REQUIREMENTS FOR A GIVEN PROJECT |  |  | Technical Representatives (TR) in SRF Operations, in coordination with the JLab Procurement Group, determine and apply criteria for the evaluation, selection, monitoring of performance, and re-evaluation of external providers
Technical Representatives (TR) in SRF Operations Monitors receipt inspection at JLab and dispositions JLab NCR program when necessary
Technical Representatives (TR) in SRF Operations Provides product-ready parts to the Inventory/Traceability Program
The TR must ensure that all drawings that are referenced in the SOW or included in the TRP are the current revision and are approved by the document owner
CALIBRATION: | CALIBRATION: | CALIBRATION: | CALIBRATION: | CALIBRATION: | CALIBRATION:
Determines equipment currently needed for critical-to-quality measurements and identifies it as Critical MTE in the Calibration Register. Assigns Calibration Custodian for Work Center M&TE. Manages verification program for Work Center. | SHOULD REVIEW PROCEDURES, TRAVELERS AND WCDS USED BY THEIR PROJECT(S) TO IDENTIFY ANY CRITICAL MTE QUALITY MEASUREMENTS AND WORK WITH WCLS/WCD AUTHORS TO ENSURE MEASUREMENTS ARE ADDRESSED | Identifies critical-to-quality measurements in work control documents.
Work Center Leads may designate any piece of M&TE as Critical MTE, with or without critical measurements identified by the WCD Authors. | SRF Project Coordinators should review the procedures, travelers and WCDs used by their project(s) to identify any critical-to-quality measurements and work with Work Center Leads and WCD Authors to ensure all Critical Measurements are addressed | Identifies critical-to-quality measurements in work control documents.
Work Center Leads should periodically review the procedures, travelers and WCDs used in their work area and identify any critical-to-quality measurements that require the use of Critical MTE |  | Identifies the measurement activities that are critical to quality based on the intended use of the measurement information or project requirements.
Work Center Leads determine the types and quantities of Critical MTE needed to support the measurement activities described in the work control documents. |  | The WCD Author will identify these “Critical Measurements” as such, and specifically state that “the use of Critical MTE is required,” in each relevant step of their travelers or procedures.
Work Center Leads are responsible for ensuring that adequate quantities of calibrated Critical MTE are available for all critical-to-quality work performed within their work center. |  | The WCD Author should inform the Work Center Lead(s) of any Critical Measurements, to ensure the proper Critical MTE is available when it is needed for measurement activities
The Calibration Register will be used by each Work Center Lead, for tracking and recording each item of Critical MTE and all associated calibrations. |  | For each Critical Measurement identified in a WCD, the WCD Author will require the performer of the measurement to record: a) property tag number (or unique serial number) of the Critical MTE used b) calibration DUE Date of the Critical MTE used |  |  |  | CALIBRATION CUSTODIAN
The Work Center Lead, or their designee, will create a calibration record for each piece of Critical MTE used in that Work Center, and ensure that the item is identified by selecting the “Critical MTE” button.
Measurement equipment not designated as Critical MTE may be entered into the Calibration Register at the discretion of the Work Center Lead, but it is not subject to the requirements of this procedure.
The Work Center Lead determines an instrument’s frequency of verification, based on the manufacturer’s recommendation and the risk associated with an “out-of-calibration” result.
The Work Center Lead may require that verifications be performed periodically or prior to each use of Critical MTE.
RECORDS: | RECORDS: | RECORDS: | RECORDS: | RECORDS: | RECORDS:
DETERMINES THE LIST OF REQUIRED RECORDS NEEDED FOR A SPECIFIC PROJECT
RESPONSIBLE FOR RECORDS CREATED BY PROJECT ACTIVITIES TO ENSURE APPROPRIATE LOCATION AND RETENTION
MUST ENSURE ALL PROJECT RECORDS ARE RETAINED IN APPROVED LOCATIONS
INFORM RECORDS MANAGER OF CHANGES TO RECORD TYPES, LOCATIONS, OR RETENETION PERIODS
DOCUMENTS: | DOCUMENTS: | DOCUMENTS: | DOCUMENTS: | DOCUMENTS: | DOCUMENTS:
THE PREFERRED LOCATION FOR ALL LEVEL 3 PROJECT DOCUMENTS IS DOCUSHARE. OTHER STORAGE LOCATIONS MAY BE USED WITH THE PERMISSION OF THE PROCESS OWNER OF DOCUMENT MANAGEMENT AND THE SRF DEPARTMENT HEAD. OTHER LOCATION MUST PROVIDE PROTECTION FROM DELETION AND MEET REQUIREMENTS OF THE DOCUMENT PROCESS PROCEDURE. | PROJECT MANAGER/PRINCIPAL INVESTIGATOR: CREATES AND MAINTAINS A REGISTER OF PROJECT DOCUMENTS REQUIRED BY THE QMS | THE PREFERRED LOCATION FOR ALL LEVEL 3 PROJECT DOCUMENTS IS DOCUSHARE. OTHER STORAGE LOCATIONS MAY BE USED WITH THE PERMISSION OF THE PROCESS OWNER OF DOCUMENT MANAGEMENT AND THE SRF DEPARTMENT HEAD. OTHER LOCATION MUST PROVIDE PROTECTION FROM DELETION AND MEET REQUIREMENTS OF THE DOCUMENT PROCESS PROCEDURE. | THE PREFERRED LOCATION FOR ALL LEVEL 3 PROJECT DOCUMENTS IS DOCUSHARE. OTHER STORAGE LOCATIONS MAY BE USED WITH THE PERMISSION OF THE PROCESS OWNER OF DOCUMENT MANAGEMENT AND THE SRF DEPARTMENT HEAD. OTHER LOCATION MUST PROVIDE PROTECTION FROM DELETION AND MEET REQUIREMENTS OF THE DOCUMENT PROCESS PROCEDURE.
STANDARDS, DESIGNS, AND OTHER DOCUMENTS DEEMED CRITICAL TO QUALITY MAY BE ISSUED TO SRF OPS BY THE CUSTOMER AND MUST BE INCLUDED IN THE PROJECT DOCUMENT REGISTER | MUST MAINTAIN A PROJECT DOCUMENT REGISTER OF LEVEL 3 DOCUMENTS | STANDARDS, DESIGNS, AND OTHER DOCUMENTS DEEMED CRITICAL TO QUALITY MAY BE ISSUED TO SRF OPS BY THE CUSTOMER AND MUST BE INCLUDED IN THE PROJECT DOCUMENT REGISTER | STANDARDS, DESIGNS, AND OTHER DOCUMENTS DEEMED CRITICAL TO QUALITY MAY BE ISSUED TO SRF OPS BY THE CUSTOMER AND MUST BE INCLUDED IN THE PROJECT DOCUMENT REGISTER
DOCUMENT OWNERS MUST REPORT ANY NEW OR REVISED DOCUMENT INFORMATION TO THE PROCESS OWNER FOR DOCUMENT MANAGEMENT OR THE SRF OPS PROJECT COORDINATOR TO ENSURE THE DOCUMENT REGISTERS CAN BE UPDATED. | THE PREFERRED LOCATION FOR ALL LEVEL 3 PROJECT DOCUMENTS IS DOCUSHARE. OTHER STORAGE LOCATIONS MAY BE USED WITH THE PERMISSION OF THE PROCESS OWNER OF DOCUMENT MANAGEMENT AND THE SRF DEPARTMENT HEAD. OTHER LOCATION MUST PROVIDE PROTECTION FROM DELETION AND MEET REQUIREMENTS OF THE DOCUMENT PROCESS PROCEDURE. | DOCUMENT OWNERS MUST REPORT ANY NEW OR REVISED DOCUMENT INFORMATION TO THE PROCESS OWNER FOR DOCUMENT MANAGEMENT OR THE SRF OPS PROJECT COORDINATOR TO ENSURE THE DOCUMENT REGISTERS CAN BE UPDATED. | DOCUMENT OWNERS MUST REPORT ANY NEW OR REVISED DOCUMENT INFORMATION TO THE PROCESS OWNER FOR DOCUMENT MANAGEMENT OR THE SRF OPS PROJECT COORDINATOR TO ENSURE THE DOCUMENT REGISTERS CAN BE UPDATED.
STANDARDS, DESIGNS, AND OTHER DOCUMENTS DEEMED CRITICAL TO QUALITY MAY BE ISSUED TO SRF OPS BY THE CUSTOMER AND MUST BE INCLUDED IN THE PROJECT DOCUMENT REGISTER
DOCUMENT OWNERS MUST REPORT ANY NEW OR REVISED DOCUMENT INFORMATION TO THE PROCESS OWNER FOR DOCUMENT MANAGEMENT OR THE SRF OPS PROJECT COORDINATOR TO ENSURE THE DOCUMENT REGISTERS CAN BE UPDATED.

## DOC TYPES - APPROVERS
REF: Document Management Procedure |  | REF: Project Execution Procedure
| DOCUMENT NUMBERING CONVENTION |  |  | The following rules apply to production travelers related to quality.
Document Type | Numbering Format | Title | Role | Purpose of the Review
SRF Program Description | SRF-##-PD-### | Author | SME | Accuracy and completeness of all technical requirements.
SRF Procedure | SRF-##-PR-### | Reviewer 1 | SRFOPS SME or WCL | Independent review of accuracy and completeness of all technical requirements.
SRF Form | SRF-##-FM-### | Reviewer 2 | SRFOPS WCL or Group Lead | Awareness to ensure availability of resources needed to execute work.
SRF Reference Document | SRF-##-RF-### | Project Representative | Project Representative | Awareness to ensure scope meets project expectations.
SRF Master Procedure | SRF-MSPR-WCA-ACTION-COMP
SRF Master Traveler | SRF-MSTR-WCA-ACTION-COMP
SRF Drawing | <designer’s choice> |  |  | The following rules apply to production procedures related to quality.
SRF Specification | <author’s choice> | Title | Role | Purpose of the Review
Project Procedure | PROJ-PR-WCA-ACTION-COMP | Author | SME | Accuracy and completeness of all technical requirements.
Project Traveler | PROJ-TR-WCA-ACTION-COMP | Reviewer 1 | SRFOPS SME or WCL | Independent review of accuracy and completeness of all technical requirements.
Project Form | PROJ-FM-<author’s choice> | Reviewer 2 | SRFOPS WCL or Group Lead | Awareness to ensure availability of resources needed to execute work.
Project Drawing | <designer’s choice>
Project Specification | <author’s choice>
DOCUMENT TEMPLATES TO BE USED
Document Type | Template
SRF Program Description | SRF-07-FM-001 SRF Program Description Template
SRF Procedure | SRF-07-FM-002 SRF Procedure Template
SRF Form | SRF-07-FM-003 Word Document Template
SRF Reference Document | SRF-07-FM-003 Word Document Template
SRF Master Procedure | SRF-07-FM-003 Word Document Template
SRF Master Traveler | Controlled by Pansophy Group Lead
SRF Drawing | Controlled by Engineering Group Lead
SRF Specification | SRF-07-FM-003 Word Document Template
Project Procedure | SRF-07-FM-003 Word Document Template
Project Traveler | Controlled by Pansophy Group Lead
Project Form | SRF-07-FM-003 Word Document Template
Project Drawing | Controlled by Engineering Group Lead
Project Specification | SRF-07-FM-003 Word Document Template
DOCUMENT APPROVERS
Document Type | Approvers
SRF Quality Manual | Quality Engineer, SRF Department Head
SRF Procedure | Document Owner, Quality Engineer, SRF Department Head
SRF Form | Document Owner, Quality Engineer, SRF Department Head
SRF Reference Document | Document Owner
SRF Master Procedure | Document Owner, Group/Work Center Lead
SRF Master Traveler | Document Owner, Group/Work Center Lead
SRF Drawing | Document Owner, Group/Work Center Lead
SRF Specification | Document Owner, Group/Work Center Lead
Project Procedure | Document Owner, SRF SME, Project Representative
Project Traveler | Document Owner, SRF SME, Project Representative
Project Drawing | Designer, Checker
Project Specification | Designer, Checker
Project Statement of Work | Document Owner, Project Representative