## HEADER
Document Title | AUPCAV WCD Register
Document Number | AUPCAV-RG-003 | Approval Date: | 2024-03-18
Revision Number | 1 | Periodic Review Date: | N/A
Project Coordinator | Naeem Huque | Department Owner: | SRF Operations
Approved by: | Name: | Signature: | Date:
Project Coordinator | Naeem Huque
Project Execution Process Owner | Tiffany Ganey
Software Group Lead | Valerie Bookwalter
Inventory Group Lead | Phil Denny
Inspection Group Lead | Anne McEwen
Fabrication Group Lead | Tony Reilly
Production Group Lead | Kirk Davis
SRF Department Head | Tony Reilly

## REVISION
Release and Revision History
Rev # | Description of Changes | Change Type | Uploaded Date:
1 | Initial version based on SRF-11-FM-005 WCD Register Template R1 | Initial | DD Mmm YYY
<2> | <brief description of changes> | <Major or Minor> | DD Mmm YYY

## WCD
AUPCAV WCD Register
Last Modified Date: |  | 2024-03-18
Project Coordinator: |  | Naeem Huque
Document Title | Document Type | Document ID | Author / Owner (SME) | Reviewer 1 (SME or WCL) | Reviewer 2 (SRFOPS WCL or Group Lead) | SRFOPS Project Representative | NCR Informative | NCR Dispositioners (Order of Precedence - SRFOPS SME(s), GROUP LEAD, PROJECT COORDINATOR) | D3 Emails (Must include at least 1 SRFOPS SME, WCL and Group Lead) | Estimated Need Date | NOTES
Cavity and Component Documents
Testing and Preparation (VTA)
AUP RFD Bare Cavity Qualification Traveler | TR | AUPCAV-PROC-BAREC-QUAL | Alex Castilla Loeza | Danny Forehand | Kirk Davis | Naeem Huque | areilly | acastill, kdavis, huque | acastill, huque, forehand | 2024-03-25
AUP RFD Dressed Cavity Qualification Traveler | TR | AUPCAV-PROC-DRESDC-QUAL | Alex Castilla Loeza | Danny Forehand | Kirk Davis | Naeem Huque | areilly | acastill, kdavis, huque | acastill, huque, forehand | 2024-06-01
AUP RFD Bare Cavity Incoming Inspection Procedure | PR | AUPCAV-PR-BAREC-INSP | Alex Castilla Loeza | Danny Forehand | Kirk Davis | Naeem Huque |  |  |  | 2024-03-25
AUP RFD Dressed Cavity Incoming Inspection Procedure | PR | AUPCAV-PR-DRESDC-INSP | Alex Castilla Loeza | Danny Forehand | Kirk Davis | Naeem Huque |  |  |  | 2024-06-01
Assembly (CLNRM)
AUP RFD Bare Cavity Cleanroom Assembly | PR | AUPCAV-PR-CLNRM-BAREC-ASSY | Alex Castilla Loeza | Danny Forehand | Kirk Davis | Naeem Huque |  |  |  | 2024-03-25
AUP RFD Dressed Cavity Cleanroom Assembly | PR | AUPCAV-PR-CLNRM-DRESDC-ASSY | Alex Castilla Loeza | Danny Forehand | Kirk Davis | Naeem Huque |  |  |  | 2024-06-01
Vertical Test (VTRF)
AUP RFD Bare Cavity RF Testing Traveler | TR | AUPCAV-VTA-BAREC-VTRF | Alex Castilla Loeza | Peter Owen | Kirk Davis | Naeem Huque | AREILLY | acastill, kdavis, huque | acastill, huque, forehand | 2024-03-25 | PDF Report to CERN
AUP RFD Dressed Cavity RF Testing Traveler | TR | AUPCAV-VTA-DRESDC-VTRF | Alex Castilla Loeza | Peter Owen | Kirk Davis | Naeem Huque | AREILLY | acastill, kdavis, huque | acastill, huque, forehand | 2024-06-01 | PDF Report to CERN
AUP RFD Bare Cavity RF Testing Procedure | PR | AUPCAV-PR-VTA-BAREC-VTRF | Alex Castilla Loeza | Peter Owen | Kirk Davis | Naeem Huque
AUP RFD Dressed Cavity RF Testing Procedure | PR | AUPCAV-PR-VTA-DRESDC-VTRF | Alex Castilla Loeza | Peter Owen | Kirk Davis | Naeem Huque
Leak Check
AUP RFD Cavity Leak Test Procedure | PR | AUPCAV-PR-CLNRM-RFD-LEAK | Alex Castilla Loeza | Danny Forehand | Kirk Davis | Naeem Huque |  |  |  | 2024-03-25
AUP RFD Cavity Leak Test Traveler | TR | AUPCAV-CLNRM-RFD-LEAK | Alex Castilla Loeza | Danny Forehand | Kirk Davis | Naeem Huque | areilly | acastill, kdavis, huque | acastill, huque, forehand | 2024-03-25 | PDF Report to CERN
Chemistry
AUP Bare Cavity HPR Procedure | PR | AUPCAV-PR-CHEM-BAREC-HPR | Alex Castilla Loeza | Alex Wildeson | Kirk Davis | Naeem Huque |  |  |  | 2024-03-25
AUP Dressed Cavity HPR Procedure | PR | AUPCAV-PR-CHEM-DRESD-HPR | Alex Castilla Loeza | Alex Wildeson | Kirk Davis | Naeem Huque |  |  |  | 2024-06-01
AUP RFD Cavity HPR | TR | AUPCAV-CHEM-RFD-HPR | Alex Castilla Loeza | Alex Wildeson | Kirk Davis | Naeem Huque | AREILLY | acastill, kdavis, huque | acastill, huque, wildeson,kdavis | 2024-03-25 | PDF Report to CERN
Inventory
Bare Cavity Inventory Traveler | TR | AUPCAV-INV-BAREC | Mike Dickey | Calvin Barnes | Mike Dickey | Naeem Huque | AREILLY,MDICKEY,CBARNES | ACASTILL,DENNY,HUQUE | AREILLY,MDICKEY,CBARNES,ACASTILL,DENNY,HUQUE | 2024-03-25
Dressed Cavity Inventory Traveler | TR | AUPCAV-INV-DRESDC | Mike Dickey | Calvin Barnes | Mike Dickey | Naeem Huque | AREILLY,MDICKEY,CBARNES | ACASTILL,DENNY,HUQUE | AREILLY,MDICKEY,CBARNES,ACASTILL,DENNY,HUQUE | 2024-03-25
HHOM Coupler Inventory Traveler | TR | AUPCAV-INV-HHOM | Mike Dickey | Calvin Barnes | Mike Dickey | Naeem Huque | AREILLY,MDICKEY,CBARNES | ACASTILL,DENNY,HUQUE | AREILLY,MDICKEY,CBARNES,ACASTILL,DENNY,HUQUE | 2024-03-25
VHOM Coupler Inventory Traveler | TR | AUPCAV-INV-VHOM | Mike Dickey | Calvin Barnes | Mike Dickey | Naeem Huque | AREILLY,MDICKEY,CBARNES | ACASTILL,DENNY,HUQUE | AREILLY,MDICKEY,CBARNES,ACASTILL,DENNY,HUQUE | 2024-03-25
HHOM-FT Inventory Traveler | TR | AUPCAV-INV-HMFT | Mike Dickey | Calvin Barnes | Mike Dickey | Naeem Huque | AREILLY,MDICKEY,CBARNES | ACASTILL,DENNY,HUQUE | AREILLY,MDICKEY,CBARNES,ACASTILL,DENNY,HUQUE | 2024-03-25
Field Antenna Inventory Traveler | TR | AUPCAV-INV-FLANT | Mike Dickey | Calvin Barnes | Mike Dickey | Naeem Huque | AREILLY,MDICKEY,CBARNES | ACASTILL,DENNY,HUQUE | AREILLY,MDICKEY,CBARNES,ACASTILL,DENNY,HUQUE | 2024-03-25
Obsoleted / Archived Documents | [10 empty] | Archived / Obsoleted Date