## HEADER
Document Title | AUPCAV WCD Register
Document Number | AUPCAV-RG-003 | Approval Date: | 2024-03-28
Revision Number | 1 | Periodic Review Date: | N/A
Project Coordinator | Naeem Huque | Department Owner: | SRF Operations
Approved by: | Name: | Signature: | Date:
Project Coordinator | Naeem Huque
Project Execution Process Owner | Tiffany Ganey
Software Group Lead | Valerie Bookwalter
Inventory Group Lead | Phil Denny
Inspection Group Lead | Anne McEwen
Fabrication Group Lead | Tony Reilly
Production Group Lead | Kirk Davis
SRF Department Head | Tony Reilly

## REVISION
Release and Revision History
Rev # | Description of Changes | Change Type | Uploaded Date:
1 | Initial version based on SRF-11-FM-005 WCD Register Template R1 | Initial | DD Mmm YYY
<2> | <brief description of changes> | <Major or Minor> | DD Mmm YYY

## WCD
AUPCAV WCD Register
Last Modified Date: |  | 2024-03-28
Project Coordinator: |  | Naeem Huque
Document Title | Document Type | Document ID | Author / Owner (SME) | Reviewer 1 (SME or WCL) | Reviewer 2 (SRFOPS WCL or Group Lead) | SRFOPS Project Representative | NCR Informative | NCR Dispositioners (Order of Precedence - SRFOPS SME(s), GROUP LEAD, PROJECT COORDINATOR) | D3 Emails (Must include at least 1 SRFOPS SME, WCL and Group Lead) | Estimated Need Date | NOTES
Cavity and Component Documents
Status Board
AUP RFD Bare Cavity Qualification Traveler | STAT BOARD | AUPCAV-PROC-CAV-QUAL-BAREC | N/A | N/A | N/A | Naeem Huque | N/A | N/A | N/A
AUP RFD Dressed Cavity Qualification Traveler | STAT BOARD | AUPCAV-PROC-CAV-QUAL-DRESDC | N/A | N/A | N/A | Naeem Huque | N/A | N/A | N/A
AUP RFD Bare Cavity VTRF Testing REPORT | RPT
AUP RFD Dressed Cavity VTRF Testing REPORT | RPT
AUP RFD Bare Cavity HPR REPORT | RPT
AUP RFD Dressed Cavity HPR REPORT | RPT
AUP RFD Bare Cavity Leak Test REPORT | RPT
AUP RFD Dressed Cavity HPR REPORT | RPT
Incoming RF (TUNE)
AUP RFD Bare Cavity Incoming RF Procedure | PR | AUPCAV-PR-TUNE-CAV-RFIN-BAREC | Alex Castilla Loeza | Danny Forehand | Kirk Davis | Naeem Huque |  |  |  | 2024-04-08
AUP RFD Dressed Cavity Incoming RF Procedure | PR | AUPCAV-PR-TUNE-CAV-RFIN-DRESDC | Alex Castilla Loeza | Danny Forehand | Kirk Davis | Naeem Huque |  |  |  | 2024-06-01
AUP RFD Bare Cavity Incoming RF Traveler | TR | AUPCAV-TUNE-CAV-RFIN-BAREC | Roland Overton | Danny Forehand | Kirk Davis | Naeem Huque | areilly | acastill, kdavis, huque | acastill, huque, forehand
AUP RFD Dressed Cavity Incoming RF Traveler | TR | AUPCAV-TUNE-CAV-RFIN-DRESDC | Roland Overton | Danny Forehand | Kirk Davis | Naeem Huque | areilly | acastill, kdavis, huque | acastill, huque, forehand
Cavity/Parts Cleaning (CHEM)
AUP Bare Cavity Exterior Cleaning | TR | AUPCAV-CHEM-CAV-DEGR-BAREC | River Fiedler | Alex Wildeson | Kirk Davis | Naeem Huque | areilly | acastill, kdavis, huque | acastill, huque, forehand | 2024-04-08
AUP Dressed Cavity Exterior Cleaning | TR | AUPCAV-CHEM-CAV-DEGR-DRESDC | River Fiedler | Alex Wildeson | Kirk Davis | Naeem Huque | areilly | acastill, kdavis, huque | acastill, huque, forehand
High-Pressure Rinse (HPR)
AUP Bare Cavity HPR Procedure | PR | AUPCAV-PR-CHEM-CAV-HPR-BAREC | River Fiedler | Alex Wildeson | Kirk Davis | Naeem Huque |  |  |  | 2024-04-08
AUP Dressed Cavity HPR Procedure | PR | AUPCAV-PR-CHEM-CAV-HPR-DRESD | River Fiedler | Alex Wildeson | Kirk Davis | Naeem Huque |  |  |  | 2024-06-01
AUP Bare Cavity HPR Traveler | TR | AUPCAV-CHEM-CAV-HPR-BAREC | River Fiedler | Alex Wildeson | Kirk Davis | Naeem Huque | AREILLY | acastill, kdavis, huque | acastill, huque, wildeson,kdavis | 2024-04-08 | PDF Report to CERN
AUP Dressed Cavity HPR Traveler | TR | AUPCAV-CHEM-CAV-HPR-DRESDC | River Fiedler | Alex Wildeson | Kirk Davis | Naeem Huque | AREILLY | acastill, kdavis, huque | acastill, huque, wildeson,kdavis | 2024-06-01 | PDF Report to CERN
Cleanroom Assembly (CLNRM)
AUP RFD Bare Cavity Assembly Traveler | TR | AUPCAV-CLNRM-CAV-ASSY-BAREC | Chris Dreyfus | Danny Forehand | Kirk Davis | Naeem Huque | AREILLY | acastill, kdavis, huque | acastill, huque, forehand | 2024-04-08 | PDF Report to CERN
AUP RFD Dressed Cavity Assembly Traveler | TR | AUPCAV-CLNRM-CAV-ASSY-DRESDC | Chris Dreyfus | Danny Forehand | Kirk Davis | Naeem Huque | AREILLY | acastill, kdavis, huque | acastill, huque, forehand | 2024-06-01 | PDF Report to CERN
AUP RFD Bare Cavity Assembly Procedure | PR | AUPCAV-PR-CLNRM-CAV-ASSY-BAREC | Alex Castilla Loeza | Danny Forehand | Kirk Davis | Naeem Huque
AUP RFD Dressed Cavity Assembly Procedure | PR | AUPCAV-PR-CLNRM-CAV-ASSY-DRESDC | Alex Castilla Loeza | Danny Forehand | Kirk Davis | Naeem Huque
Leak Check (LEAK)
AUP Bare Cavity Leak Test Procedure | PR | AUPCAV-PR-CLNRM-CAV-LEAK-BAREC | Chris Dreyfus | Danny Forehand | Kirk Davis | Naeem Huque |  |  |  | 2024-04-08
AUP Bare Cavity Leak Test Traveler | TR | AUPCAV-CLNRM-CAV-LEAK-BAREC | Chris Dreyfus | Danny Forehand | Kirk Davis | Naeem Huque | areilly | acastill, kdavis, huque | acastill, huque, forehand | 2024-04-08 | PDF Report to CERN
AUP Dressed Cavity Leak Test Procedure | PR | AUPCAV-PR-CLNRM-CAV-LEAK-DRESDC | Chris Dreyfus | Danny Forehand | Kirk Davis | Naeem Huque |  |  |  | 2024-06-01
AUP Dressed Cavity Leak Test Traveler | TR | AUPCAV-CLNRM-CAV-LEAK-DRESDC | Chris Dreyfus | Danny Forehand | Kirk Davis | Naeem Huque | areilly | acastill, kdavis, huque | acastill, huque, forehand | 2024-06-01 | PDF Report to CERN
Test Stand Assy (TSTD)
AUP Bare Cavity Test Stand Assy | TR | AUPCAV-CLNRN-CAV-TSTD-BAREC | Alex Castilla Loeza | Chris Dreyfus | Danny Forehand | Naeem Huque | areilly | acastill, kdavis, huque | acastill, huque, forehand | 2024-04-08
AUP Dressed Cavity Test Stand Assy | TR | AUPCAV-CLNRM-CAV-TSTD-DRESDC | Alex Castilla Loeza | Chris Dreyfus | Danny Forehand | Naeem Huque | areilly | acastill, kdavis, huque | acastill, huque, forehand | 2024-06-01
120C Bake (BAKE)
AUP Bare Cavity Bake | TR | AUPCAV-VSA-CAV-BAKE-BAREC | Tommy Doyle | Chris Dreyfus | Danny Forehand | Naeem Huque | areilly | acastill, kdavis, huque | acastill, huque, forehand | 2024-04-08
AUP Dressed Cavity Bake | TR | AUPCAV-VSA-CAV-BAKE-DRESDC | Tommy Doyle | Chris Dreyfus | Danny Forehand | Naeem Huque | areilly | acastill, kdavis, huque | acastill, huque, forehand | 2024-06-01
Vertical Test (VTRF)
AUP RFD Bare Cavity RF Testing Traveler | TR | AUPCAV-VTA-CAV-VTRF-BAREC | Peter Owen | Alex Castilla Loeza | Kirk Davis | Naeem Huque | AREILLY | acastill, kdavis, huque | acastill, huque, kdavis | 2024-04-08 | PDF Report to CERN
AUP RFD Dressed Cavity RF Testing Traveler | TR | AUPCAV-VTA-CAV-VTRF-DRESDC | Peter Owen | Alex Castilla Loeza | Kirk Davis | Naeem Huque | AREILLY | acastill, kdavis, huque | acastill, huque, kdavis | 2024-06-01 | PDF Report to CERN
AUP RFD Bare Cavity RF Testing Procedure | PR | AUPCAV-PR-VTA-CAV-VTRF-BAREC | Alex Castilla Loeza | Peter Owen | Kirk Davis | Naeem Huque
AUP RFD Dressed Cavity RF Testing Procedure | PR | AUPCAV-PR-VTA-CAV-VTRF-DRESDC-VTRF | Alex Castilla Loeza | Peter Owen | Kirk Davis | Naeem Huque
Packing and Shipping (SHIP)
AUP Bare Cavity Shipping | TR | AUPCAV-CMA-CAV-SHIP-BAREC | Naeem Huque | Jared Martin | John Fischer | Naeem Huque | areilly | HUQUE, FISCHER | HUQUE, FISCHER | 2024-04-08
AUP Dressed Cavity Shipping | TR | AUPCAV-CMA-CAV-SHIP-DRESDC | Naeem Huque | Jared Martin | John Fischer | Naeem Huque | areilly | HUQUE, FISCHER | HUQUE, FISCHER | 2024-06-01
Inventory
Bare Cavity Inventory Traveler | TR | AUPCAV-INV-BAREC | Mike Dickey | Calvin Barnes | Phil Denny | Naeem Huque | AREILLY,MDICKEY,CBARNES | ACASTILL,DENNY,HUQUE | AREILLY,MDICKEY,CBARNES,ACASTILL,DENNY,HUQUE | 2024-04-08
Dressed Cavity Inventory Traveler | TR | AUPCAV-INV-DRESDC | Mike Dickey | Calvin Barnes | Phil Denny | Naeem Huque | AREILLY,MDICKEY,CBARNES | ACASTILL,DENNY,HUQUE | AREILLY,MDICKEY,CBARNES,ACASTILL,DENNY,HUQUE | 2024-04-08
Obsoleted / Archived Documents | [10 empty] | Archived / Obsoleted Date