## Slide 1: Hong’s request (delete slide)
Could you please help to contribute 2-3 slides on Non-conformance issues at each Lab to the QA presentation for CD-2/3 Director Review by Tuesday 4/2?
Suggestions:
  Status: total, open, closed? What components/subsystems? Category (material, method, etc.)?
  A list of top 5 major NCRs, impacts (cost & schedule), along with root cause analysis and corrective actions
Any other highlights that you like to include are welcome.
Added 4/2/24:
  Ashley, could you please provide Status: total, open, closed? What components/subsystems? Category (material, method, etc.)?
    Added slide 4 in response to this, tried to match Fermi’s
  For all Labs, could you please prepare for how the numbers and nature (characteristics) of HE NCRs are compared to LCLS-II and explanation the differences in case this question is asked?
J1.3-22 Beamline leak (CAPA-051)
J1.3-23 coupler out of tune (CAPA-052)
Upstream bellows (CAPA-022)
Chipped FPCs (CAPA-013)
Cavity bellows damage (CAPA-038)

## Slide 2: JLab SRF Operations Quality Management System (QMS)
SRF Operations Quality Policy
Quality is our commitment to deliver world-class SRF products and services that are worthy of our customers trust by
Enabling and empowering our people to build safety, reliability, quality, and compliance into our products, technologies, and services
Delivering products to plan that support system reliability, availability, and that yield a great customer experience
Measuring our quality objectives and driving systemic continual improvement
Proactively and transparently engaging our customers
SRF Ops has enhanced the Quality Program at JLab with a QMS modelled after the ISO 9001 Standard that includes:
  4 Core Business Processes and 10 Support Processes:
    Project Execution, Vendor Management, Inventory & Traceability, Production
    Leadership, Calibration, Organizational Knowledge, Competence, Infrastructure, Records Management,
    Document Management, Nonconforming Products, Internal Audit, Corrective Action
  NCR – Nonconforming Product Report
    Ensures nonconforming products are identified, segregated, evaluated, and appropriately dispositioned
    Pansophy software used to manage our NCRs and Work Control Documents
  CAPA – Corrective and Preventative Action Report
    Used to identify, investigate root causes, and track actions to resolve quality issues
    DocuShare software used for control of records and procedures
SRF Ops was ISO 9001:2015 Certified in May 2023

## Slide 3: JLab LCLS-II HE Nonconformity Report (NCR) Counts
Data retrieved 3-Apr-2024
NCR Open/Closed Status L2HE NCR Report Summary |  |  | 
Area | Open | Closed | Total
INSP | 1 | 264 | 265
VTA | 4 | 105 | 109
CLNRM | 1 | 73 | 74
CMA | 4 | 59 | 63
INV | 0 | 30 | 30
LERF | 4 | 13 | 17
CHEM | 0 | 9 | 9
CWI | 0 | 5 | 5
TUNE | 0 | 2 | 2
Total | 14 | 560 | 574
NCRs are generated, dispositioned, and communicated to SLAC & PL
Risks are assessed through multiple channels, including CTB, quality meetings with SLAC, Jlab staff, and PLs
CAPAs are generated for programmatic and systemic nonconformities
* OTHER NCR Classification has been analyzed and is being utilized appropriately.
Chart: NCR Final Dispositions
| Use As Is | Conforming | Return To Vendor | Reject | TBD (Open)
 | 39 | 98 | 7 | 16 | 7
 | 26 | 10 | 7 | 11 | 2
 | 199 | 37 | 81 | 29 | 5

## Slide 4: JLab LCLS-II HE High Impact NCRs
J1.3-23 coupler out of tune
  Impact: ~$1k, ~3 weeks delay
  Causal Analysis: Potentially insulating vacuum, issue has not reoccurred
  Corrective Action: Procedure in development with SMEs for adjusting tuning while warm
Upstream bellows
  Impact: ~$15k, ~2-day delay to production
  Causal Analysis: Vendor tooling
  Corrective Action: Update to inspection travelers and SOW to vendor, replacement bellows ordered
Chipped FPCs
  Impact: ~$12k per FPC, ~1 month delay
  Causal Analysis: Material weakness or material handling suspected due to tight tolerances between top hat and delicate ceramic
  Corrective Action: Returned damaged FPCs to vendor for repair, fabricated tooling, increased inspection activities

## Slide 5: JLab LCLS-II HE High Impact NCRs
J1.3-22 Beamline leak
  Impact: ~$1M, ~2-3-month production extension,
  Causal Analysis: Component failure - feedthrough leaked, investigation with vendor ongoing
  Corrective Action: Rebuild J1.3-22, component actions TBD after further analysis
Cavity bellows damage
  Impact: ~$30k per cavity, ~1 month delay
  Causal Analysis: Handling during processing suspected
  Corrective Action: Bellows covers re-designed to be compatible with chemistry activities and tooling in order to remain in place throughout processing, testing, and string build
We are leveraging our QMS to continuously learn and improve

## Slide 6: JLab LCLS-II vs L2HE NCRs – Overall counts less for HE
Chart: NCRs Issued Per Month - L2HE
| Mar | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | 2021 | 2022 | 2023 | 2024
Total | 1 | 14 | 14 | 22 | 7 | 12 | 6 | 21 | 11 | 38 | 16 | 18 | 18 | 8 | 47 | 23 | 34 | 12 | 23 | 11 | 11 | 9 | 13 | 15 | 18 | 12 | 14 | 22 | 12 | 20 | 11 | 9 | 5 | 11 | 19 | 16 | 1
Chart: NCRs Issued Per Month - LCLS-II
| Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Oct | Nov | Jan | Apr | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Total | 1 | 26 | 43 | 33 | 40 | 108 | 150 | 76 | 91 | 32 | 36 | 72 | 46 | 38 | 40 | 75 | 45 | 36 | 65 | 59 | 40 | 44 | 30 | 58 | 64 | 27 | 14 | 45 | 27 | 27 | 35 | 77 | 26 | 12 | 4 | 33 | 21 | 48 | 31 | 39 | 17 | 14 | 10 | 22 | 19 | 16 | 18 | 8 | 5 | 9 | 2 | 1 | 1 | 3 | 2 | 9 | 2 | 1 | 3
Note: NCR Classifications with a value of “0” have been removed for clarity.
Chart: NCR Classifications by CMSN - LCLS-II
| J1.3-02 | J1.3-03 | J1.3-04 | J1.3-05 | J1.3-06 | J1.3-06R | J1.3-07 | J1.3-08 | J1.3-09 | J1.3-09R | J1.3-13 | J1.3-15
CMTF RF PERFORMANCE | 4 | 2 | 5 | 6 | 3 | 1
RF TEST FAILURE | 4 | 2 | 5 | 5 | 1
RF CMTF | 4 | 3 | 1
MECHANICAL | 1 | 2 | 1 | 1 | 1 | 1
DIMENSIONAL | 1 | 1 | 1 | 1 | 1 | 1
VACUUM | 1 | 1 | 1 | 1
INSTRUMENTATION | 1 | 1 | 1 | 1
LEAK TEST FAILURE | 1 | 1
OTHER | 1 | 1
FLATNESS | 1
VTA RF PERFORMANCE | 1
Data retrieved 3-Apr-2024
Chart: NCR Classifications by CMSN - L2HE
| J1.3-22 Total | J1.3-23 Total | J1.3-24 Total | J1.3-25 Total | J1.3-26 Total | J1.3-28 Total
CMTF RF PERFORMANCE | 0 | 7 | 2 | 0 | 0 | 0
RF CMTF | 0 | 5 | 2 | 0 | 0 | 1
RF TEST FAILURE | 0 | 5 | 2 | 0 | 0 | 0
MECHANICAL | 0 | 4 | 2 | 0 | 0 | 1
INSTRUMENTATION | 0 | 2 | 2 | 0 | 1 | 0
VACUUM | 2 | 1 | 2 | 0 | 0 | 1
OTHER | 0 | 2 | 2 | 0 | 0 | 0
SCRATCHES | 0 | 0 | 0 | 1 | 0 | 1
LEAK TEST FAILURE | 0 | 0 | 1 | 0 | 0 | 0