## Sheet1
C75 Components Tracker Updated 4/14/2025
End Dishes | Location | Status | Updated | Notes
SN# 1001 | Inventory | NCR#'s 1029, 1030 | 2025-04-08 | Scratch in seal area. Needs lapped
SN# 1002 | Clean Room | Good | 2025-04-02 | For pair build 032-045
SN# 1003 | Inventory | NCR# 1032 | 2025-04-08 | Surface finish OOT. Needs lapped
SN# 1004 | Inventory | NCR#'s 1033, 1034, 1035 | 2025-04-08 | Scratch in seal area. Needs lapped
SN# 1005 | Inventory | Good | 2025-04-02 | Ready for pair use.
SN# 1006 | Inventory | Good | 2025-04-02 | Ready for pair use.
SN# 1008 | Inventory | NCR#'s 1039 | 2025-04-08 | Scratch in seal area. Needs lapped
SN# 1009 | Clean Room | Good | 2025-04-02 | For pair build 032-045
SN# 177 | Tuning Room | Needs to be re-processed | 2025-04-08 | Recently disassmbled. Needs full reprocessing
SN# 179 | Tuning Room | Needs to be re-processed | 2025-04-08 | Recently disassmbled. Needs full reprocessing
SN# 008 | RAM Cabinet | Needs to be re-processed | 2025-04-08 | Recently disassmbled. Needs full reprocessing
SN# 013 | RAM Cabinet | Needs to be re-processed | 2025-04-08 | Recently disassmbled. Needs full reprocessing
164 | RAM Cabinet | Needs re-processing and new serial number | 2025-04-08 | Recently disassmbled. Needs full reprocessing
53 | RAM Cabinet | Needs re-processing and new serial number | 2025-04-08 | Recently disassmbled. Needs full reprocessing
55 | RAM Cabinet | Needs re-processing and new serial number | 2025-04-08 | Recently disassmbled. Needs full reprocessing
SN# 010 | RAM Cabinet | Needs re-processed | 2025-04-08 | Recently disassmbled. Needs full reprocessing
SN# 014 | RAM Cabinet | Needs re-processed | 2025-04-08 | Recently disassmbled. Needs full reprocessing
SN# 057 | RAM Cabinet | NCR for "dings" in bellows | 2025-04-08 | Bellows passed leak check. Needs NCR cleared before use
41 | RAM Cabinet | Needs re-processing and new serial number | 2025-04-08 | Recently disassmbled. Needs full reprocessing
42 | RAM Cabinet | Needs re-processing and new serial number | 2025-04-08 | Recently disassmbled. Needs full reprocessing
48 | RAM Cabinet | Needs re-processing and new serial number | 2025-04-08 | Recently disassmbled. Needs full reprocessing
52 | RAM Cabinet | Needs re-processing and new serial number | 2025-04-08 | Recently disassmbled. Needs full reprocessing
58 | RAM Cabinet | Needs re-processing and new serial number | 2025-04-08 | Recently disassmbled. Needs full reprocessing
62 | RAM Cabinet | Needs re-processing and new serial number | 2025-04-08 | Recently disassmbled. Needs full reprocessing
168 | RAM Cabinet | Needs re-processing and new serial number | 2025-04-08 | Recently disassmbled. Needs full reprocessing
SN# 252 | RAM Cabinet | Needs re-processing and new serial number | 2025-04-08 | Recently disassmbled. Needs full reprocessing
Elbows | Location | Status | Updated | Notes
HOME 284 | Clean Room | Good | 2025-04-02 | For pair build 032-045
HOME 285 | Clean Room | Good | 2025-04-02 | For pair build 032-045
HOME 287 | Clean Room | Good | 2025-04-02 | For pair build 032-045
HOME 291 | Clean Room | Good | 2025-04-02 | For pair build 032-045
HOME 288 | CMM Shelf | Initial inspection post disassembly | 2025-04-02 | Needs Lapping, BCP, Final CMM
HOME 289 | CMM Shelf | Initial inspection post disassembly | 2025-04-02 | Needs Lapping, BCP, Final CMM
HOME 290 | CMM Shelf | Initial inspection post disassembly | 2025-04-02 | Needs Lapping, BCP, Final CMM
HOME 296 | CMM Shelf | Initial inspection post disassembly | 2025-04-02 | Needs Lapping, BCP, Final CMM
HOME 292 | CMM Shelf | NCR# 1105 | 2025-04-02 | Cavity side, inner surface has several scratches & light dings.
HOME 293 | CMM Shelf | Initial inspection post disassembly | 2025-04-02 | Needs Lapping, BCP, Final CMM
HOME 294 | CMM Shelf | Initial inspection post disassembly | 2025-04-02 | Needs Lapping, BCP, Final CMM
HOME 295 | CMM Shelf | Initial inspection post disassembly | 2025-04-02 | Needs Lapping, BCP, Final CMM
HOME 72 | Tuning Room | Disassembled from CM-06, Needs re-processing and new serial number | 2025-04-02 | Recently disassembled, Needs re-processing
HOME 101 | Tuning Room | Disassembled from CM-06, Needs re-processing and new serial number | 2025-04-02 | Recently disassembled, Needs re-processing
HOME 255 | Tuning Room | Disassembled from CM-06, Needs re-processing and new serial number | 2025-04-02 | Recently disassembled, Needs re-processing
HOME 112 | Tuning Room | Disassembled from CM-06, Needs re-processing and new serial number | 2025-04-02 | Recently disassembled, Needs re-processing
HOME 130 | Tuning Room | Disassembled from CM-06, Needs re-processing and new serial number | 2025-04-02 | Recently disassembled, Needs re-processing
HOME 161 | Tuning Room | Disassembled from CM-06, Needs re-processing and new serial number | 2025-04-02 | Recently disassembled, Needs re-processing
HOME 177 | Tuning Room | Disassembled from CM-06, Needs re-processing and new serial number | 2025-04-02 | Recently disassembled, Needs re-processing
HOME 57 | Tuning Room | Disassembled from CM-06, Needs re-processing and new serial number | 2025-04-02 | Recently disassembled, Needs re-processing
HOME 130 | Tuning Room | Disassembled from CM-06, Needs re-processing and new serial number | 2025-04-02 | Recently disassembled, Needs re-processing
HOM Loads | Location | Status | Updated | Notes
HOML 327 | Clean Room | Good | 2025-04-02 | For pair build 032-045
HOML-328 | CMM Shelf | Good | 2025-04-02 | Waiting for next pair build
HOML-329 | CMM Shelf | Good | 2025-04-02 | Waiting for next pair build
HOML-330 | CMM Shelf | Good | 2025-04-02 | Waiting for next pair build
HOML 331 | Clean Room | Good | 2025-04-02 | For pair build 032-045
HOML-332 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-333 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-334 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-335 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-336 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-337 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-338 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-339 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-340 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-341 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-342 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-343 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-344 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-345 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-346 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-347 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-348 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-349 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-350 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-351 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-352 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-354 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML-355 | CMM Shelf | Recently disassembled, Needs re-processing | 2025-04-08 | Waiting for CMM inspection
HOML 1008 | Clean Room | Good | 2025-04-02 | For pair build 032-045
HOML 1009 | Tuning room | Disassembled from pair 032-045 | 2025-04-02 | Scratch in seal path? Need confirmation from CMM before use
HOML 1010 | Clean Room | Good | 2025-04-02 | For pair build 032-045
HOML 1011 | Tuning Room | Leaks? | 2025-04-02 | Load-Elbow joint leaked
HOML 1012 | Tuning Room | Chipped ceramic | 2025-04-02 | Needs to be dispositioned
HOML flanges 1016-1035 are ready for ceramic brazing |  |  | 2025-04-08 | Are ceramics qualified and ready to be brazed?
Inner Adapters | Location | Status | Updated | Notes
Q198 | Tuning Room | NCR for flange "A" flatness OOT. | 2025-04-02 | Needs minor lapping, BCP, final CMM
Q165 | Tuning Room | Waiting final CMM | 2025-04-08 | Has been lapped, BCP'd, and de-greased. Needs final CMM before usage.
Q711 | Tuning Room | Needs stretching/shrinking | 2025-04-02 | Initial inspection following fabrication. Needs stackup numbers before stretching/shrinking
Q712 | Tuning Room | NCR #'s 1082, 1083 for dimensional issues. | 2025-04-02 | Initial inspection following fabrication. Needs stackup numbers before stretching/shrinking
Q713 | Tuning Room | Needs stretching/shrinking | 2025-04-02 | Initial inspection following fabrication. Needs stackup numbers before stretching/shrinking
Q714 | Tuning Room | Needs stretching/shrinking | 2025-04-02 | Initial inspection following fabrication. Needs stackup numbers before stretching/shrinking
Q715 | Tuning Room | Needs leak check | 2025-04-02 | Initial inspection following fabrication. Needs stackup numbers before stretching/shrinking.
Q47 | Tuning Room | Needs to be re-processed | 2025-04-08 | Re-processing includes: CMM, Lap, BCP, De-grease, Final CMM
Q52 | Tuning Room | Needs to be re-processed | 2025-04-08 | Re-processing includes: CMM, Lap, BCP, De-grease, Final CMM
Q85 | RAM Cabinet | Needs to be re-processed | 2025-04-08 | Re-processing includes: CMM, Lap, BCP, De-grease, Final CMM
Q99 | RAM Cabinet | Needs to be re-processed | 2025-04-08 | Re-processing includes: CMM, Lap, BCP, De-grease, Final CMM
Q116 | RAM Cabinet | Needs to be re-processed | 2025-04-08 | Re-processing includes: CMM, Lap, BCP, De-grease, Final CMM
Q123 | RAM Cabinet | Needs to be re-processed | 2025-04-08 | Re-processing includes: CMM, Lap, BCP, De-grease, Final CMM
Q133 | RAM Cabinet | Needs to be re-processed | 2025-04-08 | Re-processing includes: CMM, Lap, BCP, De-grease, Final CMM