## Travelers_Age
Pulled: | 2025-04-08
ACTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | Trav Open > 6mo | % Trav Open > 6mo | NCR Open | NCR Closed | NCR Total | NCR Open > 6mo | D3 Open | D3 Closed | D3 Total | D3 Open > 6mo | Total Open | Total Closed | Grand Total | Total Open > 6mo | % Closed | % Open > 6mo |  | Trav Open
| AUPCAV | 6 | 43 | 49 | 0 | 0% | 1 | 10 | 11 | 0 | 1 | 7 | 8 | 0 | 8 | 60 | 68 | 0 | 88.24% | 0 |  | 2
| AUPPS | 14 | 443 | 457 | 12 | 85.71% | 7 | 135 | 142 | 0 | 0 | 7 | 7 | 0 | 21 | 585 | 606 | 12 | 96.53% | 57.14% |  | 16
| C100R | 17 | 3364 | 3381 | 0 | 0% | 31 | 194 | 225 | 1 | 0 | 132 | 132 | 0 | 48 | 3690 | 3738 | 1 | 98.72% | 2.08% |  | 40
| EIC197 | 35 | 1 | 36 | 1 | 2.86% | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 35 | 2 | 37 | 1 | 5.41% | 2.86% |  | 6
| EIC591SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| EICMAG | 0 | 121 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 121 | 0 | 100% | 0 |  | 0
| EICRD | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 100% | 0 |  | 0
| ER5C | 88 | 7295 | 7383 | 35 | 39.77% | 53 | 922 | 975 | 32 | 1 | 239 | 240 | 0 | 142 | 8456 | 8598 | 67 | 98.35% | 47.18% |  | 94
| L2HE | 53 | 5701 | 5754 | 8 | 15.09% | 14 | 666 | 680 | 3 | 5 | 214 | 219 | 3 | 72 | 6581 | 6653 | 14 | 98.92% | 19.44% |  | 23
| NB3SN | 2 | 148 | 150 | 1 | 50% | 10 | 15 | 25 | 10 | 2 | 7 | 9 | 2 | 14 | 170 | 184 | 13 | 92.39% | 92.86% |  | 2
| PLACLN | 11 | 5 | 16 | 7 | 63.64% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 5 | 16 | 7 | 31.25% | 63.64% |  | 11
| SRFRD | 297 | 2129 | 2426 | 124 | 41.75% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297 | 2129 | 2426 | 124 | 87.76% | 41.75% |  | 168
| SRFTRNG | 1 | 0 | 1 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0% | 0 |  | 0
| STP | 27 | 929 | 956 | 27 | 100% | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 27 | 933 | 960 | 27 | 97.19% | 100% |  | 27
| WMGRDR | 6 | 6 | 12 | 6 | 100% | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 6 | 8 | 14 | 6 | 57.14% | 100% |  | 6
| TOTALS | 557 | 20185 | 20742 | 221 | 39.68% | 116 | 1946 | 2062 | 46 | 9 | 611 | 620 | 5 | 682 | 22742 | 23424 | 272 | 97.09% | 39.88% |  | 395
|  |  | <2wks | 2-4wks | 4wks-1qtr | 1qtr-6mo | 6mo-1yr | >1yr
| PROJ | Total Travelers Open | <1/2mo | 1/2-1mo | 1-3mo | 3-6mo | 6-12mo | >12mo | Total Check | Traveler Open | PROJ | Open over 6 mo | %
| AUPCAV | 6 | 1 | 0 | 3 | 2 | 0 | 0 | TRUE | 6 | AUPCAV | 0 | 0%
| AUPPS | 14 | 0 | 0 | 2 | 0 | 1 | 11 | TRUE | 14 | AUPPS | 12 | 85.71%
| C100R | 17 | 8 | 0 | 11 | 1 | 20 | 0 | ERROR | 40 | C100R | 20 | 117.6%
| EIC197 | 35 | 0 | 0 | 6 | 1 | 0 | 0 | ERROR | 7 | EICCRB | 0 | 0%
| EIC591SC | 0 | [6 empty] | TRUE | 0 | EICCELL | 0 | #DIV/0!
| ER5C | 88 | 15 | 4 | 6 | 24 | 22 | 18 | ERROR | 89 | ER5C | 40 | 45.45%
| L2HE | 53 | 5 | 0 | 34 | 5 | 8 | 2 | ERROR | 54 | L2HE | 10 | 18.87%
| Total | 213 | 29 | 4 | 62 | 33 | 51 | 31 |  | 210 | Total | 82 | 38.5%
|  | 100% | 13.62% | 1.878% | 29.11% | 15.49% | 23.94% | 14.55%
| Open Travelers | [6 empty] | 2024 | [5 empty] | 2024-07-11
| PROJ | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov-24 | Dec-24 | Jan-25 | 25-Feb | Mar-25 | 25-Apr | May-25 | 25-Jun | Jul-25 | 25-Aug | Sep-25 | 25-Oct | Nov-25 | 25-Dec
| AUPCAV | [9 empty] | 3 | 4 | 5 | 6 | 8 | 2 | 0 | 0 | 0 | 2 | 4 | 5 | 6
| AUPPS | 29 | 30 | 33 | 43 | 29 | 40 | 29 | 29 | 35 | 29 | 29 | 29 | 29 | 29 | 38 | 38 | 39 | 16 | 16 | 17 | 14 | 14
| C100R | 63 | 62 | 28 | 41 | 48 | 29 | 37 | 34 | 41 | 36 | 36 | 40 | 46 | 28 | 23 | 43 | 38 | 35 | 40 | 41 | 39 | 17
| EIC197 | [9 empty] | 0 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 6 | 7 | 7 | 35
| EIC591SC | [9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ER5C | 144 | 110 | 113 | 105 | 121 | 125 | 59 | 46 | 86 | 106 | 104 | 152 | 142 | 126 | 116 | 115 | 104 | 104 | 94 | 97 | 90 | 88
| L2HE | 58 | 72 | 74 | 62 | 69 | 70 | 42 | 43 | 61 | 47 | 52 | 55 | 42 | 22 | 15 | 16 | 13 | 28 | 23 | 52 | 54 | 53
| TOTAL | 265 | 289 | 256 | 259 | 291 | 259 | 138 | 123 | 188 | 221 | 225 | 281 | 265 | 213 | 195 | 213 | 195 | 184 | 181 | 218 | 209 | 213 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025
Open Travelers
| PROJ | 25-Jan | 25-Feb | 25-Mar | 25-Apr | 25-May | 25-Jun | 25-Jul | 25-Aug | 25-Sep | 25-Oct | 25-Nov | 25-Dec
AUPCAV
AUPPS
C100R
EIC197
EIC591SC
ER5C
L2HE
TOTAL
5-Aug-24: Archive SNSPPU and NB3SN
| Open Travelers | [6 empty] | 2024 | [5 empty] | 2024-07-11
| PROJ | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov-24 | Dec-24
| AUPCAV | [9 empty] | 3 | 4 | 5 | 6 | 8
| AUPPS | 29 | 30 | 33 | 43 | 29 | 40 | 29 | 29 | 35 | 29 | 29 | 29 | 29 | 29
| C100R | 63 | 62 | 28 | 41 | 48 | 29 | 37 | 34 | 41 | 36 | 36 | 40 | 46 | 28
| EIC197 | [9 empty] | 0 | 0 |  | 0 | 0
| EIC591SC | [9 empty] | 0 | 0 |  | 0 | 0
| ER5C | 144 | 110 | 113 | 105 | 121 | 125 | 59 | 46 | 86 | 106 | 104 | 152 | 142 | 126
| L2HE | 58 | 72 | 74 | 62 | 69 | 70 | 42 | 43 | 61 | 47 | 52 | 55 | 42 | 22
| SNSPPU | 11 | 11 | 6 | 7 | 5 | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NB3SN | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6
| TOTAL | 281 | 289 | 256 | 259 | 291 | 259 | 143 | 128 | 194 | 227 | 231 | 287 | 271 | 213 | 0 | 0 | 0 | 0

## NCRs_Age
|  |  | <2wks | 2-4wks | 4wks-1qtr | 1qtr-6mo | 6mo-1yr | >1yr
| PROJ | Total NCR Open | <1/2mo | 1/2-1mo | 1-3mo | 3-6mo | 6-12mo | >12mo | Total Check
| AUPCAV | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| AUPPS | 7 | 5 | 0 | 6 | 3 | 0 | 0 | 14
| C100R | 31 | 4 | 2 | 6 | 4 | 0 | 1 | 17
| EIC197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EIC591SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ER5C | 53 | 1 | 7 | 5 | 16 | 16 | 8 | 53
| L2HE | 14 | 0 | 0 | 5 | 2 | 2 | 1 | 10
| TOTAL | 106 | 10 | 9 | 23 | 25 | 18 | 10 | 95
|  |  | 9.434% | 8.491% | 21.7% | 23.58% | 16.98% | 9.434% | 89.62%
| Total Open NCRs | 2024 |  |  | Added AUPCAV, EICCRB, EICELL in May reporting, SNSPPU Complete | [8 empty] | 2025
| PROJ | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov-24 | Dec-24 | 2025-01-25 | 2025-02-25 | 2025-03-25 | 2025-04-25 | 2025-05-25 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25
| AUPCAV |  |  |  |  | 1 | 3 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| AUPPS | 0 | 4 | 4 | 15 | 4 | 5 | 5 | 12 | 19 | 3 | 1 | 2 | 7 | 15 | 16 | 7
| C100R | 2 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 17 | 3 | 1 | 10 | 18 | 23 | 31
| EIC197 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EIC591SC |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ER5C | 36 | 41 | 62 | 66 | 76 | 74 | 75 | 83 | 53 | 61 | 68 | 58 | 52 | 49 | 53 | 88
| L2HE | 22 | 17 | 12 | 11 | 21 | 29 | 27 | 20 | 19 | 10 | 5 | 8 | 9 | 17 | 14 | 53
| TOTAL | 60 | 65 | 79 | 93 | 103 | 113 | 114 | 120 | 94 | 91 | 77 | 69 | 78 | 100 | 107 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pulled: | 2025-04-08
ACTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | Trav Open > 6mo | % Trav Open > 6mo | NCR Open | NCR Closed | NCR Total | NCR Open > 6mo | D3 Open | D3 Closed | D3 Total | D3 Open > 6mo | Total Open | Total Closed | Grand Total | Total Open > 6mo | % Closed | % Open > 6mo
| AUPCAV | 6 | 43 | 49 | 0 | 0% | 1 | 10 | 11 | 0 | 1 | 7 | 8 | 0 | 8 | 60 | 68 | 0 | 88.24% | 0
| AUPPS | 14 | 443 | 457 | 12 | 85.71% | 7 | 135 | 142 | 0 | 0 | 7 | 7 | 0 | 21 | 585 | 606 | 12 | 96.53% | 57.14%
| C100R | 17 | 3364 | 3381 | 0 | 0% | 31 | 194 | 225 | 1 | 0 | 132 | 132 | 0 | 48 | 3690 | 3738 | 1 | 98.72% | 2.08%
| EIC197 | 35 | 1 | 36 | 1 | 2.86% | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 35 | 2 | 37 | 1 | 5.41% | 2.86%
| EIC591SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EICMAG | 0 | 121 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 121 | 0 | 100% | 0
| EICRD | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 100% | 0
| ER5C | 88 | 7295 | 7383 | 35 | 39.77% | 53 | 922 | 975 | 32 | 1 | 239 | 240 | 0 | 142 | 8456 | 8598 | 67 | 98.35% | 47.18%
| L2HE | 53 | 5701 | 5754 | 8 | 15.09% | 14 | 666 | 680 | 3 | 5 | 214 | 219 | 3 | 72 | 6581 | 6653 | 14 | 98.92% | 19.44%
| NB3SN | 2 | 148 | 150 | 1 | 50% | 10 | 15 | 25 | 10 | 2 | 7 | 9 | 2 | 14 | 170 | 184 | 13 | 92.39% | 92.86%
| PLACLN | 11 | 5 | 16 | 7 | 63.64% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 5 | 16 | 7 | 31.25% | 63.64%
| SRFRD | 297 | 2129 | 2426 | 124 | 41.75% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297 | 2129 | 2426 | 124 | 87.76% | 41.75%
| SRFTRNG | 1 | 0 | 1 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0% | 0
| STP | 27 | 929 | 956 | 27 | 100% | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 27 | 933 | 960 | 27 | 97.19% | 100%
| WMGRDR | 6 | 6 | 12 | 6 | 100% | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 6 | 8 | 14 | 6 | 57.14% | 100%
| TOTALS | 557 | 20185 | 20742 | 221 | 39.68% | 116 | 1946 | 2062 | 46 | 9 | 611 | 620 | 5 | 682 | 22742 | 23424 | 272 | 97.09% | 39.88%
Total Open NCRs | 2023
PROJ | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | Sep-23 | Oct-23 | Nov-23 | Dec-23
AUPCAV
AUPPS | 0 | 1 | 3 | 3 | 3 | 2 | 3 | 6 | 4 | 0 | 0 | 0
C100R | 2 | 4 | 1 | 1 | 3 | 3 | 4 | 4 | 0 | 2 | 9 | 5
EIC197
EIC591SC
ER5C | 46 | 19 | 19 | 29 | 33 | 33 | 37 | 38 | 43 | 33 | 33 | 38
L2HE | 57 | 57 | 40 | 44 | 40 | 37 | 31 | 24 | 26 | 29 | 23 | 23
TOTAL | 105 | 81 | 63 | 77 | 79 | 75 | 75 | 72 | 73 | 64 | 65 | 66

## D3
Data pulled: | 2025-04-08
| ACTIVE PROJECTS ONLY | [20 empty] | Copy/Paste
| PROJ | Trav Open | Trav Closed | Trav Total | Trav Open > 6mo | % Trav Open > 6mo | NCR Open | NCR Closed | NCR Total | NCR Open > 6mo | D3 Open | D3 Closed | D3 Total | D3 Open > 6mo | Total Open | Total Closed | Grand Total | Total Open > 6mo | % Closed | % Open > 6mo |  | PROJ
| AUPCAV | 6 | 43 | 49 | 0 | 0% | 1 | 10 | 11 | 0 | 1 | 7 | 8 | 0 | 8 | 60 | 68 | 0 | 88.24% | 0 |  | AUPCAV | 1
| AUPPS | 14 | 443 | 457 | 12 | 85.71% | 7 | 135 | 142 | 0 | 0 | 7 | 7 | 0 | 21 | 585 | 606 | 12 | 96.53% | 57.14% |  | AUPPS | 0
| C100R | 17 | 3364 | 3381 | 0 | 0% | 31 | 194 | 225 | 1 | 0 | 132 | 132 | 0 | 48 | 3690 | 3738 | 1 | 98.72% | 2.08% |  | C100R | 0
| EIC197 | 35 | 1 | 36 | 1 | 2.86% | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 35 | 2 | 37 | 1 | 5.41% | 2.86% |  | EIC197 | 0
| EIC591SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | EIC591SC | 0
| EICMAG | 0 | 121 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 121 | 0 | 100% | 0 |  | ER5C | 1
| EICRD | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 100% | 0 |  | L2HE | 5
| ER5C | 88 | 7295 | 7383 | 35 | 39.77% | 53 | 922 | 975 | 32 | 1 | 239 | 240 | 0 | 142 | 8456 | 8598 | 67 | 98.35% | 47.18% |  | Total | 7
| L2HE | 53 | 5701 | 5754 | 8 | 15.09% | 14 | 666 | 680 | 3 | 5 | 214 | 219 | 3 | 72 | 6581 | 6653 | 14 | 98.92% | 19.44%
| NB3SN | 2 | 148 | 150 | 1 | 50% | 10 | 15 | 25 | 10 | 2 | 7 | 9 | 2 | 14 | 170 | 184 | 13 | 92.39% | 92.86%
| PLACLN | 11 | 5 | 16 | 7 | 63.64% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 5 | 16 | 7 | 31.25% | 63.64%
| SRFRD | 297 | 2129 | 2426 | 124 | 41.75% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297 | 2129 | 2426 | 124 | 87.76% | 41.75%
| SRFTRNG | 1 | 0 | 1 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0% | 0
| STP | 27 | 929 | 956 | 27 | 100% | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 27 | 933 | 960 | 27 | 97.19% | 100%
| WMGRDR | 6 | 6 | 12 | 6 | 100% | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 6 | 8 | 14 | 6 | 57.14% | 100%
| TOTALS | 557 | 20185 | 20742 | 221 | 39.68% | 116 | 1946 | 2062 | 46 | 9 | 611 | 620 | 5 | 682 | 22742 | 23424 | 272 | 97.09% | 39.88%
|  |  | 2023 | [5 empty] | 2024
| PROJ | Total D3s Over Proj Life | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov-24 | Dec-24
| NB3SN | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SNSPPU | 186 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| PROJ | Total D3s Over Proj Life | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov-24 | Dec-24 | 2025-01-25 | 2025-02-25 | 2025-03-25 | 2025-04-25 | 2025-05-25 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25
| AUPCAV | 8 | [10 empty] | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| AUPPS | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| C100R | 132 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 2 | 1 | 1 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| EIC197 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EIC591SC | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ER5C | 240 | 13 | 14 | 10 | 5 | 7 | 4 | 6 | 8 | 15 | 15 | 20 | 20 | 20 | 16 | 5 | 5 | 4 | 3 | 1 | 1 | 1 | 1
| L2HE | 219 | 21 | 22 | 1 | 2 | 3 | 19 | 9 | 9 | 7 | 7 | 8 | 6 | 3 | 3 | 5 | 4 | 3 | 5 | 6 | 3 | 3 | 5
| Total | 606 | 34 | 36 | 11 | 7 | 10 | 24 | 18 | 19 | 23 | 23 | 33 | 31 | 28 | 19 | 10 | 9 | 7 | 8 | 7 | 6 | 5 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Project Metrics Report History
Date data pulled above table
2023-07-19
ACTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | NCR Open | NCR Closed | NCR Total | D3 Open | D3 Closed | D3 Total | Total Open | Total Closed | Grand Total | % Closed
| C100R | 63 | 1612 | 1675 | 3 | 118 | 121 | 0 | 77 | 77 | 66 | 1807 | 1873 | 96.48%
| ER5C | 144 | 5211 | 5355 | 52 | 684 | 736 | 13 | 169 | 182 | 209 | 6064 | 6273 | 96.67%
| L2HE | 58 | 4226 | 4284 | 33 | 425 | 458 | 21 | 103 | 124 | 112 | 4754 | 4866 | 97.7%
| SNSPPU | 11 | 2803 | 2814 | 1 | 648 | 649 | 3 | 181 | 184 | 15 | 3632 | 3647 | 99.59%
| AUPPS | 20 | 89 | 109 | 3 | 26 | 29 | 0 | 0 | 0 | 23 | 115 | 138 | 83.33%
| NB3SN | 5 | 135 | 140 | 1 | 14 | 15 | 0 | 7 | 7 | 6 | 156 | 162 | 96.3%
| Total | 301 | 14076 | 14377 | 93 | 1915 | 2008 | 37 | 537 | 574 | 431 | 16528 | 16959 | 5.7007
2023-08-03
CTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | NCR Open | NCR Closed | NCR Total | D3 Open | D3 Closed | D3 Total | Total Open | Total Closed | Grand Total | % Closed
| C100R | 62 | 1617 | 1679 | 4 | 118 | 122 | 0 | 77 | 77 | 66 | 1812 | 1878 | 96.49%
| ER5C | 100 | 5310 | 5410 | 56 | 686 | 742 | 14 | 170 | 184 | 170 | 6166 | 6336 | 97.32%
| L2HE | 74 | 4316 | 4390 | 26 | 444 | 470 | 22 | 103 | 125 | 122 | 4863 | 4985 | 97.55%
| SNSPPU | 12 | 2806 | 2818 | 3 | 648 | 651 | 3 | 181 | 184 | 18 | 3635 | 3653 | 99.51%
| AUPPS | 29 | 89 | 118 | 3 | 26 | 29 | 0 | 0 | 0 | 32 | 115 | 147 | 78.23%
| NB3SN | 5 | 135 | 140 | 1 | 14 | 15 | 0 | 7 | 7 | 6 | 156 | 162 | 96.3%
| TOTALS | 282 | 14273 | 14555 | 93 | 1936 | 2029 | 39 | 538 | 577 | 414 | 16747 | 17161 | 97.59%
2023-10-02
ACTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | NCR Open | NCR Closed | NCR Total | D3 Open | D3 Closed | D3 Total | Total Open | Total Closed | Grand Total | % Closed
| C100R | 41 | 1789 | 1830 | 2 | 122 | 124 | 0 | 79 | 79 | 43 | 1990 | 2033 | 97.88%
| ER5C | 105 | 5618 | 5723 | 62 | 706 | 768 | 5 | 181 | 186 | 172 | 6505 | 6677 | 97.42%
| L2HE | 62 | 4513 | 4575 | 26 | 475 | 501 | 2 | 127 | 129 | 90 | 5115 | 5205 | 98.27%
| SNSPPU | 7 | 2816 | 2823 | 5 | 657 | 662 | 3 | 182 | 185 | 15 | 3655 | 3670 | 99.59%
| AUPPS | 39 | 126 | 165 | 0 | 45 | 45 | 0 | 0 | 0 | 39 | 171 | 210 | 81.43%
| NB3SN | 5 | 135 | 140 | 1 | 14 | 15 | 0 | 7 | 7 | 6 | 156 | 162 | 96.3%
| TOTALS | 259 | 14997 | 15256 | 96 | 2019 | 2115 | 10 | 576 | 586 | 365 | 17592 | 17957 | 97.97%
2023-11-06
ACTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | NCR Open | NCR Closed | NCR Total | D3 Open | D3 Closed | D3 Total | Total Open | Total Closed | Grand Total | % Closed
| C100R | 48 | 1913 | 1961 | 9 | 136 | 145 | 0 | 95 | 95 | 57 | 2144 | 2201 | 97.41%
| ER5C | 121 | 5746 | 5867 | 50 | 726 | 776 | 7 | 183 | 190 | 178 | 6655 | 6833 | 97.39%
| L2HE | 69 | 4577 | 4646 | 28 | 485 | 513 | 3 | 127 | 130 | 100 | 5189 | 5289 | 98.11%
| SNSPPU | 5 | 2819 | 2824 | 5 | 658 | 663 | 3 | 182 | 185 | 13 | 3659 | 3672 | 99.65%
| AUPPS | 43 | 148 | 191 | 0 | 55 | 55 | 0 | 7 | 7 | 43 | 210 | 253 | 83%
| NB3SN | 5 | 135 | 140 | 1 | 14 | 15 | 0 | 7 | 7 | 6 | 156 | 162 | 96.3%
| TOTALS | 291 | 15338 | 15629 | 93 | 2074 | 2167 | 13 | 601 | 614 | 397 | 18013 | 18410 | 97.84%
2023-11-30
CTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | NCR Open | NCR Closed | NCR Total | D3 Open | D3 Closed | D3 Total | Total Open | Total Closed | Grand Total | % Closed
| C100R | 29 | 2520 | 2549 | 5 | 140 | 145 | 1 | 95 | 96 | 35 | 2755 | 2790 | 98.75%
| ER5C | 125 | 5832 | 5957 | 52 | 727 | 779 | 4 | 188 | 192 | 181 | 6747 | 6928 | 97.39%
| L2HE | 65 | 4628 | 4693 | 23 | 498 | 521 | 19 | 133 | 152 | 107 | 5259 | 5366 | 98.01%
| SNSPPU | 6 | 2819 | 2825 | 5 | 658 | 663 | 3 | 182 | 185 | 14 | 3659 | 3673 | 99.62%
| AUPPS | 29 | 180 | 209 | 0 | 57 | 57 | 0 | 7 | 7 | 29 | 244 | 273 | 89.38%
| NB3SN | 5 | 135 | 140 | 1 | 14 | 15 | 0 | 7 | 7 | 6 | 156 | 162 | 96.3%
| TOTALS | 259 | 16114 | 16373 | 86 | 2094 | 2180 | 27 | 612 | 639 | 372 | 18820 | 19192 | 98.06%
2024-02-05
ACTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | NCR Open | NCR Closed | NCR Total | D3 Open | D3 Closed | D3 Total | Total Open | Total Closed | Grand Total | % Closed
| C100R | 42 | 2836 | 2878 | 3 | 147 | 150 | 3 | 100 | 103 | 48 | 3083 | 3131 | 98.47%
| ER5C | 94 | 5986 | 6080 | 56 | 736 | 792 | 6 | 192 | 198 | 156 | 6914 | 7070 | 97.79%
| L2HE | 42 | 4763 | 4805 | 18 | 521 | 539 | 9 | 155 | 164 | 69 | 5439 | 5508 | 98.75%
| SNSPPU | 1 | 2823 | 2824 | 1 | 664 | 665 | 3 | 182 | 185 | 5 | 3669 | 3674 | 99.86%
| AUPPS | 29 | 293 | 322 | 0 | 61 | 61 | 0 | 7 | 7 | 29 | 361 | 390 | 92.56%
| NB3SN | 5 | 135 | 140 | 1 | 14 | 15 | 0 | 7 | 7 | 6 | 156 | 162 | 96.3%
| TOTALS | 213 | 16836 | 17049 | 79 | 2143 | 2222 | 21 | 643 | 664 | 313 | 19622 | 19935 | 98.43%
2024-02-26
CTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | NCR Open | NCR Closed | NCR Total | D3 Open | D3 Closed | D3 Total | Total Open | Total Closed | Grand Total | % Closed
| C100R | 38 | 2861 | 2899 | 3 | 148 | 151 | 2 | 101 | 103 | 43 | 3110 | 3153 | 98.64%
| ER5C | 85 | 6080 | 6165 | 59 | 744 | 803 | 8 | 194 | 202 | 152 | 7018 | 7170 | 97.88%
| L2HE | 55 | 4809 | 4864 | 12 | 535 | 547 | 9 | 162 | 171 | 76 | 5506 | 5582 | 98.64%
| SNSPPU | 1 | 2823 | 2824 | 2 | 664 | 666 | 3 | 182 | 185 | 6 | 3669 | 3675 | 99.84%
| AUPPS | 29 | 318 | 347 | 1 | 62 | 63 | 0 | 7 | 7 | 30 | 387 | 417 | 92.81%
| NB3SN | 5 | 135 | 140 | 1 | 14 | 15 | 0 | 7 | 7 | 6 | 156 | 162 | 96.3%
| TOTALS | 213 | 17026 | 17239 | 78 | 2167 | 2245 | 22 | 653 | 675 | 313 | 19846 | 20159 | 98.45%
2024-04-01
ACTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | NCR Open | NCR Closed | NCR Total | D3 Open | D3 Closed | D3 Total | Total Open | Total Closed | Grand Total | % Closed
| C100R | 45 | 2872 | 2917 | 1 | 150 | 151 | 1 | 102 | 103 | 47 | 3124 | 3171 | 98.52%
| ER5C | 124 | 6202 | 6326 | 81 | 762 | 843 | 15 | 198 | 213 | 220 | 7162 | 7382 | 97.02%
| L2HE | 62 | 4944 | 5006 | 13 | 560 | 573 | 7 | 171 | 178 | 82 | 5675 | 5757 | 98.58%
| SNSPPU | 1 | 2825 | 2826 | 1 | 679 | 680 | 3 | 183 | 186 | 5 | 3687 | 3692 | 99.86%
| AUPPS | 46 | 318 | 364 | 4 | 73 | 77 | 0 | 7 | 7 | 50 | 398 | 448 | 88.84%
| NB3SN | 5 | 135 | 140 | 1 | 14 | 15 | 0 | 7 | 7 | 6 | 156 | 162 | 96.3%
| TOTALS | 283 | 17296 | 17579 | 101 | 2238 | 2339 | 26 | 668 | 694 | 410 | 20202 | 20612 | 98.01%
2024-05-06
ACTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | Trav Open > 6mo | % Trav Open > 6mo | NCR Open | NCR Closed | NCR Total | NCR Open > 6mo | D3 Open | D3 Closed | D3 Total | D3 Open > 6mo | Total Open | Total Closed | Grand Total | Total Open > 6mo | % Closed | % Open > 6mo
| AUPCAV | 4 | 5 | 9 | 0 | 0% | 1 | 3 | 4 | 0 | 1 | 0 | 1 | 0 | 6 | 8 | 14 | 0 | 57.14% | 0
| AUPPS | 29 | 376 | 405 | 27 | 93.1% | 4 | 73 | 77 | 0 | 0 | 7 | 7 | 0 | 33 | 456 | 489 | 27 | 93.25% | 81.82%
| C100R | 40 | 2873 | 2913 | 15 | 37.5% | 1 | 150 | 151 | 1 | 4 | 102 | 106 | 0 | 45 | 3125 | 3170 | 16 | 98.58% | 35.56%
| ER5C | 140 | 6366 | 6506 | 19 | 13.57% | 76 | 789 | 865 | 41 | 20 | 200 | 220 | 2 | 236 | 7355 | 7591 | 62 | 96.89% | 26.27%
| L2HE | 53 | 5096 | 5149 | 12 | 22.64% | 21 | 578 | 599 | 1 | 8 | 178 | 186 | 2 | 82 | 5852 | 5934 | 15 | 98.62% | 18.29%
| NB3SN | 6 | 138 | 144 | 5 | 83.33% | 0 | 15 | 15 | 0 | 0 | 7 | 7 | 0 | 6 | 160 | 166 | 5 | 96.39% | 83.33%
| SRFRD | 92 | 2004 | 2096 | 1 | 1.09% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 2004 | 2096 | 1 | 95.61% | 1.09%
| STP | 27 | 929 | 956 | 24 | 88.89% | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 27 | 933 | 960 | 24 | 97.19% | 88.89%
| TOTALS | 391 | 17787 | 18178 | 103 | 26.34% | 103 | 1609 | 1712 | 43 | 33 | 497 | 530 | 4 | 527 | 19893 | 20420 | 150 | 97.42% | 28.46%
2024-06-03
ACTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | Trav Open > 6mo | % Trav Open > 6mo | NCR Open | NCR Closed | NCR Total | NCR Open > 6mo | D3 Open | D3 Closed | D3 Total | D3 Open > 6mo | Total Open | Total Closed | Grand Total | Total Open > 6mo | % Closed | % Open > 6mo
| AUPCAV | 5 | 14 | 19 | 0 | 0% | 3 | 3 | 6 | 0 | 1 | 2 | 3 | 0 | 9 | 19 | 28 | 0 | 67.86% | 0
| AUPPS | 29 | 376 | 405 | 29 | 100% | 5 | 78 | 83 | 0 | 0 | 7 | 7 | 0 | 34 | 461 | 495 | 29 | 93.13% | 85.29%
| C100R | 40 | 2896 | 2936 | 18 | 45% | 2 | 150 | 152 | 1 | 4 | 102 | 106 | 0 | 46 | 3148 | 3194 | 19 | 98.56% | 41.3%
| EICCRB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EICELL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EICMAG | 0 | 121 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 121 | 0 | 100% | 0
| EICRD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ER5C | 152 | 6399 | 6551 | 19 | 12.5% | 74 | 797 | 871 | 40 | 20 | 200 | 220 | 2 | 246 | 7396 | 7642 | 61 | 96.78% | 24.8%
| L2HE | 51 | 5277 | 5328 | 9 | 17.65% | 29 | 588 | 617 | 1 | 6 | 184 | 190 | 2 | 86 | 6049 | 6135 | 12 | 98.6% | 13.95%
| NB3SN | 6 | 138 | 144 | 5 | 83.33% | 6 | 15 | 21 | 0 | 0 | 7 | 7 | 0 | 12 | 160 | 172 | 5 | 93.02% | 41.67%
| PLACLN | 8 | 4 | 12 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 12 | 0 | 33.33% | 0
| SRFRD | 118 | 2004 | 2122 | 2 | 1.69% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 2004 | 2122 | 2 | 94.44% | 1.69%
| STP | 27 | 929 | 956 | 24 | 88.89% | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 27 | 933 | 960 | 24 | 97.19% | 88.89%
| WMGRDR | 0 | 6 | 6 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 8 | 8 | 0 | 100% | 0
| TOTALS | 436 | 18164 | 18600 | 106 | 24.31% | 119 | 1633 | 1752 | 42 | 31 | 506 | 537 | 4 | 586 | 20303 | 20889 | 152 | 97.19% | 25.94%
2024-07-11
ACTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | Trav Open > 6mo | % Trav Open > 6mo | NCR Open | NCR Closed | NCR Total | NCR Open > 6mo | D3 Open | D3 Closed | D3 Total | D3 Open > 6mo | Total Open | Total Closed | Grand Total | Total Open > 6mo | % Closed | % Open > 6mo
| AUPCAV | 6 | 21 | 27 | 0 | 0% | 4 | 3 | 7 | 0 | 1 | 3 | 4 | 0 | 11 | 27 | 38 | 0 | 71.05% | 0
| AUPPS | 29 | 376 | 405 | 29 | 100% | 5 | 78 | 83 | 0 | 0 | 7 | 7 | 0 | 34 | 461 | 495 | 29 | 93.13% | 85.29%
| C100R | 46 | 2914 | 2960 | 24 | 52.17% | 3 | 150 | 153 | 1 | 4 | 111 | 115 | 0 | 53 | 3175 | 3228 | 25 | 98.36% | 47.17%
| EICCRB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EICELL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EICMAG | 0 | 121 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 121 | 0 | 100% | 0
| EICRD | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 100% | 0
| ER5C | 142 | 6428 | 6570 | 24 | 16.9% | 75 | 801 | 876 | 39 | 20 | 200 | 220 | 2 | 237 | 7429 | 7666 | 65 | 96.91% | 27.43%
| L2HE | 42 | 5408 | 5450 | 6 | 14.29% | 27 | 606 | 633 | 1 | 3 | 192 | 195 | 2 | 72 | 6206 | 6278 | 9 | 98.85% | 12.5%
| NB3SN | 6 | 138 | 144 | 5 | 83.33% | 10 | 15 | 25 | 0 | 2 | 7 | 9 | 0 | 18 | 160 | 178 | 5 | 89.89% | 27.78%
| PLACLN | 8 | 4 | 12 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 12 | 0 | 33.33% | 0
| SRFRD | 154 | 2005 | 2159 | 10 | 6.49% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | 2005 | 2159 | 10 | 92.87% | 6.49%
| SRFTRNG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STP | 27 | 929 | 956 | 24 | 88.89% | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 27 | 933 | 960 | 24 | 97.19% | 88.89%
| WMGRDR | 0 | 6 | 6 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 8 | 8 | 0 | 100% | 0
| TOTALS | 460 | 18350 | 18810 | 122 | 26.52% | 124 | 1656 | 1780 | 41 | 30 | 525 | 555 | 4 | 614 | 20531 | 21145 | 167 | 97.1% | 27.2%
2024-08-05
ACTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | Trav Open > 6mo | % Trav Open > 6mo | NCR Open | NCR Closed | NCR Total | NCR Open > 6mo | D3 Open | D3 Closed | D3 Total | D3 Open > 6mo | Total Open | Total Closed | Grand Total | Total Open > 6mo | % Closed | % Open > 6mo
| AUPCAV | 8 | 23 | 31 | 0 | 0% | 4 | 3 | 7 | 0 | 0 | 5 | 5 | 0 | 12 | 31 | 43 | 0 | 72.09% | 0
| AUPPS | 29 | 376 | 405 | 29 | 100% | 12 | 81 | 93 | 0 | 0 | 7 | 7 | 0 | 41 | 464 | 505 | 29 | 91.88% | 70.73%
| C100R | 28 | 2940 | 2968 | 4 | 14.29% | 1 | 152 | 153 | 1 | 0 | 115 | 115 | 0 | 29 | 3207 | 3236 | 5 | 99.1% | 17.24%
| EIC197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EIC591SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EICMAG | 0 | 121 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 121 | 0 | 100% | 0
| EICRD | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 100% | 0
| ER5C | 126 | 6490 | 6616 | 29 | 23.02% | 83 | 804 | 887 | 40 | 16 | 204 | 220 | 6 | 225 | 7498 | 7723 | 75 | 97.09% | 33.33%
| L2HE | 22 | 5464 | 5486 | 3 | 13.64% | 20 | 617 | 637 | 1 | 3 | 195 | 198 | 2 | 45 | 6276 | 6321 | 6 | 99.29% | 13.33%
| NB3SN | 1 | 143 | 144 | 0 | 0% | 10 | 15 | 25 | 0 | 2 | 7 | 9 | 0 | 13 | 165 | 178 | 0 | 92.7% | 0
| PLACLN | 8 | 4 | 12 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 12 | 0 | 33.33% | 0
| SRFRD | 183 | 2005 | 2188 | 17 | 9.29% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183 | 2005 | 2188 | 17 | 91.64% | 9.29%
| SRFTRNG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STP | 27 | 929 | 956 | 25 | 92.59% | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 27 | 933 | 960 | 25 | 97.19% | 92.59%
| WMGRDR | 0 | 6 | 6 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 8 | 8 | 0 | 100% | 0
| TOTALS | 432 | 18501 | 18933 | 107 | 24.77% | 130 | 1675 | 1805 | 42 | 21 | 538 | 559 | 8 | 583 | 20714 | 21297 | 157 | 97.26% | 26.93%
2024-09-06
ACTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | Trav Open > 6mo | % Trav Open > 6mo | NCR Open | NCR Closed | NCR Total | NCR Open > 6mo | D3 Open | D3 Closed | D3 Total | D3 Open > 6mo | Total Open | Total Closed | Grand Total | Total Open > 6mo | % Closed | % Open > 6mo
| AUPCAV | 2 | 29 | 31 | 0 | 0% | 2 | 8 | 10 | 0 | 0 | 7 | 7 | 0 | 4 | 44 | 48 | 0 | 91.67% | 0
| AUPPS | 38 | 391 | 429 | 14 | 36.84% | 19 | 84 | 103 | 0 | 0 | 7 | 7 | 0 | 57 | 482 | 539 | 14 | 89.42% | 24.56%
| C100R | 23 | 2942 | 2965 | 2 | 8.7% | 1 | 152 | 153 | 1 | 0 | 115 | 115 | 0 | 24 | 3209 | 3233 | 3 | 99.26% | 12.5%
| EIC197 | 1 | 0 | 1 | 0 | 0% | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 50% | 0
| EIC591SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EICMAG | 0 | 121 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 121 | 0 | 100% | 0
| EICRD | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 100% | 0
| ER5C | 116 | 6589 | 6705 | 33 | 28.45% | 53 | 847 | 900 | 29 | 5 | 216 | 221 | 2 | 174 | 7652 | 7826 | 64 | 97.78% | 36.78%
| L2HE | 15 | 5507 | 5522 | 2 | 13.33% | 19 | 620 | 639 | 3 | 5 | 196 | 201 | 2 | 39 | 6323 | 6362 | 7 | 99.39% | 17.95%
| NB3SN | 1 | 143 | 144 | 0 | 0% | 10 | 15 | 25 | 0 | 2 | 7 | 9 | 0 | 13 | 165 | 178 | 0 | 92.7% | 0
| PLACLN | 8 | 4 | 12 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 12 | 0 | 33.33% | 0
| SRFRD | 102 | 2129 | 2231 | 26 | 25.49% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 2129 | 2231 | 26 | 95.43% | 25.49%
| SRFTRNG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STP | 27 | 929 | 956 | 27 | 100% | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 27 | 933 | 960 | 27 | 97.19% | 100%
| WMGRDR | 6 | 6 | 12 | 0 | 0% | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 6 | 8 | 14 | 0 | 57.14% | 0
| TOTALS | 339 | 18790 | 19129 | 104 | 30.68% | 104 | 1730 | 1834 | 33 | 12 | 553 | 565 | 4 | 455 | 21073 | 21528 | 141 | 97.89% | 30.99%
2024-10-03
ACTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | Trav Open > 6mo | % Trav Open > 6mo | NCR Open | NCR Closed | NCR Total | NCR Open > 6mo | D3 Open | D3 Closed | D3 Total | D3 Open > 6mo | Total Open | Total Closed | Grand Total | Total Open > 6mo | % Closed | % Open > 6mo
| AUPCAV | 0 | 31 | 31 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 7 | 7 | 0 | 0 | 48 | 48 | 0 | 100% | 0
| AUPPS | 38 | 391 | 429 | 14 | 36.84% | 3 | 106 | 109 | 1 | 0 | 7 | 7 | 0 | 41 | 504 | 545 | 15 | 92.48% | 36.59%
| C100R | 43 | 2942 | 2985 | 2 | 4.65% | 17 | 152 | 169 | 1 | 0 | 115 | 115 | 0 | 60 | 3209 | 3269 | 3 | 98.16% | 5%
| EIC197 | 1 | 1 | 2 | 0 | 0% | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 0 | 66.67% | 0
| EIC591SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EICMAG | 0 | 121 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 121 | 0 | 100% | 0
| EICRD | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 100% | 0
| ER5C | 115 | 6666 | 6781 | 65 | 56.52% | 61 | 849 | 910 | 31 | 5 | 219 | 224 | 0 | 181 | 7734 | 7915 | 96 | 97.71% | 53.04%
| L2HE | 16 | 5568 | 5584 | 3 | 18.75% | 10 | 631 | 641 | 2 | 4 | 201 | 205 | 2 | 30 | 6400 | 6430 | 7 | 99.53% | 23.33%
| NB3SN | 1 | 143 | 144 | 0 | 0% | 10 | 15 | 25 | 0 | 2 | 7 | 9 | 0 | 13 | 165 | 178 | 0 | 92.7% | 0
| PLACLN | 8 | 4 | 12 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 12 | 0 | 33.33% | 0
| SRFRD | 124 | 2129 | 2253 | 32 | 25.81% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 2129 | 2253 | 32 | 94.5% | 25.81%
| SRFTRNG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STP | 27 | 929 | 956 | 27 | 100% | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 27 | 933 | 960 | 27 | 97.19% | 100%
| WMGRDR | 6 | 6 | 12 | 0 | 0% | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 6 | 8 | 14 | 0 | 57.14% | 0
| TOTALS | 379 | 18931 | 19310 | 143 | 37.73% | 101 | 1767 | 1868 | 35 | 11 | 561 | 572 | 2 | 491 | 21259 | 21750 | 180 | 97.74% | 36.66%
2024-11-04
ACTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | Trav Open > 6mo | % Trav Open > 6mo | NCR Open | NCR Closed | NCR Total | NCR Open > 6mo | D3 Open | D3 Closed | D3 Total | D3 Open > 6mo | Total Open | Total Closed | Grand Total | Total Open > 6mo | % Closed | % Open > 6mo
| AUPCAV | 0 | 31 | 31 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 7 | 7 | 0 | 0 | 48 | 48 | 0 | 100% | 0
| AUPPS | 39 | 391 | 430 | 14 | 35.9% | 1 | 108 | 109 | 1 | 0 | 7 | 7 | 0 | 40 | 506 | 546 | 15 | 92.67% | 37.5%
| C100R | 38 | 2980 | 3018 | 2 | 5.26% | 3 | 178 | 181 | 1 | 1 | 115 | 116 | 0 | 42 | 3273 | 3315 | 3 | 98.73% | 7.14%
| EIC197 | 1 | 1 | 2 | 0 | 0% | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 0 | 66.67% | 0
| EIC591SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EICMAG | 0 | 121 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 121 | 0 | 100% | 0
| EICRD | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 100% | 0
| ER5C | 104 | 6775 | 6879 | 67 | 64.42% | 68 | 856 | 924 | 44 | 4 | 224 | 228 | 3 | 176 | 7855 | 8031 | 114 | 97.81% | 64.77%
| L2HE | 13 | 5600 | 5613 | 3 | 23.08% | 5 | 636 | 641 | 2 | 3 | 202 | 205 | 1 | 21 | 6438 | 6459 | 6 | 99.67% | 28.57%
| NB3SN | 2 | 143 | 145 | 1 | 50% | 10 | 15 | 25 | 0 | 2 | 7 | 9 | 0 | 14 | 165 | 179 | 1 | 92.18% | 7.14%
| PLACLN | 7 | 5 | 12 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 5 | 12 | 0 | 41.67% | 0
| SRFRD | 144 | 2129 | 2273 | 34 | 23.61% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 2129 | 2273 | 34 | 93.66% | 23.61%
| SRFTRNG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STP | 27 | 929 | 956 | 27 | 100% | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 27 | 933 | 960 | 27 | 97.19% | 100%
| WMGRDR | 6 | 6 | 12 | 0 | 0% | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 6 | 8 | 14 | 0 | 57.14% | 0
| TOTALS | 381 | 19111 | 19492 | 148 | 38.85% | 87 | 1807 | 1894 | 48 | 10 | 567 | 577 | 4 | 478 | 21485 | 21963 | 200 | 97.82% | 41.84%
2024-11-25
ACTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | Trav Open > 6mo | % Trav Open > 6mo | NCR Open | NCR Closed | NCR Total | NCR Open > 6mo | D3 Open | D3 Closed | D3 Total | D3 Open > 6mo | Total Open | Total Closed | Grand Total | Total Open > 6mo | % Closed | % Open > 6mo
| AUPCAV | 0 | 31 | 31 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 7 | 7 | 0 | 0 | 48 | 48 | 0 | 100% | 0
| AUPPS | 16 | 424 | 440 | 14 | 87.5% | 2 | 108 | 110 | 1 | 0 | 7 | 7 | 0 | 18 | 539 | 557 | 15 | 96.77% | 83.33%
| C100R | 35 | 3008 | 3043 | 2 | 5.71% | 1 | 180 | 181 | 1 | 0 | 117 | 117 | 0 | 36 | 3305 | 3341 | 3 | 98.92% | 8.33%
| EIC197 | 1 | 1 | 2 | 0 | 0% | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 0 | 66.67% | 0
| EIC591SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EICMAG | 0 | 121 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 121 | 0 | 100% | 0
| EICRD | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 100% | 0
| ER5C | 104 | 6848 | 6952 | 59 | 56.73% | 58 | 867 | 925 | 39 | 3 | 230 | 233 | 1 | 165 | 7945 | 8110 | 99 | 97.97% | 60%
| L2HE | 28 | 5645 | 5673 | 6 | 21.43% | 8 | 652 | 660 | 2 | 5 | 205 | 210 | 1 | 41 | 6502 | 6543 | 9 | 99.37% | 21.95%
| NB3SN | 2 | 143 | 145 | 1 | 50% | 10 | 15 | 25 | 6 | 2 | 7 | 9 | 0 | 14 | 165 | 179 | 7 | 92.18% | 50%
| PLACLN | 8 | 5 | 13 | 7 | 87.5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 5 | 13 | 7 | 38.46% | 87.5%
| SRFRD | 161 | 2129 | 2290 | 36 | 22.36% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 2129 | 2290 | 36 | 92.97% | 22.36%
| SRFTRNG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STP | 27 | 929 | 956 | 27 | 100% | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 27 | 933 | 960 | 27 | 97.19% | 100%
| WMGRDR | 6 | 6 | 12 | 0 | 0% | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 6 | 8 | 14 | 0 | 57.14% | 0
| TOTALS | 388 | 19290 | 19678 | 152 | 39.18% | 79 | 1836 | 1915 | 49 | 10 | 578 | 588 | 2 | 477 | 21704 | 22181 | 203 | 97.85% | 42.56%
2024-12-05
| PROJ | Trav | Trav | Trav | Trav | % | NCR | NCR | NCR | NCR | D3 | D3 | D3 | D3 | Total | Total | Grand | Total | % | %
|  | Open | Closed | Total | Open | Trav | Open | Closed | Total | Open | Open | Closed | Total | Open | Open | Closed | Total | Open | Closed | Open >
[5 empty] | > | Open |  |  |  | > |  |  |  | > |  |  |  | > |  | 6mo
[5 empty] | 6mo | > 6mo |  |  |  | 6mo |  |  |  | 6mo |  |  |  | 6mo
| AUPCAV | 0 | 31 | 31 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 7 | 7 | 0 | 0 | 48 | 48 | 0 | 100 | 0
%
| AUPPS | 16 | 424 | 440 | 14 | 87.5 | 5 | 108 | 113 | 1 | 0 | 7 | 7 | 0 | 21 | 539 | 560 | 15 | 96.25 | 71.43
[6 empty] | % | [12 empty] | % | %
| C100R | 33 | 3012 | 3045 | 2 | 6.06% | 5 | 180 | 185 | 1 | 0 | 117 | 117 | 0 | 38 | 3309 | 3347 | 3 | 98.86 | 7.89%
%
| EIC197 | 1 | 1 | 2 | 0 | 0% | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 0 | 66.67 | 0
%
| EIC591SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EICMAG | 0 | 121 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 121 | 0 | 100 | 0
%
| EICRD | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 100 | 0
%
| ER5C | 84 | 6897 | 6981 | 47 | 55.95 | 48 | 889 | 937 | 20 | 3 | 230 | 233 | 1 | 135 | 8016 | 8151 | 68 | 98.34 | 50.37
[6 empty] | % | [12 empty] | % | %
| L2HE | 21 | 5657 | 5678 | 6 | 28.57 | 7 | 654 | 661 | 2 | 5 | 205 | 210 | 1 | 33 | 6516 | 6549 | 9 | 99.5 | 27.27
[6 empty] | % | [12 empty] | % | %
| NB3SN | 2 | 143 | 145 | 1 | 50 | 10 | 15 | 25 | 6 | 2 | 7 | 9 | 2 | 14 | 165 | 179 | 9 | 92.18 | 64.29
[6 empty] | % | [12 empty] | % | %
| PLACLN | 11 | 5 | 16 | 7 | 63.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 5 | 16 | 7 | 31.25 | 63.64
[6 empty] | % | [12 empty] | % | %
| SRFRD | 168 | 2129 | 2297 | 36 | 21.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 2129 | 2297 | 36 | 92.69 | 21.43
[6 empty] | % | [12 empty] | % | %
| SRFTRNG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STP | 27 | 929 | 956 | 27 | 100 | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 27 | 933 | 960 | 27 | 97.19 | 100
[6 empty] | % | [12 empty] | % | %
| WMGRDR | 6 | 6 | 12 | 0 | 0% | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 6 | 8 | 14 | 0 | 57.14 | 0
%
| TOTALS | 369 | 19355 | 19724 | 140 | 37.94 | 75 | 1860 | 1935 | 30 | 10 | 578 | 588 | 4 | 454 | 21793 | 22247 | 174 | 97.96 | 38.33
[6 empty] | % | [12 empty] | % | %
2025-01-13
CTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | Trav Open > 6mo | % Trav Open > 6mo | NCR Open | NCR Closed | NCR Total | NCR Open > 6mo | D3 Open | D3 Closed | D3 Total | D3 Open > 6mo | Total Open | Total Closed | Grand Total | Total Open > 6mo | % Closed | % Open > 6mo
| AUPCAV | 2 | 33 | 35 | 0 | 0% | 0 | 10 | 10 | 0 | 0 | 7 | 7 | 0 | 2 | 50 | 52 | 0 | 96.15% | 0
| AUPPS | 16 | 429 | 445 | 14 | 87.5% | 7 | 115 | 122 | 0 | 0 | 7 | 7 | 0 | 23 | 551 | 574 | 14 | 95.99% | 60.87%
| C100R | 40 | 3053 | 3093 | 20 | 50% | 10 | 180 | 190 | 1 | 0 | 117 | 117 | 0 | 50 | 3350 | 3400 | 21 | 98.53% | 42%
| EIC197 | 6 | 1 | 7 | 0 | 0% | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 8 | 0 | 25% | 0
| EIC591SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EICMAG | 0 | 121 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 121 | 0 | 100% | 0
| EICRD | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 100% | 0
| ER5C | 94 | 6948 | 7042 | 44 | 46.81% | 52 | 894 | 946 | 21 | 1 | 232 | 233 | 0 | 147 | 8074 | 8221 | 65 | 98.21% | 44.22%
| L2HE | 23 | 5682 | 5705 | 8 | 34.78% | 9 | 659 | 668 | 2 | 6 | 206 | 212 | 2 | 38 | 6547 | 6585 | 12 | 99.42% | 31.58%
| NB3SN | 2 | 143 | 145 | 1 | 50% | 10 | 15 | 25 | 10 | 2 | 7 | 9 | 2 | 14 | 165 | 179 | 13 | 92.18% | 92.86%
| PLACLN | 11 | 5 | 16 | 7 | 63.64% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 5 | 16 | 7 | 31.25% | 63.64%
| SRFRD | 168 | 2129 | 2297 | 42 | 25% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 2129 | 2297 | 42 | 92.69% | 25%
| SRFTRNG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STP | 27 | 929 | 956 | 27 | 100% | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 27 | 933 | 960 | 27 | 97.19% | 100%
| WMGRDR | 6 | 6 | 12 | 0 | 0% | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 6 | 8 | 14 | 0 | 57.14% | 0
| TOTALS | 395 | 19479 | 19874 | 163 | 41.27% | 88 | 1877 | 1965 | 34 | 9 | 581 | 590 | 4 | 492 | 21937 | 22429 | 201 | 97.81% | 40.85%
2025-02-07
ACTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | Trav Open > 6mo | % Trav Open > 6mo | NCR Open | NCR Closed | NCR Total | NCR Open > 6mo | D3 Open | D3 Closed | D3 Total | D3 Open > 6mo | Total Open | Total Closed | Grand Total | Total Open > 6mo | % Closed | % Open > 6mo
| AUPCAV | 4 | 36 | 40 | 0 | 0% | 1 | 10 | 11 | 0 | 1 | 7 | 8 | 0 | 6 | 53 | 59 | 0 | 89.83% | 0
| AUPPS | 17 | 432 | 449 | 14 | 82.35% | 15 | 115 | 130 | 0 | 0 | 7 | 7 | 0 | 32 | 554 | 586 | 14 | 94.54% | 43.75%
| C100R | 41 | 3153 | 3194 | 28 | 68.29% | 18 | 180 | 198 | 1 | 1 | 123 | 124 | 0 | 60 | 3456 | 3516 | 29 | 98.29% | 48.33%
| EIC197 | 7 | 1 | 8 | 0 | 0% | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 | 9 | 0 | 22.22% | 0
| EIC591SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EICMAG | 0 | 121 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 121 | 0 | 100% | 0
| EICRD | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 100% | 0
| ER5C | 94 | 7011 | 7105 | 46 | 48.94% | 49 | 902 | 951 | 21 | 1 | 233 | 234 | 0 | 144 | 8146 | 8290 | 67 | 98.26% | 46.53%
| L2HE | 52 | 5692 | 5744 | 9 | 17.31% | 17 | 659 | 676 | 3 | 3 | 212 | 215 | 2 | 72 | 6563 | 6635 | 14 | 98.91% | 19.44%
| NB3SN | 2 | 143 | 145 | 1 | 50% | 10 | 15 | 25 | 10 | 2 | 7 | 9 | 2 | 14 | 165 | 179 | 13 | 92.18% | 92.86%
| PLACLN | 11 | 5 | 16 | 7 | 63.64% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 5 | 16 | 7 | 31.25% | 63.64%
| SRFRD | 200 | 2129 | 2329 | 61 | 30.5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 2129 | 2329 | 61 | 91.41% | 30.5%
| SRFTRNG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STP | 27 | 929 | 956 | 27 | 100% | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 27 | 933 | 960 | 27 | 97.19% | 100%
| WMGRDR | 6 | 6 | 12 | 6 | 100% | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 6 | 8 | 14 | 6 | 57.14% | 100%
| TOTALS | 461 | 19658 | 20119 | 199 | 43.17% | 110 | 1885 | 1995 | 35 | 8 | 594 | 602 | 4 | 579 | 22137 | 22716 | 238 | 97.45% | 41.11%
2025-03-06
ACTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | Trav Open > 6mo | % Trav Open > 6mo | NCR Open | NCR Closed | NCR Total | NCR Open > 6mo | D3 Open | D3 Closed | D3 Total | D3 Open > 6mo | Total Open | Total Closed | Grand Total | Total Open > 6mo | % Closed | % Open > 6mo
| AUPCAV | 5 | 40 | 45 | 0 | 0% | 1 | 10 | 11 | 0 | 1 | 7 | 8 | 0 | 7 | 57 | 64 | 0 | 89.06% | 0
| AUPPS | 14 | 439 | 453 | 12 | 85.71% | 16 | 122 | 138 | 0 | 0 | 7 | 7 | 0 | 30 | 568 | 598 | 12 | 94.98% | 40%
| C100R | 39 | 3265 | 3304 | 20 | 51.28% | 23 | 182 | 205 | 1 | 0 | 128 | 128 | 0 | 62 | 3575 | 3637 | 21 | 98.3% | 33.87%
| EIC197 | 7 | 1 | 8 | 0 | 0% | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 | 9 | 0 | 22.22% | 0
| EIC591SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EICMAG | 0 | 121 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 121 | 0 | 100% | 0
| EICRD | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 100% | 0
| ER5C | 90 | 7154 | 7244 | 40 | 44.44% | 53 | 908 | 961 | 22 | 1 | 236 | 237 | 0 | 144 | 8298 | 8442 | 62 | 98.29% | 43.06%
| L2HE | 54 | 5696 | 5750 | 10 | 18.52% | 14 | 664 | 678 | 3 | 3 | 212 | 215 | 3 | 71 | 6572 | 6643 | 16 | 98.93% | 22.54%
| NB3SN | 2 | 143 | 145 | 1 | 50% | 10 | 15 | 25 | 10 | 2 | 7 | 9 | 2 | 14 | 165 | 179 | 13 | 92.18% | 92.86%
| PLACLN | 11 | 5 | 16 | 7 | 63.64% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 5 | 16 | 7 | 31.25% | 63.64%
| SRFRD | 247 | 2129 | 2376 | 100 | 40.49% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247 | 2129 | 2376 | 100 | 89.6% | 40.49%
| SRFTRNG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STP | 27 | 929 | 956 | 27 | 100% | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 27 | 933 | 960 | 27 | 97.19% | 100%
| WMGRDR | 6 | 6 | 12 | 6 | 100% | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 6 | 8 | 14 | 6 | 57.14% | 100%
| TOTALS | 502 | 19928 | 20430 | 223 | 44.42% | 117 | 1905 | 2022 | 36 | 7 | 602 | 609 | 5 | 626 | 22435 | 23061 | 264 | 97.29% | 42.17%
2025-04-08
ACTIVE PROJECTS ONLY
| PROJ | Trav Open | Trav Closed | Trav Total | Trav Open > 6mo | % Trav Open > 6mo | NCR Open | NCR Closed | NCR Total | NCR Open > 6mo | D3 Open | D3 Closed | D3 Total | D3 Open > 6mo | Total Open | Total Closed | Grand Total | Total Open > 6mo | % Closed | % Open > 6mo
| AUPCAV | 6 | 43 | 49 | 0 | 0% | 1 | 10 | 11 | 0 | 1 | 7 | 8 | 0 | 8 | 60 | 68 | 0 | 88.24% | 0
| AUPPS | 14 | 443 | 457 | 12 | 85.71% | 7 | 135 | 142 | 0 | 0 | 7 | 7 | 0 | 21 | 585 | 606 | 12 | 96.53% | 57.14%
| C100R | 17 | 3364 | 3381 | 0 | 0% | 31 | 194 | 225 | 1 | 0 | 132 | 132 | 0 | 48 | 3690 | 3738 | 1 | 98.72% | 2.08%
| EIC197 | 35 | 1 | 36 | 1 | 2.86% | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 35 | 2 | 37 | 1 | 5.41% | 2.86%
| EIC591SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EICMAG | 0 | 121 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 121 | 0 | 100% | 0
| EICRD | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 100% | 0
| ER5C | 88 | 7295 | 7383 | 35 | 39.77% | 53 | 922 | 975 | 32 | 1 | 239 | 240 | 0 | 142 | 8456 | 8598 | 67 | 98.35% | 47.18%
| L2HE | 53 | 5701 | 5754 | 8 | 15.09% | 14 | 666 | 680 | 3 | 5 | 214 | 219 | 3 | 72 | 6581 | 6653 | 14 | 98.92% | 19.44%
| NB3SN | 2 | 148 | 150 | 1 | 50% | 10 | 15 | 25 | 10 | 2 | 7 | 9 | 2 | 14 | 170 | 184 | 13 | 92.39% | 92.86%
| PLACLN | 11 | 5 | 16 | 7 | 63.64% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 5 | 16 | 7 | 31.25% | 63.64%
| SRFRD | 297 | 2129 | 2426 | 124 | 41.75% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297 | 2129 | 2426 | 124 | 87.76% | 41.75%
| SRFTRNG | 1 | 0 | 1 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0% | 0
| STP | 27 | 929 | 956 | 27 | 100% | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 27 | 933 | 960 | 27 | 97.19% | 100%
| WMGRDR | 6 | 6 | 12 | 6 | 100% | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 6 | 8 | 14 | 6 | 57.14% | 100%
| TOTALS | 557 | 20185 | 20742 | 221 | 39.68% | 116 | 1946 | 2062 | 46 | 9 | 611 | 620 | 5 | 682 | 22742 | 23424 | 272 | 97.09% | 39.88%

## QO1 (hidden)
Objective 1: | SRF Project Documents for Major Projects
Owner: | Ed Daly
How Tracked? | Tracked on Project Register |  | Project Execution Document Tracker
|  |  | Owner: | Ed Daly
Goal | 95% |  | Last Updated: | 2023-07-24
| 25 | Project Documents Expected
Document
Date | Project Documents | Percent Complete | Project | Project Execution Plan | Work Control Document Register | Document Register | Record Register | Acceptance Criteria Document
2023-03-23 | 16 | 64% | ER5C
2023-08-04 | 17 | 68% | C100R | 1 | 1 | 1 | 1
|  | 0% | SNSPPU | 1 | 1 | 1 | 1 | 1
|  | 0% | L2HE | 1 | 1 | 1 |  | 1
|  | 0% | AUPPS | 1 | 1 | 1 | 1 | 1
0%
|  | 0% | QO Metric: | 18 | 72%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## QO2 (hidden)
Objective 2: | Competence specific to WorkCenters
Owner:
How Tracked?
Goal | 90% | of SRF Staff with specific WorkCenter competency
Date | SRF Staff with specific WorkCenter competency | Total SRF Staff | Perceont Complete
2023-03-23 | 17 | 79 | 21.52%

## QO3 (hidden)
Objective 3: | Close Work Control Documents
Owner:
How Tracked? | Pansophy
Goal less than | 400 | Open Travelers
Date
2023-03-23 | 330
2023-04-01 | 328
2023-07-19 | 301
2023-08-03 | 282
|  |  | OPEN TRAVELERS | Data from QC Reports - Travelers Reports - Travelers by Prj Op/Cl
2023
|  |  | PROJ | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | 2024-01-24 | 2024-02-24
|  |  | C100R | 271 | 276 | 6 | 24 | 55 | 60 | 61 | 16 | 48 | 52 | 28 | 41 | 37 | 39
|  |  | ER5C | 157 | 184 | 49 | 117 | 128 | 104 | 71 | 69 | 91 | 89 | 90 | 90 | 59 | 40
|  |  | L2HE | 70 | 63 | 51 | 104 | 129 | 122 | 82 | 64 | 64 | 69 | 64 | 69 | 41 | 48
|  |  | SNSPPU | 19 | 15 | 3 | 5 | 6 | 5 | 4 | 0 | 6 | 7 | 5 | 6 | 1 | 1
|  |  | AUPPS | 16 | 12 | 12 | 12 | 12 | 12 | 29 | 30 | 33 | 43 | 29 | 40 | 29 | 29
|  |  | NB3SN | 11 | 12 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  |  | TOTAL | 544 | 562 | 126 | 267 | 335 | 308 | 252 | 289 | 256 | 259 | 291 | 259 | 172 | 162

## QO4 (hidden)
Objective 4: | Cryomodule Performance
Owner:
How Tracked?
Goal | 95% | tested voltage within admin limits of 2023 delivered cryomodules
Date
2023-03-23 | 107% | -based on preliminary data of 1 L2HE Cryomodule
2023-08-04 | 100%

## QO5 (hidden)
Objective 5: | Completion of CAPA Reports
Owner: | Ashley M
How Tracked? | CAPA Register
Goal | 90%
Date | 45-day response time | Percent | 180-day completion time | Percent | Total CAPAs
2023-03-23 | 15 | 78.95% | 19 | 100% | 19
2023-08-03 | 9 | 64.29% | 14 | 100% | 14

## QO6 (hidden)
Objective 6: | Completion of Internal Audits
Owner: | Ashley M
How Tracked? | Audit Register
Goal | 14 | Total Processes
Date | Audits Completed
2023-03-23 | 2 | 14.29%
2023-07-19 | 8 | 57.14%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## QO7 (hidden)
Objective 7: | Customer Satisfaction Surveys to Major Customers
Owner: | Tony R
How Tracked? | Survey Folder in Docushare
Goal | 100%
| 4 | major customers provided a survey in 2023
Date | Completed Surveys | Percent
2023-03-23 | 1 | 25%
2023-07-19 | 3 | 75%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## QO8 (hidden)
Objective 8: | Acceptance Criteria Reports for Major Projects
Owner: | Ed Daly
How Tracked?
Goal | 100% | acceptance criteria reports sent with deliveries to 5 major projects
Date | Acceptance Criteria Report | Deliveries to Major Projects | Percent sent
2023-03-23 | 0 | 0 | #DIV/0!
2023-08-04 | 2