## PrimaryWinWgdSteps
Step # |  | Work Step Description | Traveler ID | Optional Step? | Hyperlink to DRAFT | Author | Reviewer 1 (SRFOPS SME or WCL) | Reviewer 2 (SRFOPS WCL or Group Lead) | Project Representative | NCR Informative | NCR Dispositioners | D3 Emails
1 | A | Brazed Ceramic Assembly and Visual Check | C100R-FURN-CEBRZ-BRAZ |  | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262703/C100R-FURN-CEBRZ-BRAZ_R1.docx
| B | Leak Check | C100R-CMA-WINWGD-LEAK |  | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262706/C100R-CMA-WINWGD-LEAK_R1.docx
| C | Degrease | C100R-CHEM-COMP-DEGR |  | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262708/C100R-CHEM-COMP-DEGR-R2.docx
2 | A | Window Brazement Adapter | C100R-FURN-WBA-BRAZ |  | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262702/C100R-FURN-WBA-BRAZ_R1.docx
| B | Leak Check | C100R-CMA-WINWGD-LEAK |  | Open new instance of Traveler
| C | Degrease | C100R-CHEM-COMP-DEGR |  | Open new instance of Traveler
| D | RF Test | C100R-CMTF-WINWGD-HPRF | Optional | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262705/C100R-CMTF-WINWGD-HPRF_R1.docx
| E | Leak Check | C100R-CMA-WINWGD-LEAK | Optional | Open new instance of Traveler
| F | Degrease | C100R-CHEM-COMP-DEGR | Optional | Open new instance of Traveler
3 | A | Send to Ion Implantation | None |  | N/A
| B | JLAB Shipping Authorization Form | N/A (INSIGHT) |  | https://misportal.jlab.org/railsForms/shipping_authorizations/new
| C | SRFOPS Internal Shipping Communication Form | N/A (PANSOPHY >> FACILITIES >> SHIPPING FORM) |  | https://pansophy.jlab.org/pansophy/Facilities/SRFOPS_ShippingForm.cfm
4 | A | Visual Inspection after Ion Implantation | C100R-FURN-WBA-INSP |  | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262701/C100R-FURN-WBA-INSP_R1.docx
| B | Leak Check | C100R-CMA-WINWGD-LEAK |  | Open new instance of Traveler
| C | Degrease | C100R-CHEM-COMP-DEGR |  | Open new instance of Traveler
| D | RF Test | C100R-CMTF-WINWGD-HPRF | Optional | Open new instance of Traveler
| E | Leak Check | C100R-CMA-WINWGD-LEAK | Optional | Open new instance of Traveler
| F | Degrease | C100R-CHEM-COMP-DEGR | Optional | Open new instance of Traveler
5 | A | Send to Anti-Multipacting Coating | None |  | N/A
| B | JLAB Shipping Authorization Form | N/A (INSIGHT) |  | https://misportal.jlab.org/railsForms/shipping_authorizations/new
| C | SRFOPS Internal Shipping Communication Form | N/A (PANSOPHY >> FACILITIES >> SHIPPING FORM) |  | https://pansophy.jlab.org/pansophy/Facilities/SRFOPS_ShippingForm.cfm
6 | A | Visual Inspection after Anti-Multipacting Coating | C100R-FURN-WBA-INSP |  | Open new instance of Traveler
| B | Leak Check | C100R-CMA-WINWGD-LEAK |  | Open new instance of Traveler
| C | Degrease | C100R-CHEM-COMP-DEGR |  | Open new instance of Traveler
| D | RF Test | C100R-CMTF-WINWGD-HPRF | Optional | Open new instance of Traveler
| E | Leak Check | C100R-CMA-WINWGD-LEAK | Optional | Open new instance of Traveler
| F | Degrease | C100R-CHEM-COMP-DEGR | Optional | Open new instance of Traveler
7 | A | Double Sided Rectangular Flange Inspection | C100R-INSP-DSRF |  | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262711/C100R-INSP-DSRF_R1.docx
8 | A | Window Assembly | C100R-FURN-WIN-ASSY |  | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262700/C100R-FURN-WIN-ASSY_R1.docx
| B | Welded Window Flange | C100R-CMA-WIN-WELD |  | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262707/C100R-CMA-WIN-WELD_R1.docx
| C | Leak Check | C100R-CMA-WINWGD-LEAK |  | Open new instance of Traveler
| D | Degrease | C100R-CHEM-COMP-DEGR |  | Open new instance of Traveler
| E | RF Test | C100R-CMTF-WINWGD-HPRF |  | Open new instance of Traveler
| F | Leak Check | C100R-CMA-WINWGD-LEAK |  | Open new instance of Traveler
| G | Degrease | C100R-CHEM-COMP-DEGR |  | Open new instance of Traveler
9 | A | Window Assembly | C100R-FURN-WIN-ASSY |  | Return to Previously Opened Traveler
| B | Adapter Weld to Window | C100R-EBW-WINWGD |  | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262704/C100R-EBW-WINWGD_R1.docx
| C | Leak Check | C100R-CMA-WINWGD-LEAK |  | Open new instance of Traveler
| D | Degrease | C100R-CHEM-COMP-DEGR |  | Open new instance of Traveler
10 | A | Waveguide Inspection | C100R-INSP-WGD |  | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262710/C100R-INSP-WGD_R1.docx
11 | A | Welded Window Waveguide Assembly | C100R-FURN-WINWGD-ASSY |  | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262712/C100R-FURN-WINWGD-ASSY_R1.docx
| B | Weld Window to Waveguide | C100R-EBW-WINWGD |  | Open new instance of Traveler
| C | Leak Check | C100R-CMA-WINWGD-LEAK |  | Open new instance of Traveler
| D | Degrease | C100R-CHEM-COMP-DEGR |  | Open new instance of Traveler
| E | RF Test | C100R-CMTF-WINWGD-HPRF | Optional | Open new instance of Traveler
| F | Leak Check | C100R-CMA-WINWGD-LEAK | Optional | Open new instance of Traveler
| G | Degrease | C100R-CHEM-COMP-DEGR | Optional | Open new instance of Traveler
| H | Welded Window to Waveguide Inspection | C100R-INSP-WINWGD |  | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262709/C100R-INSP-WINWGD_R1.docx
Existing Travelers
|  | Secondary Window Inspection | C100R-INSP-WIN-RCYC
|  | New Waveguide Inspection | C100R-CAV-INSP-WGD

## NewTravelers
| Work Step Description | Traveler ID | Hyperlink to DRAFT | Author | Reviewer 1 (SRFOPS SME or WCL) | Reviewer 2 (SRFOPS WCL or Group Lead) | Project Representative | NCR Informative | NCR Dispositioners | D3 Emails
Uploaded | Degrease | C100R-CHEM-COMP-DEGR | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262708/C100R-CHEM-COMP-DEGR-R2.docx | R. Fiedler | T. Ganey | A. Mitchell | A. Reilly | areilly | ashleya,ganey | areilly,ashleya,ganey
| Welded Window Flange | C100R-CMA-WIN-WELD | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262707/C100R-CMA-WIN-WELD_R1.docx | S. Williams | A. Auston | J. Fischer | A. Reilly | areilly,fischer | scott,grose,ganey | areilly,fischer,scott,grose,ganey
Approved | Leak Check | C100R-CMA-WINWGD-LEAK | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262706/C100R-CMA-WINWGD-LEAK_R1.docx | G. Grose | S. Williams | C. Wilcox | A. Reilly | areilly,wilcox | scott,gross,forehand,dreyfuss,ganey | areilly,wilcox,scott,gross,forehand,dreyfuss,ganey
Uploaded | RF Test | C100R-CMTF-WINWGD-HPRF | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262705/C100R-CMTF-WINWGD-HPRF_R1.docx | M. Drury | M. McCaughan | M. Drury | A. Reilly | areilly,michaelm | scott,grose,drury,ganey | areilly,michaelm,scott,grose,drury,ganey
Approved | Adapter Weld to Window | C100R-EBW-WINWGD | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262704/C100R-EBW-WINWGD_R1.docx | S. Williams | G. Grose | A. O'Brien | A. Reilly | areilly | grose,scott,ganey,aobrien | areilly,grose,scott,ganey,aobrien
Approved | Brazed Ceramic Assembly and Visual Check | C100R-FURN-CEBRZ-BRAZ | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262703/C100R-FURN-CEBRZ-BRAZ_R1.docx | G. Grose |  | S. Williams | A. Reilly | areilly | scott,grose,ganey | areilly,scott,grose,ganey
Approved | Window Brazement Adapter | C100R-FURN-WBA-BRAZ | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262702/C100R-FURN-WBA-BRAZ_R1.docx | G. Grose |  | S. Williams | A. Reilly | areilly | scott,grose,ganey | areilly,scott,grose,ganey
Approved | Visual Inspection after Ion Implantation | C100R-FURN-WBA-INSP | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262701/C100R-FURN-WBA-INSP_R1.docx | G. Grose |  | S. Williams | A. Reilly | areilly | scott,grose,ganey | areilly,scott,grose,ganey
Approved | Window Assembly | C100R-FURN-WIN-ASSY | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262700/C100R-FURN-WIN-ASSY_R1.docx | G. Grose |  | S. Williams | A. Reilly | areilly | scott,grose,ganey | areilly,scott,grose,ganey
Approved | Welded Window Waveguide Assembly | C100R-FURN-WINWGD-ASSY | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262712/C100R-FURN-WINWGD-ASSY_R1.docx | G. Grose |  | S. Williams | A. Reilly | areilly,dreyfuss,forehand | scott,grose,ganey | areilly,dreyfuss,forehand,scott,grose,ganey
| Double Sided Rectangular Flange Inspection | C100R-INSP-DSRF | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262711/C100R-INSP-DSRF_R1.docx | S. Williams | E. Mosby | A. McEwen | A. Reilly | areilly,fischer | scott,grose,ganey | areilly,fischer,scott,grose,ganey
| Waveguide Inspection | C100R-INSP-WGD | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262710/C100R-INSP-WGD_R1.docx | S. Williams | E. Mosby | A. McEwen | A. Reilly | areilly | scott,grose,ganey,lzhao | areilly,scott,grose,ganey,lzhao
| Welded Window to Waveguide Inspection | C100R-INSP-WINWGD | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-262709/C100R-INSP-WINWGD_R1.docx | S. Williams | E. Mosby | A. McEwen | A. Reilly | areilly | scott,grose,ganey,dreyfuss,forehand | areilly,scott,grose,ganey,dreyfuss,forehand

## Open Travelers
Travelers: | To be Archived | # of Travelers Open | # of Travelers Closed
C100R-CAV-INSP-WGD-RCYC | Yes | 0 | 39
C100R-CAV-RWRK-WGD | Yes | 0 | 2
C100R-CST-ASSY-WGD | Yes | 0 | 35
C100R-FURN-WINW-BRAZ | Yes | 0 | 25
C100R-INSP-ADPT | Yes | 24 | 22
C100R-INSP-WIN | Yes | 0 | 23
C100R-INSP-WIN-RCYC | No (for secondary windows) | 0 | 18
C100R-WELD-WIN-ASSY | Yes | 0 | 24
C100R-CAV-INSP-WGD | No (for new waveguides) | 0 | 8

## C100R-INSP-ADPT_Data
User Defined Query on 08-Nov-22
WINWSN | TECHNICIANNAME | DATETIME | CONTAINERDAMAGED | CONTAINERPICS | SHIPDOCOK | SHIPDOCDETAIL | VISUALCLEAN | VISUALCERAMIC | VISUALCOMMENT | SWEEPPASS | DIM_WIDTH | DIM_LENGTH | DIM_THK | DIM_RADIUS1 | DIM_RADIUS2 | DIM_RADIUS3 | DIM_RADIUS4 | DIM_WIDTHPASSED | DIM_LENGTHPASSED | DIM_THKPASSED | DIM_RADIUS1PASSED | DIM_RADIUS2PASSED | DIM_RADIUS3PASSED | DIM_RADIUS4PASSED | DIM_OPENING_1 | DIM_OPENING_2 | DIM_OPENING_3 | DIM_OPENING_1PASSED | DIM_OPENING_2PASSED | DIM_OPENING_3PASSED | DIM_CERTHK_1 | DIM_CERTHK_2 | DIM_CERTHK_3 | DIM_CERTHK_1PASSED | DIM_CERTHK_2PASSED | DIM_CER_THK_2 | INITIALLEAKTECHNAME | INITIALLEAKPASS | INITIALLEAKFILE | RF_TECHNAME | RF1_TIME | UPLOADRF_FILE | RF_TESTCOMMENT | FINALLEAKTECHNAME | FINALLEAKTIME | FINALLEAKPASS | FINALLEAKFILE | SHIPIONTECHNAME | SHIPIONDATE | TITECHNAME | TIDATE | TICONTAINEROK | TIVISPASS | TICOMMENT | TI_RF_SMPL | TI_ILEAK_TECH | TI_ILEAK_DATE | TI_ILEAK_PASS | TI_RF_TECH | TI_RF_DATE | TI_RF_FILE | TI_RF_PASS | TI_FLEAK_TECH | TI_FLEAK_DATE | TI_FLEAK_PASS | SHIP_ANTI | SHIP_ANTI_DATE | TIO2_TECH_NAME | TIO2_DATE | TIO2_CONTAINEROK | TIO2_VISPASS | TIO2_COMMENT | TIO2_RF_SMPL | TIO2_ILEAKTECH | TIO2_ILEAKDATE | TIO2_ILEAKPASS | TIO2_RF_TECH | TIO2_RF_DATE | TIO2_RF_FILE | TIO2_RF_PASS | TIO2_FLEAKTECH | TIO2_FLEAKDATE | TIO2_FLEAKPASS | TIO2_FLEAKFILE
JL100 | GEORGED | 2020-11-09 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | Visual okay. | Yes | 1.719 | 5.532 | 0.624 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.987 | 0.983 | 0.987 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 99CB7E42-B9AD-3F8F-074E9635B79C6F1D | LPAGE | 2020-10-08 |  | Eyelet tested 126'C at 12kW | PROSPER | 2020-10-09 | Yes | DFE4E973-D0B9-6B93-EAE3CBED7CF8071E | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2020-12-10 |  | Yes | PROSPER | 2020-12-11 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2021-02-09 |  | Yes | PROSPER | 2021-02-10 | Yes
JL101 | GEORGED | 2020-11-10 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | Visual okay. | Yes | 1.718 | 5.534 | 0.627 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.99 | 0.988 | 0.989 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 99E0D4B8-AC68-281F-09CACA8AED86D690 | LPAGE | 2020-10-10 |  | Eyelet tested 126'C at 12kW | PROSPER | 2020-10-11 | Yes |  | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2020-12-16 |  | Yes | PROSPER | 2020-12-16 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-01 | Yes | LPAGE | 2022-02-02 |  | Yes | PROSPER | 2021-02-10 | Yes
JL102 | GEORGED | 2020-11-10 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | Okay. | Yes | 1.718 | 5.534 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.99 | 0.99 | 0.988 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 99EFEE10-C034-6E89-AA78A44D05B5C3C8 | LPAGE | 2020-10-09 |  | Eyelet tested 126'C at 12kW | PROSPER | 2020-10-09 | Yes | E02F9BB5-EF55-330C-49D6E9459F5EE41D | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2020-12-11 |  | Yes | PROSPER | 2020-12-12 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2012-02-12 |  | Yes | PROSPER | 2012-02-13 | Yes
JL103 | GEORGED | 2020-11-10 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | OK. | Yes | 1.718 | 5.534 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.99 | 0.988 | 0.988 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 9A24C725-B238-B81C-AB703BB426F82FF7 | LPAGE | 2020-10-07 |  | Eyelet tested 130'C at 12kW | PROSPER | 2020-10-09 | Yes | 1FE24A8E-E821-C75B-38AC54ADC79887B3 | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | SCOTT | 2020-12-10 | Yes | LPAGE | 2020-12-14 |  | Yes | PROSPER | 2020-12-15 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2021-03-22 |  | Yes | PROSPER | 2021-03-23 | Yes
JL104 | GEORGED | 2020-11-10 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | Ok. | Yes | 1.718 | 5.534 | 0.624 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.987 | 0.988 | 0.988 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 9A3316C7-B872-BFE4-8528B0D942758C62 | LPAGE | 2020-10-07 |  | Eyelet tested 129'C at 12kW | PROSPER | 2020-10-08 | Yes | E03EB55A-994A-54BB-8612BF3493F4E7D1 | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2020-12-14 |  | Yes | PROSPER | 2020-12-15 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2021-11-02 |  | Yes | PROSPER | 2021-11-02 | Yes
JL105 | GEORGED | 2020-11-10 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | Okay. | Yes | 1.718 | 5.533 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.99 | 0.991 | 0.99 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 9B528A49-9505-00E1-DAC2D3128E8CB32F | LPAGE | 2020-10-07 |  | Eyelet tested 128'C at 12kW | PROSPER | 2020-10-09 | Yes | 133E5D1F-A210-65C6-15C5D442DE4ADB74 | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2020-12-16 |  | Yes | PROSPER | 2020-12-17 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2021-03-22 |  | Yes | PROSPER | 2021-03-23 | Yes
JL106 | GEORGED | 2020-11-10 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | Okay. | Yes | 1.718 | 5.533 | 0.622 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.988 | 0.989 | 0.99 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 9B6FF214-C666-9FE6-0A91B1D6A30E6D90 | LPAGE | 2020-10-09 |  | Eyelet tested 133'C at 12kW | PROSPER | 2020-10-10 | Yes | 13306628-F8E3-318B-79C495BC3DF12615 | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2020-12-16 |  | Yes | PROSPER | 2020-12-17 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 |  | LPAGE | 2021-03-22 |  | Yes | PROSPER | 2021-03-23 | Yes
JL107 | GEORGED | 2020-11-10 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | Okay. | Yes | 1.719 | 5.533 | 0.624 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.99 | 0.99 | 0.991 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 9B8A05D9-B6D1-4CFA-AB2F8F24B02EF78C | LPAGE | 2020-10-08 |  | Eyelet tested 131'C at 12kW | PROSPER | 2020-10-09 | Yes | 131FC4EA-9594-C72D-6005B8312F259447 | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2020-12-17 |  | Yes | PROSPER | 2020-12-18 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2021-02-12 |  | Yes | PROSPER | 2021-02-13 | Yes
JL108 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | Ok | Yes | 1.719 | 5.533 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.988 | 0.988 | 0.989 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 9B9994E7-F198-5210-9CDA1D5FC18077E2 | LPAGE | 2020-10-09 |  | Eyelet tested 125'C at 12kW | PROSPER | 2020-10-09 | Yes | 13076447-BF05-AB82-FEA2BF03A1E20A20 | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2020-12-17 |  | Yes | PROSPER | 2020-12-18 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2021-03-23 |  | Yes | PROSPER | 2021-03-24 | Yes
JLAB-69 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | Okay. Note - weld spatter on face of flange. | Yes | 1.718 | 5.532 | 0.626 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.988 | 0.989 | 0.99 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes |  | LPAGE | 2020-10-06 |  | Eyelet tested 134'C at 12kW | PROSPER | 2020-10-09 | Yes | B24B9DAD-0F4B-4A6A-64A7D905503F104C | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2021-01-06 |  | Yes | PROSPER | 2021-01-07 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2021-03-08 |  | Yes | PROSPER | 2021-03-09 | Yes
JL109 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | Ok | Yes | 1.718 | 5.534 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.989 | 0.988 | 0.99 | Yes | Yes | Yes | 0.095 | 0.096 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 9BAB1FE6-969C-0B46-90E8CBFC2E910714 | LPAGE | 2020-10-14 |  | Eyelet tested 127'C at 12kW | PROSPER | 2020-10-15 | Yes | 7C96FAC3-C251-DD04-C0F5F1BC41E877E0 | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2020-12-17 |  | Yes | PROSPER | 2020-12-18 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2012-02-15 |  | Yes | PROSPER | 2012-02-16 | Yes
JL110 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | Ok | Yes | 1.718 | 5.534 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.988 | 0.988 | 0.988 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 9BB972B2-A4E7-3A47-84E768256A744A88 | LPAGE | 2020-10-14 |  | Eyelet tested 125'C at 12kW | PROSPER | 2020-10-15 | Yes | 7CA3156F-CAB7-CA6D-11F3952504B2F83E | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2020-12-18 |  | Yes | PROSPER | 2020-12-19 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2021-03-23 |  | Yes | PROSPER | 2021-03-24 | Yes
JL111 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | Ok | Yes | 1.717 | 5.533 | 0.624 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.988 | 0.989 | 0.989 | Yes | Yes | Yes | 0.095 | 0.096 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 9BEDE788-E8E0-A9D9-2BF9F5A5F28B213F | LPAGE | 2020-10-15 |  | Eyelet tested 131'C at 12kW | PROSPER | 2020-10-16 | Yes | 7CAEC385-017C-B30D-E10D48D8D983406C | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2020-12-18 |  | Yes | PROSPER | 2020-12-19 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2012-02-15 |  | Yes | PROSPER | 2012-02-16 | Yes
JL112 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | Ok. | Yes | 1.717 | 5.533 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.99 | 0.99 | 0.99 | Yes | Yes | Yes | 0.095 | 0.096 | 0.096 | Yes | Yes | Yes | PROSPER | Yes | 9C1F1FF7-F33B-9E6A-3358D10D31715406 | LPAGE | 2020-10-15 |  | Eyelet tested 129'C at 12kW | PROSPER | 2020-10-16 | Yes | 7CBBBEFD-FB52-C181-6E8819037783F249 | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2020-12-21 |  | Yes | PROSPER | 2020-12-21 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2021-03-24 |  | Yes | PROSPER | 2021-03-25 | Yes
JL113 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | Ok. | Yes | 1.718 | 5.533 | 0.624 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.989 | 0.988 | 0.99 | Yes | Yes | Yes | 0.095 | 0.095 | 0.096 | Yes | Yes | Yes | PROSPER | Yes | 9C3F846F-ED01-2420-C916721EC2172372 | LPAGE | 2020-10-15 |  | Eyelet tested 129'C at 12kW | PROSPER | 2020-10-16 | Yes | 7CCC0770-9765-83C0-1A1F0EDDDDDBA9B9 | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2020-12-21 |  | Yes | PROSPER | 2020-12-22 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2021-03-24 |  | Yes | PROSPER | 2021-03-25 | Yes
JL114 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | Ok | Yes | 1.718 | 5.533 | 0.624 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.99 | 0.988 | 0.989 | Yes | Yes | Yes | 0.096 | 0.096 | 0.096 | Yes | Yes | Yes | PROSPER | Yes |  | LPAGE | 2020-10-16 |  | Eyelet tested 129'C at 12kW | PROSPER | 2020-10-17 | Yes | B1CDE6CD-AD5C-B5C4-DF0F5161B54D67B1 | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2020-12-21 |  | Yes | PROSPER | 2020-12-22 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 |  | Yes |  | Yes | POWERS | 2021-02-08 | Yes | LPAGE | 2021-03-25 |  | Yes | PROSPER | 2021-03-26 | Yes
JL115 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | Ok | Yes | 1.718 | 5.533 | 0.624 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.988 | 0.99 | 0.99 | Yes | Yes | Yes | 0.095 | 0.096 | 0.096 | Yes | Yes | Yes | PROSPER | Yes |  | LPAGE | 2020-10-19 |  | Eyelet tested 132'C at 12kW | PROSPER | 2020-10-20 | Yes | B1DD7933-9743-0512-2C04735C6113EC80 | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2020-12-22 |  | Yes | PROSPER | 2020-12-23 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2022-02-16 |  | Yes | PROSPER | 2022-02-17 | Yes
JL116 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | Ok | Yes | 1.718 | 5.534 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.99 | 0.99 | 0.99 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes |  | LPAGE | 2020-10-19 |  | Eyelet tested 127'C at 12kW | PROSPER | 2020-10-20 | Yes | B1EEE51F-FCE6-7F26-4406A817D93DE038 | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2020-12-22 |  | Yes | PROSPER | 2020-12-23 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2021-02-16 |  | Yes | PROSPER | 2021-02-17 | Yes
JL117 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | Okay. | Yes | 1.717 | 5.533 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.988 | 0.988 | 0.988 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes |  | LPAGE | 2020-10-20 |  | Eyelet tested 127'C at 12kW | PROSPER | 2020-10-21 | Yes | B214EECA-C17C-2F82-5434C41E53D473AD | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 |  | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2020-12-23 |  | Yes | PROSPER | 2020-12-23 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2021-03-02 |  | Yes | PROSPER | 2021-03-03 | Yes
JL118 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | OK. | Yes | 1.718 | 5.533 | 0.624 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.99 | 0.99 | 0.99 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes |  | LPAGE | 2020-10-21 |  | Eyelet tested 125'C at 12kW | PROSPER | 2020-10-22 | Yes | B232B572-C890-A505-A20F51C868C77BE4 | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2021-01-04 |  | Yes | PROSPER | 2021-01-07 |  |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2021-03-02 |  | Yes | PROSPER | 2021-03-03 | Yes
JL119 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | OK | Yes | 1.717 | 5.533 | 0.624 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.988 | 0.988 | 0.99 | Yes | Yes | Yes | 0.096 | 0.095 | 0.096 | Yes | Yes | Yes | PROSPER | Yes |  | LPAGE | 2020-10-22 |  | Eyelet tested 129'C at 12kW | PROSPER | 2020-10-23 | Yes | 7B8EB6AA-EA6F-A84C-4F3D0A96EFB8416F | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2021-01-05 |  | Yes | PROSPER | 2021-01-11 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2021-03-19 |  | Yes | PROSPER | 2021-03-20 | Yes | EDA29CD5-005C-B783-B2FD3FF3A2B1C627
JL120 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | Yes | Yes | OK | Yes | 1.718 | 5.533 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.989 | 0.989 | 0.99 | Yes | Yes | Yes | 0.095 | 0.096 | 0.096 | Yes | Yes | Yes | PROSPER | Yes |  | LPAGE | 2020-10-22 |  | Eyelet tested 125'C at 12kW | PROSPER | 2020-10-23 | Yes | 7B9A8419-FFD9-185F-DBE988A5B4BD5715 | SCOTT | 2020-10-24 | SCOTT | 2020-12-10 | Yes | Yes |  | Yes | PROSPER | 2020-12-10 | Yes | LPAGE | 2020-12-10 |  | Yes | PROSPER | 2020-12-11 | Yes |  | 2021-01-12 | SCOTT | 2021-01-22 | Yes | Yes |  | Yes | PROSPER | 2021-02-08 | Yes | LPAGE | 2021-03-21 |  | Yes | PROSPER | 2021-03-22 | Yes | EDCA951E-AC4E-8130-046A84B8557EAD88
JL-121 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes | [28 empty] | CLIGHT | Yes |  | LPAGE | 2022-08-19 |  |  | PROSPER | 2022-08-19 | Yes |  | SCOTT | 2022-10-07 | GROSE | 2022-10-19 | Yes | Yes | Discoloration on ion implantation side of ceramic-grey lines present
JL-122 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes | [28 empty] | CLIGHT | Yes |  | LPAGE | 2022-08-16 |  |  | PROSPER | 2022-08-19 | Yes |  | SCOTT | 2022-10-07 | GROSE | 2022-10-19 | Yes | Yes | Discoloration on ion implantation side of ceramic-grey lines present
JL-123 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-124 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-125 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-126 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-127 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-129 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-130 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-131 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-132 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-133 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-134 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-135
JL-136 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-137 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-138 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-139 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-140 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-141 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-142 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-143 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-144 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
JL-145 | GROSE | 2022-10-25 | No |  | Yes |  | Yes | Yes
C100R-FURN-WBA-BRAZ | C100R-INSP-ADPT | Other
VisInspTechName | TechnicianName
VisInspDateTime | DateTime
WBASN | WINWSN
VisualClean | VisualClean
VisualCeramic | VisualCeramic
VisualPics | VisualPics
VisualComment | VisualComment
SweepPass | SweepPass
LeakCheck1OK | InitialLeakPass
LeakCheck1Complete
RFTested | If RF_TechName is not blank, then "Yes"; else "No"
RFTestOK
RFTestCompleted | RF1_Time
LeakCheck2OK | FinalLeakPass
LeakCheck2Complete | FinalLeakTime
ReadyForIon | If ShipIonTechName is not blank, then "Yes"; else "No"
ReadyforIonDate | ShipIonDate
C100R-FURN-WBA-INSP | C100R-INSP-ADPT | Other
InspTech | TiTechName
InspDate | TiDate
WBASN | WINWSN
InspReason |  | Ion Implantation
InspReasonComment
ContainerOK | TiContainerOK
InspPass | TiVisPass
InspComment | TiComment
InspImage | VisualPics
LeakCheck1OK | Ti_Ileak_Pass
LeakCheck1Complete | Ti_Ileak_Date
RFTested | Ti_RF_smpl
RFTestOK | Ti_RF_Pass
RFTestCompleted | Ti_RF_Date
LeakCheck2OK | Ti_Fleak_Pass
LeakCheck2Complete | Ti_FLEeak_Date
C100R-CMTF-WINWGD-HPRF | C100R-INSP-ADPT | Other
RFTestTech | RF_TechName
RFTestDate | RF1_Time
RFTestReason |  | Adapter Brazement Assembly
ReasonOtherComment
CompType |  | WBA
WBASN | WINWSN
RFTestPassed
RFTestCompleteDate | RF1_Time
RFTestFile | UploadRF_file
RFTestComment | RF_TestComment
C100R-CMA-WINWGD-LEAK | C100R-INSP-ADPT | Other
LeakCheckTech | InitalLeakTechName
LeakCheckDate
LeakCheckReason |  | Adapter Brazement Assembly
ReasonOtherComment
CompType |  | WBA
WBASN | WINWSN
LeakCheckPassed | InitialLeakPass
LeakCheckCompleteDate
LeakCheckFile | InitialLeakFile
LeakCheckComment
C100R-CMTF-WINWGD-HPRF | C100R-INSP-ADPT | Other
RFTestTech | Ti_RF_Tech
RFTestDate | Ti_RF_Date
RFTestReason |  | After Ion Implantation
ReasonOtherComment
CompType |  | WBA
WBASN | WINWSN
RFTestPassed | Ti_RF_Pass
RFTestCompleteDate | Ti_RF_Date
RFTestFile | Ti_RF_file
RFTestComment
C100R-CMA-WINWGD-LEAK | C100R-INSP-ADPT | Other
LeakCheckTech | Ti_ILeakTech
LeakCheckDate | Ti_Ileak_Date
LeakCheckReason |  | After Ion Implantation
ReasonOtherComment
CompType |  | WBA
WBASN | WINWSN
LeakCheckPassed | Ti_Ileak_Pass
LeakCheckCompleteDate
LeakCheckFile
LeakCheckComment