Hot

Check Out

Key Activities and Dates thru February

(subject to change)

RECO Kick-Off Meeting, Feb 19th @ 1530 in MCC

  - February 16th  - February 17th

    - Inj/Beam Permit ~ 1030 – 2000

    - NL lock-up 0700 for SRF commissioning.

    - Call-Ins for show stoppers.

    - Last two days for SL access. HCO W/O beam should be performed.

  - February 18th  - February 19th

    - Inj/Beam Permit 0800 – 2000

    - NL remains locked-up for SRF commissioning.

    - SL lock-up sometime during day shift on 18th.

    - Call-Ins for show stoppers.

    - BSY in PP

    - RF and Magnet groups perform early HCO

    - PSS certification 1600 – Halls/BSY

  - February 20th  - February 21st (Weekend)

    - NL and SL/Power Permit for SRF commissioning.

    - RF Group On-Call for show stoppers

  - February 22nd

    - RECO ‘Opening Day’

    - Inj/Beam Permit. Basically remains locked-up from now on.

    - All cryomodules FULL

    - NL/SL remain locked-up for SRF commissioning.

    - BSY in PP

    - RF and Magnet groups continue early HCO

    - PSS certification 1600 – SL

  - February 23rd

    - Float for SRF commissioning NL/SL might be locked-up. If not, both Linacs’ will be open for repairs.

    - PSS certification 1600 – SL

  - February 24th-February 26th

    - Full machine lock-up 1030.

    - RF and Magnets ON for pre-PSS certification.

    - PSS certification 1600 – NL/Inj and Functional Tests on the 26th.

    - PSS Float on the 27th.