## Slide 1
Closeout Report on the
DOE/SC CD-2-3 Review of the
Proton Power Upgrade (PPU) Project
Oak Ridge National Laboratory
July 14-17, 2019
Ethan Merrill
Committee Chair
Office of Science, U.S. Department of Energy
http://www.science.doe.gov/opa/

## Slide 2: Review Committee Participants
Ethan Merrill, DOE/SC, Chairperson
Jeff McGhee, ANL

## Slide 3: Charge Questions
Design Maturity: Is the final design sufficiently well-defined and technically sound to achieve the specified technical performance requirements and to establish a performance baseline and start construction?
Project Scope: Will the project scope, as currently defined, achieve the objectives in the Mission Need Statement? Is the Work Breakdown Structure dictionary and are the key performance parameters (KPPs) appropriately defined to establish a credible performance baseline and start construction?
Cost and Schedule: Are the cost and schedule estimates, including contingencies, mature and of sufficient quality to establish a credible cost and schedule performance baseline and to start construction? Are the cost, schedule, and performance metrics being properly collected and updated? Are major cost and schedule assumptions, resource constraints, and project risks, including COVID-19, being adequately addressed?
Technical: Is the technical progress to date sufficient to meet the performance specifications and support the procurements and installation as planned? Is the trajectory appropriate for meeting the threshold KPPs by CD-4?
Management: Is the project being properly planned, managed, and staffed to successfully deliver the scope within the proposed cost and schedule? Does the project have the necessary resources? Are project risks being appropriately identified and managed? Have the requirements for CD-2 and CD-3 been met? Is the project ready for CD-2 and CD-3?
ES&H/QA: Are Environment, Safety, and Health and Quality Assurance (ES&H/QA) requirements and plans, including COVID-19 protections and safety measures, being properly addressed?
Recommendations: Have past review recommendations been appropriately addressed?

## Slide 4: 2.1 Superconducting RF M. Kelly, ANL T. Nicol, FNAL Subcommittee 1
Design Maturity: Is the final design sufficiently well-defined and technically sound to achieve the specified technical performance requirements and to establish a performance baseline and start construction? Yes.
Project Scope: Will the project scope, as currently defined, achieve the objectives in the Mission Need Statement? Yes. Is the Work Breakdown Structure dictionary and are the key performance parameters (KPPs) appropriately defined to establish a credible performance baseline and start construction? Yes.
Technical: Is the technical progress to date sufficient to meet the performance specifications and support the procurements and installation as planned? Is the trajectory appropriate for meeting the threshold KPPs by CD-4? Yes. Many procurements are ongoing and will need to be monitored closely, especially so in this time of limited travel.
Recommendations: Have past review recommendations been appropriately addressed? Yes, all previous review recommendations have either been closed or addressed.

## Slide 5: 2.1 Superconducting RF M. Kelly, ANL, T. Nicol, FNAL Subcommittee 1
Findings
The PPU will double the SNS beam power capability from 1.4 MW to 2.8 MW. 30% of the beam power will come from an increase in beam energy. 50% will come from an increase in beam current.
Long lead procurements have been previously approved and initiated. The CD-3A approval provided $10.5M for cavities and couplers. The CD-3B approval provided $53.4M for cryomodules and the klystron gallery buildout.
CD-3A contracts for cavities and couplers were placed on schedule and work is approximately 75% complete. Contracts associated with CD-3B have begun and are on schedule. These activities are 19% complete.
The receipt and installation activities for seven new cryomodules are on or near the project critical path. Cryomodule installation is required to coincide with planned maintenance outages from FY2022 to FY2024.
Jefferson Laboratory (JLab) is the PPU partner for cryomodules. JLab does have other significant and overlapping commitments. The LCLS-II project work is wrapping up, while LCLS-II-HE and PPU are ramping up.

## Slide 6: 2.1 Superconducting RF M. Kelly, ANL T. Nicol, FNAL Subcommittee 1
Findings (cont’d)
PPU work at the SNS has been ongoing throughout the first several months of the COVID pandemic. JLab was largely shut down for the early period of the pandemic but restarted PPU activities in June 2020. PPU is indicated to be one of the priority activities and was among the initial restart activities at JLab.
The majority of the PPU managers were present at the original SNS installation. However, JLab is in the process of hiring thirteen new technical staff to meet its cryomodule assembly needs, both for PPU and other projects. Eleven of the planned thirteen staff have been hired to date.
The present field performance of the existing SNS superconducting linac (SCL), when combined with the PPU, would be sufficient to provide the total desired beam energy of 1.3 GeV. No upgrades of the existing SCL are needed. The existing SCL beam energy and power capability were demonstrated in a 1.7 MW beam power test.
All 30 fundamental power couplers have been received at the SNS. Six have been delivered to JLab. Processing is ongoing for the remaining couplers.

## Slide 7: 2.1 Superconducting RF M. Kelly, ANL, T. Nicol, FNAL Subcommittee 1
Findings (cont’d)
As discussed in previous reviews, new PPU cavities use high-purity niobium end groups and have a coupler probe that is slightly thicker and shorter than for the existing SNS couplers. The cryomodule will include a re-design of the warm-to-cold transition. This re-design is led by JLab. The warm-to-cold transition on the beamline is now made in the cleanroom.
Cavities are in production at Research Instruments (RI). An experienced local accelerator scientist has been hired to perform vendor visits on behalf of the SNS. Two additional cavities are being ordered from RI, bringing the total to 32.
The new cavities from Research Instruments will be chemically processed at the vendor. Helium jacketing will be performed at JLab and no subsequent chemistry is planned. The first four RI cavities will be tested at JLab both before and after helium jacketing.
Three original SNS spare cavities have been sent to JLab for jacketing and testing. These cavities will be tested, jacketed, and re-tested by the end of summer 2020.
SCL activities have approved Interface Control Documents (ICDs). One is for the cryomodule assembly at Jefferson Lab and the other for the cryomodule installation in the SNS tunnel.

## Slide 8: 2.1 Superconducting RF M. Kelly, ANL, T. Nicol, FNAL Subcommittee 1
Findings (cont’d)
Costs are about 50% long-lead procurements. The remaining 50% will be based on CD-2/3 approval.
The cryomodule delivery dates are sufficiently advanced to allow strategic cryomodule placement. The project is attempting to have more than the required number of cryomodules on hand for each of the three planned outages. Delivery for the first five cryomodules are, respectively, in Nov. 2021, Feb. 2022, March 2022, May 2022, and July 2022.
Sixteen low and medium risks, and no high-level risks have been identified for SCL systems.
In the context of cryomodule shipping issues for other DOE projects, a cryomodule shipping test has been added to the PPU work scope. A slow tuner test has also been added. In total, one complete cryomodule worth of spare cavities and couplers is included in the project plan.
PPU cryomodules delivered to the SNS from JLab will undergo extensive cold testing up to the operating gradients at the SNS both before and after installation into the tunnel. The new plan for plasma processing is to only perform this on medium beta cryomodules outside of the tunnel.

## Slide 9: 2.1 Superconducting RF M. Kelly, ANL, T. Nicol, FNAL Subcommittee 1
Findings (cont’d)
The cryomodule support saddles are one part of the SNS team scope for the SCL. These are under fabrication in US industry and are behind schedule due to a problem with a subcontracted US vendor. There is presently sufficient float with respect to the project schedule that no impact is expected.
Two medium beta cryomodules (CM1 and CM11) are planned for repair ahead of PPU cryomodule arrivals.
All thirty couplers have been delivered to SNS. Sixteen of thirty couplers received have been tested and conditioned to specifications. RF couplers are currently being conditioned at 700 kW in traveling wave and 600 kW in standing wave.
More bridge waveguides have been ordered, but the SNS has used nearly all existing devices. This could potentially lead to a gap in coupler testing.
There is some risk of delay in delivery of inter-cavity bellows due to a vendor being redirected for other work.

## Slide 10: 2.1 Superconducting RF M. Kelly, ANL, T. Nicol, FNAL Subcommittee 1
Findings (cont’d)
There do not appear to be practical cooldown limits on either the primary or thermal shield circuits. The primary circuit is cooled at a rate of about 100 K/hr with a similar rate on the thermal shield.
A new nozzle is available for one of the turbines. This is designed for 20% increased flow and a corresponding increase in shield refrigeration capacity from 8.3 kW to 10 kW. The new nozzle will only be installed if it is found to be needed at a later date.

## Slide 11: 2.1 Superconducting RF M. Kelly, ANL, T. Nicol, FNAL Subcommittee 1
Comments
PPU managers have experience from the original SNS installation. This reduces the likelihood of loss of institutional knowledge and is important for complex cavity and cryomodule systems.
The SNS vacuum, cryogenics, and controls groups, and the SCL team generally, appear to have sufficient workforce and expertise to carry out the work plan. As with any lean group, the loss key managers or technical staff could have a significant impact.
New technical staff recently hired at JLab will require time on site to ramp up to full productivity. The issue could be compounded by COVID restrictions. So far, the JLab team has not been limited by such restrictions.
The SCL cost and schedule are not yet impacted significantly due to COVID. This appears to be because both the SNS and PPU vendors have continued hands-on work these past months. Required hands-on work at JLab during the shutdown was limited.

## Slide 12: 2.1 Superconducting RF M. Kelly, ANL, T. Nicol, FNAL Subcommittee 1
Comments (cont’d)
Overall, the SCL systems are progressing well with respect to the P6 project plan.
SCL controls work for PPU appears to be progressing well. The approach is to replicate existing cryomodule controls and adjust, where necessary, for obsolescence.
SCL cryogenics work for PPU is a moderately sized effort (cost ~$1M), and also appears to be progressing well. Technical review of the system has been performed as part of major DOE reviews.
SCL utilities work includes vacuum and water systems. This work is also entails mostly a replication of existing systems and progress to date is good.

## Slide 13: 2.1 Superconducting RF M. Kelly, ANL, T. Nicol, FNAL Subcommittee 1
Comments (cont’d)
The JLab/SNS/PPU team have robust tools in place for tracking vendor hardware. Much of the hardware needed to perform work is in hand, but key pieces are still with industrial partners.
Therefore, the team should be willing to change or supplement vendors if necessary. This does not likely apply for cavities, vacuum vessels or other major components, but could be a wise course for smaller components.
Small changes to the cavities and couplers are well thought out. Overall, the SCL system is technically conservative. This adds confidence that systems will perform as planned.
There are planned repairs to three existing SNS cryomodules. These may be time consuming for technical staff but would not appear to have major impact for PPU installation or performance.

## Slide 14: 2.1 Superconducting RF M. Kelly, ANL, T. Nicol, FNAL Subcommittee 1
Comments (cont’d)
The technical choice not to perform cavity chemistry after jacketing is not the normal practice for SRF cavities.
The ongoing work at JLab to test, jacket and re-test three existing cavities from the original SNS is needed to vet the plan for chemistry. If it is found that chemistry is desired after jacketing, this would impact cost and schedule. Even though the team has four spare cavities planned, it would be prudent to consider a course of action in case chemistry after jacketing is needed.
Much information was shared about the status of cavities, helium vessels, and couplers, but other major components are also critical to cryomodule fabrication. These include vacuum vessels, thermal shields, space frames, and tuners. Some of these require close interaction with their respective vendors, particularly if vendors are new. Oversight is more difficult with restricted travel and the project needs to continue with diligence to ensure the status of procured items is understood and that these remain on schedule to the extent possible.

## Slide 15: 2.1 Superconducting RF M. Kelly, ANL, T. Nicol, FNAL Subcommittee 1
Recommendations
Proceed to CD-2/3

## Slide 16: 2.2 Target F. Pellemoine, FNAL; F. Sordo, ESS-Bilbao; M. Calviani, CERN / Subcommittee 2
Design Maturity: Is the final design sufficiently well-defined and technically sound to achieve the specified technical performance requirements and to establish a performance baseline and start construction?
  Yes
Project Scope: Will the project scope, as currently defined, achieve the objectives in the Mission Need Statement? Is the Work Breakdown Structure dictionary and are the key performance parameters (KPPs) appropriately defined to establish a credible performance baseline and start construction?
Yes
Technical: Is the technical progress to date sufficient to meet the performance specifications and support the procurements and installation as planned? Is the trajectory appropriate for meeting the threshold KPPs by CD-4?
Yes
Recommendations: Have past review recommendations been appropriately addressed?
Yes

## Slide 17: 2.2 Target F. Pellemoine, FNAL; F. Sordo, ESS-Bilbao; M. Calviani, CERN / Subcommittee 2
Findings
  PPU will increase the beam power on target from 1.4 to 2 MW, and the beam energy from 1 GeV to 1.3 GeV, involving evaluation and modification on the target and the target station. PPU will deliver 33kJ per pulse at 60 Hz to the FTS and it will extend the FTS facility lifetime from 40 to 60 years.
  Most of FTS (except the target module) was initially designed for 2.0 MW with 1.0 GeV protons. Only the target module needs new design inside the Monolith and it is a replaceable system. All the other hardware inside the Monolith (replaceable or permanent one) are ready for PPU operation and extended lifetime of 60 years. Gas injection increase and beam energy increase imply some work on other subsystem outside of the Monolith. They were evaluated and addressed in the PPU FTS system.
  Contemporary computing power, modeling & simulation techniques have provided more robust and resolved evaluations compared to original SNS efforts.
  The design of the target module is based on 10+ operational experiment and a extensive R&D program.
  High flow gas injection in the target to mitigate the target vessel fatigue and the cavitation damage is essential. Last target (T24) operated at ~1.4 MW up to 2967 MW-hr with a minimum gas flow (0.71 SLPM) with much less cavitation damage and no failure.

## Slide 18: 2.2 Target F. Pellemoine, FNAL; F. Sordo, ESS-Bilbao; M. Calviani, CERN / Subcommittee 2
Findings (cont.)
  Measurements during operation show gas injection reduces strain on target structure by significant amount.
  There is a strong and well-developed collaboration with target manufacturing companies. This manufacturing experience has been integrated in the PPU target.
  The target implementation strategy within PPU includes two “test” targets that will be placed into operation, demonstrating target features and potentially higher beam power. The fabrication of test target 2 will have the same design as of the production targets.
  To streamline the approval process, one purchase requisition will be placed with two-line items : one for one (1) PPU Test Target 2 and one for the three (3) production targets and will not be exercised until CD3 and ESAAB approval is received.
  Collaboration with JPARC was effective on gas injection development (design of bubbler, simulations), the Moderator Cryogenic System, and the Molecular Sieve Beds (tritium retention).

## Slide 19: 2.2 Target F. Pellemoine, FNAL; F. Sordo, ESS-Bilbao; M. Calviani, CERN / Subcommittee 2
Findings (cont.)
  After evaluation of the Target Utility Systems, FTS cooling systems has the capacity for PPU operation. Scope were updated to supply target gas with two different ways : primarily via recirculation and via once-through gas injection as backup to recirculating system.
  Neutronics provide the bases for evaluations, design upgrades, n-performance, facility safety support. There is no design or hardware upgrade scope within neutronics. Confidence builds up on several years of experience and simulation benchmarking.
  The addition of the catalyst beds to each of the three LH2 loops will ensure consistent neutronic performance by maintaining >99% parahydrogen. It will allow to meet the required stability in minutes compare to hours or days.
  The Mercury Process System needs 3 new hardware to support higher flow gas injection (up to 20 SLPM): Mercury Pump Overflow Tank (OFT), Return Line Gas Liquid Separator (GLS), In-cell target gas supply hardware. All of them are well developed for preliminary design status. The final design reviews should be completed by November 2020 and fabrication expect to start early 2021.
  Gas Liquid Separator (GLS) is well developed and mature. Experimental results shows a separation ratio close to 90% which is already above PPU requirements.

## Slide 20: 2.2 Target F. Pellemoine, FNAL; F. Sordo, ESS-Bilbao; M. Calviani, CERN / Subcommittee 2
Findings (cont.)
  The Mercury Off-Gas Treatment System (MOTS) needs upgrades to support higher flow gas injection (up to 20 SLPM): a second delay bed (final design complete), additional cryogenic carbon adsorber (preliminary design), larger molecular sieve beds for the 20 SLPM gas injection flow.
  The vessel, shielding, and instrument systems evaluations confirm that all temperatures and stresses under PPU operation are acceptable.
  5 USIs identified in the HAR are related to the FTS : “beam energy increase” doesn’t require further action, “Target gas injection rate increase” requires a credit Rad Protection Program to control entry to GAR, “introduction of new Orth-Para Catalytic Converter” requires credited catalyst module retention elements, “Excessive Power (>2 MW) Directed to Target” requires credited Beam Power Limiting System (under P.4 WBS).

## Slide 21: 2.2 Target F. Pellemoine, FNAL; F. Sordo, ESS-Bilbao; M. Calviani, CERN / Subcommittee 2
Comments
  The Committee was impressed with the amount of progress and number of tasks performed since the CD-3B review in the various technical subprojects of FTS.
  The design for each sub systems of the FTS is matured at the appropriate level: 2MW target and the delay beds, shielding and crane of the MOTS are ready to proceed to CD3. Mercury Process Systems, Moderator Cryogenic Systems, Target Utility Systems, remaining parts of the MOTS, and the safety-control Systems are ready to proceed to CD2 and are well advanced at that stage.
  P.5 is supported by a very strong and well-balanced team between experienced personal and young staff. New hiring in the Target Utility Systems from industry is beneficial for the project.
  Recent results with operation target on strain measurement with gas injection increase the confidence in the ability of the project to operate PPU target at 2 MW for at least 1,250 hours.
  Having routinely measurements on operation target of the strain vs. the gas flow and the beam power (equivalent beam power) confirmed the efficiency of gas injection for fatigue stress mitigation and the committee encourages to continue this good practice when higher gas rate and higher beam power are available.

## Slide 22: 2.2 Target F. Pellemoine, FNAL; F. Sordo, ESS-Bilbao; M. Calviani, CERN / Subcommittee 2
Comments (cont.)
  The team continues systematic PIE (Post Irradiation Examination) on spent targets to characterize damage and determine leak causes. Again, the committee encourages to continue this good practice to evaluate the effect of gas injection or design modification on fatigue and cavitation mitigation.
  The target implementation strategy includes two “test” targets that will be placed into operation, demonstrating target features and potentially higher beam power. The fabrication of test target 2 will have the same design than the production targets. It will be a good preparation for the fabrication of the production target and it will increase the likelihood of project success.
  Numerous design reviews have been completed and resulted in significant feedback, advancing the designs. This practice should be continued through construction readiness and operations.
  Target welding QA/QC is a critical aspect of the 2 MW operation in view of maximizing reliability. Design reviews and discussions with vendors should be continued with the aim of maximizing the QA in their production. Multiple sourcing of targets should be sought in order to avoid relying on single source expertise. An analysis on whether in-sourcing of some of the components may be cost as well as schedule effective is encouraged.

## Slide 23: 2.2 Target F. Pellemoine, FNAL; F. Sordo, ESS-Bilbao; M. Calviani, CERN / Subcommittee 2
Comments (cont.)
  R&D efforts within (and outside) the PPU project have made substantial contributions to support design and operation improvement. The remaining project R&D tasks should be completed in the next four months. Continuing R&D beyond CD3 and the scheduled project development is strongly encouraged as it will be beneficial for target operation lifetime.
  Most of the upgrade and installation will be performed remotely. The committee supports the new activity to build a mock-up of the Hg Pump Overflow Tank (OFT), and of the Gas Liquid Separator (GLS) for remote installation test. We encourage the team to complete the final design and procure the mock-up as soon as possible to implement any changes if needed in the final design of the OFT and the GLS.
  Extensive R&D led to a Gas Liquid Separator (GLS) that is well developed and mature. Experimental results shows a separation ratio close to 90% which is already above PPU requirements.

## Slide 24: 2.2 Target F. Pellemoine, FNAL; F. Sordo, ESS-Bilbao; M. Calviani, CERN / Subcommittee 2
Comments (cont.)
  In-situ diagnostics with Raman spectroscopy for confirmation of H2 state by using direct laser viewing through dual sapphire windows will provide higher sensitivity than current diagnostics. Integrity test was delayed and started in June. This test needs to be complete ASAP and before end of July to validate the final design (FDR scheduled in August 2020).
  The committee endorses the addition of two trains of two beds to increase reliability and to provide capability to regenerate while MOTS is in operation.
  The thermomechanical evaluation of the working conditions of permanent components (vessel, shielding, inner reflector etc. ) shows acceptable level of temperatures and stresses. The components have been validated according to ASME BPVC criteria, and areas with high radiation level are limited in volume. Based on that, the committee considers that safety margins are acceptable for reliable operation of the components for PPU conditions. The review panel supports the lifetime extension of the facility to 60 years and endorses the increase of the administrative dose limit to 20 DPA for the ORP shell structure.
  It is assumed that the Aluminum PBW will be maintained. Contingency plans should be envisaged in case finally a decision (by Operation) is take to use an Inconel PBW.

## Slide 25: 2.2 Target F. Pellemoine, FNAL; F. Sordo, ESS-Bilbao; M. Calviani, CERN / Subcommittee 2
Comments (cont.)
  Involvement of safety experts and controls experts in each design review is a good practice and should continue during procurement, installation and test/commissioning of the upgraded systems.
  The committee commends the analysis done on the target safety systems and encourages the implementation of the evolutionary upgrades foresee to mitigate the mercury spill events.
  Off-Normal Analysis review for Target Utility System is delayed due to COVID-19 and may impact the final design review and procurement. If the in-person meeting could not take place by autumn, it is suggested to carry out remotely in any case to avoid potential delays in the target procurement.
  COVID-19 impact has been limited on the FTS. Nevertheless, 2 MW target is on critical path and careful follow-up is needed to investigate potential delays with vendors, due to backlog or procurement challenges.

## Slide 26: 2.2 Target F. Pellemoine, FNAL; F. Sordo, ESS-Bilbao; M. Calviani, CERN / Subcommittee 2
Recommendations
  Ready to proceed to CD2-3

## Slide 27: 2.3 RF A. Nassiri, ANL and M. Fazio, SLAC Subcommittee 3
Design Maturity: Is the final design sufficiently well-defined and technically sound to achieve the specified technical performance requirements and to establish a performance baseline and start construction? Yes.
Project Scope: Will the project scope, as currently defined, achieve the objectives in the Mission Need Statement? Yes. Is the Work Breakdown Structure dictionary and are the key performance parameters (KPPs) appropriately defined to establish a credible performance baseline and start construction? Yes.
Technical: Is the technical progress to date sufficient to meet the performance specifications and support the procurements and installation as planned? Yes. LLRF demonstration on the Linac is expected to be completed in Fall 2020. Is the trajectory appropriate for meeting the threshold KPPs by CD-4? Yes.
Recommendations: Have past review recommendations been appropriately addressed? Yes.

## Slide 28: 2.3 RF A. Nassiri, ANL and M. Fazio, SLAC Subcommittee 3
2.3 Findings
  RF Systems technical scope includes: (1) addition of 28 new SCL HPRF stations rated at 700kW peak, (2) upgrade of 3 DTL HPRF stations to 3 MW peak, (3) development of 28 new LLRF systems, (4) upgrade of existing RFQ and DTL modulators to support 3MW operation, (5) addition of 3 new modulators (AT-HVCM) in the SCL, (6) addition of mechanical and electrical utilities in the SCL, (7) upgrade of mechanical systems in the DTL, and (8) EPICS programming and extension of the network, timing, machine, and personnel protection systems.
  The primary requirements for PPU RF Systems are to support the increased beam current of 38mA and the increased beam energy to 1.3 GeV.
  New RF stations to support the new SCL cavities are basically duplicates of the existing RF systems with some improvements.
  To support the proton beam current increase to 38 mA, DTL3-DTL5 of the NCL will be upgraded to 3 MW klystrons as well upgrading to HVCMs. There is no need to change the circulator or load.
  The LLRF will provide control and protection for the 28 new SCL cavities.
  The existing linac modulators will support the use of both 2.5 and 3 MW klystrons by updating the modulator topology.
  Three new linac modulators (AT-HVCMs) will power groups of 9,9, and 10 klystrons.

## Slide 29: 2.3 RF A. Nassiri, ANL and M. Fazio, SLAC Subcommittee 3
2.3 Findings
  Utilities will provide electrical and mechanical support to all PPU technical equipment including new SCL and DTL upgrades.
  Controls will integrate new technical equipment into the site wide controls infrastructure.
  The RF Systems team issued a number of purchase orders since the CD-3B including AT-HVCM transformer, SCR and built-to-print tanks, cable and tray for the first two transmitters, SCL DI water pumps and heat exchanger and controls hardware and HPRF transmitters and SCL klystrons.
  The RF Systems team completed NCL circulator and load review and continued the design of 3W klystron with vendor.
  For the RF Systems, currently COVID-19 has no impact to the project milestones. The team review vendor updates regularly to assess potential future schedule impact.
  The RF Systems do not have any high risk items in the Risk Register. Risks are all medium or low.
  Final design reviews of HPRF transmitter ( with vendor), RFQ/DTL HVCM, and LLRF are planned for Summer/Fall 2020.
  Receipt of major rf components ( transmitters 30 and 31, 1st 12 SCL klystrons, and SCL-MOD-30) are expected in Summer 2021.
  Installation of transmitters 30 and 31 equipment will start in Summer 2021.

## Slide 30: 2.3 RF A. Nassiri, ANL and M. Fazio, SLAC Subcommittee 3
2.3 Findings
  The circuit topology of the RFQ HVCM mimics the Alternate Topology HVCM (AT-HVCM) used in for the new SCL RF stations.
  The exiting linac modulators have updated design to support 3MW klystron operation. It provides a common design for both RFQ and DTLs.
  New LLRF system successfully “witnessed” 23D operation – cavity control test is scheduled for this summer.
  RF Systems awarded CD-3B procurements totaling ~$23M.
  The entire RF Systems will be at final design after the completion of HVCM and LLRF FDRS. Installation of equipment starts in summer 2021.
  The existing LLRF systems for the Linac have components that are obsolete.
  The existing system is PPU capable but cannot meet Second Target Station (STS) requirements ( cannot support more than one beam flavor and cannot do pulse-to-pulse AFF correction).
  The LLRF system is responsible for high-power protection of cavities by providing fast shutdown of the RF drive signal as part of the High-power protection and interlocks.
  Cavity field control module-II hardware development. The team has partnered with a company on board fabrication.
  The team has partnered with LBNL for firmware collaboration. LBNL team is assisting with upgrading system model and providing DSP firmware and knowledge transfer.

## Slide 31: 2.3 RF A. Nassiri, ANL and M. Fazio, SLAC Subcommittee 3
2.3 Comments
The RF Systems team is experienced, skilled, and qualified with many years of design and operation experience. The team has made great strides since CD-3a/CD-3b.
The technical presentations were detailed and very informative. We appreciate the team’s availability to answer our questions and provide us with additional information before and during this review.
RF Systems technical design is mature and likely to meet the project baseline performance.
RF Systems design is about 90% complete. Final design reviews of RFQ-DTL HVCM and LLRF are planned for Summer/Fall 2020.
Overall, the level of RF Systems documentation is sufficient to support baseline design.
The team is encouraged to do timely onsite acceptance tests of the rf components as they arrive from vendors.
Procurement of new 3 MW klystrons needs continuing vendor follow-up to prevent further delivery delays.
The team successfully tested the new LLRF system on SCL cavity 23D. Full control test of LLRF system on SCL-23D is planned for Summer 2020.
We support completing the LLRF system “full control” test (field control) on SCL cavity 23D before holding the Final Design Review of the LLRF.
Managing LLRF collaboration with LBNL and vendor could be very challenging. The team needs to do their due diligence to stay the course.

## Slide 32: 2.3 RF A. Nassiri, ANL and M. Fazio, SLAC Subcommittee 3
2.3 Comments
The Committee supported the project team’s choice of a µTCA.4 platform for the LLRF system; leveraging TCA commercial hardware is sound.
Controls are based on existing designs that have been demonstrated and present minimal risks.
Based on the simulated operation of NCL circulator and load at normal and off-normal reflected power conditions, there is no need to upgrade circulator or load for PPU. We concur with this conclusion.
The RF Systems team should complete the final design reviews of LLRF, HPRF transmitter (with the vendor) and RFQ/DTL HVCM by end of Q1 FY21.
The RF team should continue to stay vigilant and proactive on QA of rf components delivered by the vendors to identify noncompliance issues early on for timely corrective actions.
Continue to review documentations as the project progresses and update as needed specially the ICDs, installation, test and commissioning plans.
All recommendations from past reviews have been addressed and closed.

## Slide 33: 2.3 RF A. Nassiri, ANL and M. Fazio, SLAC Subcommittee 3
2.3 Comments
L2 and L3 managers have a general understanding of the impacts of COVID-19 on RF Systems. COVID-19 mitigations are addressed at the Project-level.
COVID-19 has not yet had a significant impact on RF Systems that would require changes to the project milestones. The team is doing regular follow-ups with the vendors to measure the impact on hardware delivery schedule.
A notable impact from COVID-19 on RF Systems is the delay in 3MW klystron delivery which moves it to “near” critical path. RF Systems has some schedule float available if needed.
The procurements of all RF components should be closely monitored with regular follow-up and communication with vendors, particularly given the COVID-19 pandemic uncertainty.
RF Systems staffing has not changed since the last review. The Project believes that it has the required engineering and technician staff to adequately support PPU. COVID-19 mitigation plans for onsite work will impose new restrictions that may require staffing adjustment. The team should reevaluate RF Systems staffing level as the situation evolves.

## Slide 34: 2.3 RF A. Nassiri, ANL and M. Fazio, SLAC Subcommittee 3
2.3 Recommendations
Tabulate PPU SCL RF power requirements by the next DOE IPR. The table should include the following operating parameters supporting 1.3 GeV beam energy and 38 mA macro-pulse average beam current:
  Klystrons operating voltage and beam current
  Nominal and maximum klystron output power
  RF power transmission losses
  accelerating gradient
  Cavities loaded-Q
  Lorentz detuning
  Microphonics detuning
  RF source power overhead
  Cavities control power margin
Proceed to CD-2/3

## Slide 35: 2.4 Ring-Accelerator Sergei Nagaitsev (FNAL), Wolfram Fischer (BNL), Uli Wienands (ANL)
Design Maturity: Is the final design sufficiently well-defined and technically sound to achieve the specified technical performance requirements and to establish a performance baseline and start construction?
  Yes. The final design is well-defined and technically sound (CD-2/3 ready), some outstanding scope FDR left for Sep 2020. One outstanding system (BPLS) will have its PDR in Feb 2021 and its FDR in Aug 2021. The BPLS system is on a near-critical path but it’s well-defined in scope and there are mitigation plans in place in case there is a schedule delay.
Project Scope: Will the project scope, as currently defined, achieve the objectives in the Mission Need Statement? Is the Work Breakdown Structure dictionary and are the key performance parameters (KPPs) appropriately defined to establish a credible performance baseline and start construction?
  Yes

## Slide 36: 2.4 Ring-Accelerator Sergei Nagaitsev (FNAL), Wolfram Fischer (BNL), Uli Wienands (ANL)
Technical: Is the technical progress to date sufficient to meet the performance specifications and support the procurements and installation as planned? Is the trajectory appropriate for meeting the threshold KPPs by CD-4?
  Yes. Also, the committee noticed big improvements in defining the performance specifications for several systems (e.g. BPLS and the beam dump). Also noted is the successful 1.7-MW equivalent demonstration of beam, stored in the ring (1.83e14 protons at extraction, higher than the threshold KPP).
Recommendations: Have past review recommendations been appropriately addressed?
  N/A (there were no past review recommendations). The project team considered the comments from the June 2019 review and changed some technical specifications and designs.

## Slide 37: 2.4 Ring-Accelerator Sergei Nagaitsev (FNAL), Wolfram Fischer (BNL), Uli Wienands (ANL)
Findings
  To achieve 2.8 MW, the beam energy is increasing by 30%, the remainder is achieved by beam current. All existing ring magnets are determined to be “good” as is, except for injection and extraction sections.
  Chicane and Dump septum magnet drawings are being finalized
  New Injection dump line Quadrupole adds additional control of beam spot size
  Injection kicker power supply upgrade is simple and low risk.
  Extraction kicker power supply is running a 30-day test to verify reliability
  Extraction septum shims analysis in progress with initial data showing distortion roughly halfway between original design and current operation at 1.0 GeV.
  Handling the increased particle-throughput by the stripping foil was reported to result in increased temperature but it is within acceptable limits.
  Ring Injection Dump imaging system designs and engineering review are nearing completion.
  Bench testing for the Imaging System provided confidence in design.

## Slide 38: 2.4 Ring-Accelerator Sergei Nagaitsev (FNAL), Wolfram Fischer (BNL), Uli Wienands (ANL)
  Calibration of the analytical model of the RID shielding and structural elements correlates closely with measured data.
  Work underway to appropriately document use of the code-allowable higher temperature bound
  The Ring-Injection Dump is capable of handling up to 150 kW with the limit re-confirmed by calibrated modelling. 60 kW is current normal operation; Main concern is overheating the concrete by exceeding power over longer time scales (months).
  Utilities: The transformer fan upgrade kits have been selected; The water cooling design is mature, system design emulates standard, proven SNS best practice, no technical risk.
  PFN Room Cooling: the design recovery plan is advancing after two unresolved issues found, while preparing for the FDR.

## Slide 39: 2.4 Ring-Accelerator Sergei Nagaitsev (FNAL), Wolfram Fischer (BNL), Uli Wienands (ANL)
With exception of BPLS, the Ring Controls are based on mature, proven designs. The BPLS is based on COTS/MOTS, where possible. Custom designs are based on industry standards for high reliability signal processing. Ring Controls scope is well understood and supports the PPU KPPs.
The BPLS was added to the scope after CD-1. The scope is now well defined, and documented in the WBS dictionary.
The Beam Power Limiting System cost has increased substantially since last review (June 2019) because of a better scope and schedule definition. Some technical requirements were relaxed since the previous review (beam shut-off: 2 pulse limit then, 60 seconds limit now).

## Slide 40: 2.4 Ring-Accelerator Sergei Nagaitsev (FNAL), Wolfram Fischer (BNL), Uli Wienands (ANL)
Comments
  We congratulate the team on excellent progress since the previous review
  The successful 1.7 MW equivalent beam power test is a significant step towards the PPU performance goal.
  The beam dump has a power limit 150 kW. The injection dump power rating has been established conservatively with the help of models and the experimentally verified temperature evolution of the concrete under load. It appears that the thermal time constant of the beam dump concrete is 100-s of days, which should allow for some operational flexibility to exceed the rated power for short periods of time. We suggest the project team evaluate and document such a relaxed flexibility.
  The BPL system, while well defined in its requirements, will be challenging to implement in the time scale foreseen. Issues that may take additional effort are noise on the FCT data, difficulty in maintaining calibration of the FCT under changing beam properties, programming effort for the FPGAs and the general overhead incurred when building credited safety systems. Presently the BPLS is not rated as high risk despite being near the critical path. The committee supports an early installation (now) of a test FCT to start recording and processing signals.

## Slide 41: 2.4 Ring-Accelerator Sergei Nagaitsev (FNAL), Wolfram Fischer (BNL), Uli Wienands (ANL)
Comments
The upgrade of the kicker pulsers is an efficient scheme and avoids reconfiguration in the extraction area. The added stress on the kickers is quite marginal and should pose no issues for reliability.
An impressive amount of high-quality data for the Ring Injection Dump power-handling capability was shown, and the imaging system to be installed appears well thought out and analyzed, and it will be a valuable diagnostic.
The upgraded DI water system that lower the temperatures in the ring systems should not change the temperature of the rf cavities in the ring.
It may be prudent to anticipate sporadic leaks when the water temperature is lowered (because of different thermal expansions).
Recommendations
-- By the next DOE IPR, evaluate adding a Risk Registry entry for the Beam-Power Limiting System.
-- Proceed to CD 2/3 approval

## Slide 42: 3. Conventional Facilities J. Cisek, ANL / Subcommittee 5
Design Maturity: Is the final design sufficiently well-defined and technically sound to achieve the specified technical performance requirements and to establish a performance baseline and start construction? YES
Project Scope: Will the project scope, as currently defined, achieve the objectives in the Mission Need Statement? YES Is the Work Breakdown Structure dictionary and are the key performance parameters (KPPs) appropriately defined to establish a credible performance baseline and start construction? YES
Recommendations: Have past review recommendations been appropriately addressed? YES

## Slide 43: 3. Conventional Facilities J. Cisek, ANL / Subcommittee 5
Findings
WBS P.6 Conventional Facilities (CF) includes the design, procurement and construction of
  Klystron gallery bldg. modifications to support the installation, assembly and operation of the technical components.
  A new Ring to Target Beam Transport (RTBT) stub to facilitate the beam tie-in for the Second Target Station Project without a major shutdown
  Water & HVAC controls for the klystron gallery buildout
CF technical requirements are listed in the Final Design Report
CF scope contains several interfaces with other parts of PPU that are recorded in Interface Control Documents
Technical requirement specifications/final designs for CF scope are complete, though the BIM model for the klystron gallery buildout is not finished
High Performance Sustainable Building guidelines are not applicable for this project since the building does not exceed 5,000 gsf
The klystron gallery bldg. modifications were part of the project CD-3B approval and the construction portion of this scope was moved to WBS P.10 Long Lead Procurements

## Slide 44: 3. Conventional Facilities J. Cisek, ANL / Subcommittee 5
Findings
Construction of the klystron gallery bldg. modifications is in progress
  CPI = 1.00
  SPI = 0.75
The klystron gallery bldg. modification scope experienced challenges during procurement due to lack of contractor interest and high bids
CF scope is not currently listed on the PPU critical path schedule
The planned construction period for the RTBT stub is during the extended SNS outage in FY23
Outage construction of the RTBT stub is near critical path with 37 days of float
Bids are not in hand for the RTBT stub and will not be until closer to the anticipated start of construction in FY22
The RTBT stub cost estimate and schedule were developed by the A/E design firm with input from an outside CM contractor
The COVID-19 pandemic has had little/no impact on CF scope to date
The CF team received three prior review recommendations. All three recommendations are closed

## Slide 45: 3. Conventional Facilities J. Cisek, ANL / Subcommittee 5
Comments
The CF team is well established and fully functional
The CF scope as outlined in the final design report will meet the approved Mission Need
The utilization of BIM for the klystron gallery buildout is a best practice and the project has already experienced added value from BIM
The CF team did not have much BIM experience and has realized challenges implementing BIM practices. However, the team has recently added a BIM coordinator which has helped to finalize the BIM model. The team is also actively tracking BIM lessons learned which will benefit the Second Target Station Project and other projects at ORNL that will utilize BIM
The CD-3B scope for the klystron gallery bldg. modification is currently behind schedule with an SPI of 0.75. This schedule delay is due to inclement weather but also contractor performance. The CF team is working with lab procurement to obtain a corrective action plan from the contractor to get back on schedule

## Slide 46: 3. Conventional Facilities J. Cisek, ANL / Subcommittee 5
Comments
If the klystron gallery building modifications scope is further delayed, then this may cause construction to coincide with the technical installation in the same area. This will make the technical installation more challenging but still achievable with minimal schedule risk
The CF team updated the RTBT stub cost estimate to reflect the realization of high bids on the CD-3B procurement. While a great step to mitigate the risk of high bids, there is opportunity to improve the confidence level of the CF budget with an independent cost estimate
Since the outage construction of the RTBT stub scope is near critical path, the project team is working to maximize the amount of work that can be completed before the outage
To mitigate the schedule risk of the RTBT stub construction, the CF team should work with the contractor prior to award to ensure a credible working schedule

## Slide 47: 3. Conventional Facilities J. Cisek, ANL / Subcommittee 5
Comments
The STS Project is seeking CD-3A approval for site work that could coincide with the RTBT stub construction and would create logistical challenges
The RTBT stub procurement approach includes utilizing the STS construction manager with a fallback option to competitively bid the scope. The plan is sound but there is still significant risk due to the unknowns surrounding the STS CM as well as the volatility of the contractor market
The CF team is actively managing the schedule risk for the RTBT stub outage construction, however no such risk exists in the project risk register
Past review recommendations have been appropriately addressed

## Slide 48: 3. Conventional Facilities J. Cisek, ANL / Subcommittee 5
Recommendations
Prior to CD-2/3 ESAAB, complete a thorough risk analysis of the RTBT stub procurement, construction logistics, cost, and schedule to identify risks not currently in the project risk register, and update the risk register accordingly
Proceed to CD-2/3

## Slide 49: Environment, Safety and Health J. Fleming, LBNL, M. Fries, ANL, J. McGhee, ANL Subcommittee 6
ES&H/QA: Are Environment, Safety, and Health and Quality Assurance (ES&H/QA) requirements and plans, including COVID-19 protections and safety measures, being properly addressed? YES
Recommendations: Have past review recommendations been appropriately addressed? YES

## Slide 50: Environment, Safety and Health J. Fleming, LBNL, M. Fries, ANL, J. McGhee, ANL Subcommittee 6
Findings
  National Environmental Protection Agency Categorical Exclusion (Cx) was approved.
  Hazard Analysis Report (HAR) was completed and updated for CD-2/3.
  Construction Project Safety and Health Plan was completed in September 2019.
  COVID-19 protections and safety measures have been presented and are being flowed-down to lower-tiered subcontractors.
  Quality Assurance Plan was completed and was prepared specific for the project.
  External Readiness Review (ERR) or Accelerator Readiness Reviews (ARR) are required to be performed and approved as part of the transition to operations plan.

## Slide 51: Environment, Safety and Health J. Fleming, LBNL, M. Fries, ANL, J. McGhee, ANL Subcommittee 6
Comments
  Integrated Safety Management is well established in the project and is being flowed-down to lower, tiered subcontractors through the ORNL Chestnut Ridge Project Safety and Health Plan.
  ESH&Q personnel are well integrated into the project and providing support for project document reviews and field inspections.
  Construction oversight and safety is well managed and a Safety Services Representative provides 40% time for construction oversight and safety review.
  ORNL has implemented robust, COVID-19 precautions and safety measures through response plans, density monitoring, training and testing which have been flowed-down to lower, tiered subcontractors and is commendable.
  A COVID-19 Subcontractor Hazard Analysis is required to address precautions and safety measures for onsite construction work, which is a best practice.
  Hazard Analysis Report or an unreviewed safety issue (USI) should incorporate and address hazards associated with the connection of the RTBT to the main SNS.
  Suggest re-evaluating the Oxygen Deficiency Hazard calculations with the increased helium usage.

## Slide 52: Environment, Safety and Health J. Fleming, LBNL, M. Fries, ANL, J. McGhee, ANL Subcommittee 6
Comments
  Quality Assurance program has improved and is in place with functional requirements of the QA program that meets the elements needed.
  QA coordination with partner Laboratories is very well structured.
  Ensure the statement of work review includes completion of the Quality Assurance Grading checklist and development of acceptance criteria.
  RTBT design review should include project QA and ES&H organization to review the Conventional Facilities construction for RTBT stub to be sure requirements are incorporated.
  Procedures and an engineered containment have been incorporated into the design to mitigate the sources of the March 2020 ORPS mercury release.
  Project plans include revisions of the Facility Safety Document (FSAD-PF) and Accelerator Safety Envelope (ASE) to support crediting the Beam Power Limiting System after first cryomodule outage and Radiation Safety can implement a Hold process till the BPLS is ready.
  Increased proton energy and intensity for the project will potentially increase residual radiation levels in the ring injection area which would require additional evaluations and mitigations of radiation hazards.

## Slide 53: Environment, Safety and Health J. Fleming, LBNL, M. Fries, ANL, J. McGhee, ANL Subcommittee 6
Recommendations
  Present evaluations and mitigations of radiation hazards from the increase in proton energy and intensity at the next project review.
  Change wording in RTBT design review from “Project QA and ESH organization should to shall review the Conventional Facilities construction documents for RTBT stub” to ensure requirements are followed.
  Proceed to CD-2/3 ESAAB.

## Slide 54: 5. Cost and Schedule A. Bampton, PNNL / S. Morgan, LBNL
Project Scope: Will the project scope, as currently defined, achieve the objectives in the Mission Need Statement? Is the Work Breakdown Structure dictionary and are the key performance parameters (KPPs) appropriately defined to establish a credible performance baseline and start construction?
  Yes
Cost and Schedule: Are the cost and schedule estimates, including contingencies, mature and of sufficient quality to establish a credible cost and schedule performance baseline and to start construction? Are the cost, schedule, and performance metrics being properly collected and updated? Are major cost and schedule assumptions, resource constraints, and project risks, including COVID-19, being adequately addressed?
  Yes
Recommendations: Have past review recommendations been appropriately addressed?
  Yes

## Slide 55: 5. Cost and Schedule A. Bampton, PNNL / S. Morgan, LBNL
Findings: Cost
$272M TPC has increased by $42M since CD-1. $16M of the increase was recently added to address possible COVID impacts. Determination of contingency to address COVID impacts was developed top-down.
The project scope/upgrades are based on existing technologies and designs (“with some improvements”) are data based- the design is estimated to be 92% complete.
  81% of estimates reflect vendor input - 33% Vendor Estimate, 41% Placed Contracts, 7% Vendor quote

## Slide 56: 5. Cost and Schedule A. Bampton, PNNL / S. Morgan, LBNL
Cost Estimate History
Findings: Cost – cont.
Bottom up ETC for the existing plan was completed in April.
The estimate is generally supported by detailed basis at the 5 level of the WBS.
CAM interviews of RF systems ($65M) and SCL systems ($39M).

## Slide 57: 5. Cost and Schedule A. Bampton, PNNL / S. Morgan, LBNL
Findings: Schedule
Schedule health score/metric is 88. Drivers for this score were identified. Logic density, merge hotspots, etc.
Critical Path runs thru the Fabrication of the target.
Schedule contingency is now stated as 42 months = 8 months risk register, 22 months ‘1250’ KPP, 12 months COVID
Schedule includes 6,096 activities, 841 milestones and 9,426 relationships.
Schedule assumes a 8.5 month shutdown in 2023.
Project schedule with float has minimal external constraints due to other downstream or parallel project efforts. The Secondary Target System will need hand-off well after current scheduled hand-off.

## Slide 58: 5. Cost and Schedule A. Bampton, PNNL / S. Morgan, LBNL
Findings: Other
2 Cost and Schedule related recommendations from CD-3b have been addressed.
The project has been reporting EV since about CD-3A. The EVM system and the project was surveilled in Dec. 2019
Risk workshop conducted by Keith Molenar in Jan 2019.
Buydown lists exist for use of contingency totaling $23.5M. The buydown is comprised of critical, operational and economical spares.

## Slide 59: 5. Cost and Schedule A. Bampton, PNNL / S. Morgan, LBNL
Comments
The project team has demonstrated good project cost and schedule performance in executing CD-3A/3B scope.
Final design is estimated at 92% complete. Remaining design effort is rated as low risk. 81% of the fabrication/procurement estimates are based on vendor input creating a strong basis of estimate
Risks appear to be understood and project team is using best practices and utilizing industry leading outside expertise to help advance risk management planning. Another best practice would be to have risks independently reviewed.
Possible impacts of COVID should continue to be analyzed. Despite this being an evolving issue, mitigations need to be developed for the various scenarios at various vendors and institutions and near term risks (6-9 months) added to the register.
Continued attention to the potential impacts the project could have on related projects, especially around the RTBT stub, will be required as the project moves along. It is not anticipated that the RTBT stub work schedule would impact other projects at this time.

## Slide 60: 5. Cost and Schedule A. Bampton, PNNL / S. Morgan, LBNL
Recommendations
Proceed to CD-2/3

## Slide 61: 5. Cost and Schedule A. Bampton, PNNL / S. Morgan, LBNL
PROJECT STATUS (as of March 2020) |  | 
Project Type | Line Item | 
CD-1 | Planned: Q3 FY17 | Actual: April 4, 2018
CD-3A | Planned: Q2 FY19 | Actual: October 5, 2018
CD-3B | Planned: Q4 FY19 | Actual: September 5, 2019
CD-2 | Planned: Q2 FY20 | Actual:
CD-3 | Planned: Q2 FY21 | Actual:
CD-4 | Planned: Q4 FY28 | Actual:
TPC Percent Complete | Planned: N/A | Actual: N/A
TPC Cost to Date | $ 51.8 M | 
TPC Committed to Date | $ 33.1 M | 
TPC* (tentative, will be baselined at CD-2) | $ 271.6 M | 
TEC | $ 197.8 M | 
Contingency Cost (w/Mgmt Reserve) | $ 63.0 M | 40% to go
Contingency Schedule on CD-4 | 42 months | 72% to go
CPI Cumulative | N/A | 
SPI Cumulative | N/A | 

## Slide 62: 6. Project Management P. Mantica, MSU / Subcommittee 8
Enzo Carrone (SLAC), Deb Grubbe (retired DuPont), Paul Mantica (MSU), Lori Plummer (retired SLAC), John Tapia (SLAC/LANL)
Cost and Schedule: Are the cost and schedule estimates, including contingencies, mature and of sufficient quality to establish a credible cost and schedule performance baseline and to start construction? Are the cost, schedule, and performance metrics being properly collected and updated? Are major cost and schedule assumptions, resource constraints, and project risks, including COVID-19, being adequately addressed? Yes to all
Management: Is the project being properly planned, managed, and staffed to successfully deliver the scope within the proposed cost and schedule? Does the project have the necessary resources? Are project risks being appropriately identified and managed? Have the requirements for CD-2 and CD-3 been met? Is the project ready for CD-2 and CD-3? Yes to all
Recommendations: Have past review recommendations been appropriately addressed? Yes

## Slide 63: 6. Project Management P. Mantica, MSU / Subcommittee 8
Findings
Cost estimate Data Base used to support Cost Basis in P6
Point cost estimate for PMB $271.6M
  Increase of $26M from CD-3B to present
  Within the $184M - $320M CD-1 cost range
Point cost estimate includes 40% cost contingency on remaining work
42 months of schedule contingency, with 22 months assigned to mitigate for target KPP
Last ETC exercise in early 2020, EAC determined from actuals + ETC
Critical path is civil construction for klystron gallery, procure and target design target modules, install cryomodules, and ARR
Many tasks are near critical path
EV reports for LLP (officially since CD-3B)
26% of work has been performed
EVMS surveillance review in Dec 2019, no CARS and 2 CIO* addressed and closed
LLP SPI=0.98/CPI=1.03
  CD-3A for SC cavities is 75% complete, on schedule for March 2021 completion
  CD-3B for CM construction, RF systems, and klystron gallery construction is 19% complete, forecast finish is Q2 of FY2022

## Slide 64: 6. Project Management P. Mantica, MSU / Subcommittee 8
Findings (cont.)
Assumptions document is prepared
Schedule constraint is SNS maintenance outages
Schedule assumption is that there are three planned outages beginning in FY22
Each quarter of the published operations schedule is made official one month prior to the start of that quarter
Schedule assumption is that project is not funding limited
Risk register has 72 active threats and 3 active opportunities
  49 threats and 13 opportunities have been retired
  10 new risks added since CD-3B
  Risks continually evaluated and monitored
  Risk workshop conducted Jan 2019 with CAMS, led by K. Molenaar
COVID-19 top-down contingency additions: schedule 12 months, cost $16M
  Cost impact approximately 10% on remaining work
  COVID-19 risk is held as a management assessment outside of the risk register
  Impact on procurements with value above $150k have been analyzed

## Slide 65: 6. Project Management P. Mantica, MSU / Subcommittee 8
Findings (cont.)
Project management plan in place that provides comprehensive description of processes and guidance for cost, schedule, and technical scope management
Experienced leadership team, three changes since last review
  ESHQ lead, ring system lead (L2), pre-ops lead (L2)
JLab Partner lab management experienced and actively participated in review
  An MOU exists between ORNL and JLab for PPU
  Standardized tools for PM between labs
A consultant was hired to represent ORNL interests for delivery of cavities from the international vendor
A new deputy director for projects has been appointed by ORNL
A three-phased approach to commissioning and operations is planned. The approval process steps are defined and includes externals reviews
Project spares are included in the baseline
  List of Critical, Operational, and Economical spares ($23M) exists
Scope contingency (buy-back and removal) prepared by team
61% of point cost estimate has been appropriated
  Risk register includes potential delay due to lack of funding
Project has a change management board that consist of technical system owners who review proposed technical changes to assess and mitigate impacts

## Slide 66: 6. Project Management P. Mantica, MSU / Subcommittee 8
Findings (cont.)
Project staffing is near peak
  Head Count between April and June 2020 range is 168 to 196 people supporting PPU
  Number of people supporting PPU at >50% level of effort in this time period is 51 to 54 people
  Number of FTEs ranges from 62.1 to 66.9
  Majority of staff is matrixed from NScD
  A major laboratory staff structure reorganization effort has just initiated
Staffing needs being met due to improved operations management and higher SNS reliability
  1.4MW at 95% availability
Partner labs delivering scope
  JLab is providing cryomodules
  Fermilab is providing new chicane magnets and the injection dump septum magnet
  LBNL is collaborating on LLRF development
SNS and ORNL provide critical support such as matrix staff and conditioned storage facilities
The geographical extensiveness of the PPU Project encompasses many locations across the SNS

## Slide 67: 6. Project Management P. Mantica, MSU / Subcommittee 8
Findings (cont.)
CD-2 requirements mostly in place except for PEP finalization and two subsystems that are still in preliminary design
CD-3 requirements mostly in place, outside of PEP, final design status, final design review
  Final design at 92% with remaining subsystem/component designs to be completed, reviewed and recommendations resolved prior to fabrication or procurement of these items
  Remaining design accounts for $7M of $83M total
  Key Performance Parameters are defined in the PEP (draft)
  Technical Parameter List is published
  Final Design Report is published
  Interface Control Documents are published
All recommendations from prior DOE/SC reviews (26) are closed
Director’s Review (June 2020) had 8 recommendations (7 closed, 1 in progress)

## Slide 68: 6. Project Management P. Mantica, MSU / Subcommittee 8
Comments
The Project Management team is functioning well and was well prepared for the CD-2/3 review
The new Director of Projects, reporting to the Laboratory Director, should serve PPU project well in addressing resource needs and sharing lessons learned from other laboratory projects
Partner lab (JLab) has benefitted from lessons learned in CM production for other projects. PPU overall would also benefit from increased communication between project managers of other large DOE-SC accelerator projects
Matrixing seems to be working well, especially since SNS operations has recently shown high reliability. It is understood that user operation has priority, and the project needs to be well positioned to argue for appropriate resources to meet cost and schedule
Project needs to ensure effective communications with other activities, both large and small, throughout the SNS
The subcommittee feels the cost and schedule contingency is appropriate
Project responded well to previous recommendation to better develop the risk-based contingency

## Slide 69: 6. Project Management P. Mantica, MSU / Subcommittee 8
Comments (cont.)
The project has a top down assessment of COVID-19 impact, and should start a bottom up assessment of impacts to cost and forecast schedules
Project is encouraged to continue flushing out scope contingency, both removal and buy-back. Scope buy-back discussions with STS could be pursued
Change management process seems sound, project should continue to communicate technical changes to all stakeholders
Project needs to consider the need for and risk to duration associated with safety system certification and/or revalidation at the end of each of the planned outages and plan accordingly
Key stakeholders need to be aware of need to communicate emergent issues with meeting outage schedules at least 6 months in advance. Valuable lessons learned available from the recent LCLS-II Long Down Time
The three-phased approach to commissioning and operations is reasonable, and makes appropriate use of external reviews
The subcommittee feels that the remaining designs are low risk
Management of vendors should be tightened across the project, since visits to remote sites, both domestic and international, are restricted due to the COVID-19 situation

## Slide 70: 6. Project Management P. Mantica, MSU / Subcommittee 8
Recommendations
Supplement the PPU COVID-19 vendor impacts list with the following information: PPU point-of-contact (both procurement and technical); planned frequency of vendor contact; date of last vendor contact; method of last vendor contact. This revised PPU COVID-19 vendor impacts list shall be appropriately communicated to DOE starting next month and continue monthly
The project is ready to proceed to CD-2/3