Weekly Reporting SNS PPU

WBS P.02.03 Cryomodule Integration (JLab Scope)

April 30, 2021

Issues:

Impact of COVID-19 - JLab remains at MEDCON-5 with limited operations.  Staff who can work remotely will continue to do so through at least MAY 2021.  Lab continues to evaluate circumstances that would allow a return to MEDCON-4.

Staff are onsite to perform PPU-related work (since 15-JUN).

Accomplishments this week:

Management:

- PPU activities are continuing onsite, with testing of production cavities, preparation for string assembly #2, preparation for cold mass assembly and receipt inspection of components.

- Off-site work efforts continue, focused on completion of procurement activities and preparations for production.

- Evaluating impacts of COVID-19 on overall project schedule and developing mitigations.

- Testing tanked cavities for string #2 based on results from string #1 post-tanking tests (3 of 5 passed on first try after tanking).

- Incorporating BCR for 8th CM into baseline.

- Planning for Howell/Mammosser visit week beginning 5/3/21.

Engineering & Design:

- Sustaining engineering activities are continuing in order to revise drawing packages based on feedback during the procurement phase.

Procurement:

- 5 active procurement awards; 83 completed (arrived at JLab).

- End Cans:

  - Supply end can (SEC) 01 is ready to be returned to vendor.

  - SEC 02 is on the end can tool to be inspected.

  - SEC 03 is uncrated and preliminary inspections performed. Bellows and bridge tube orientation look alright. It will wait for more detailed inspections to be done.

  - Return end can 01 & 02 will be shipped together early May.

- Vacuum Vessels:

  - Vessel #2 is currently having final machining stages performed, and is due to ship to JLab on 6/7/21.

  - Vessel #3 is undergoing final welding steps, will be in machining center for final machining this week. Due to ship to JLab on 7/5/21.

  - Vessel 4 has had the stiffener rings welded completely on and is awaiting its first post weld machining process. Scheduled for delivery to JLAB on 8/2/2021.

  - Vessel 5 is having its stiffener rings welded on. Scheduled for delivery to JLAB on 8/30/2021.

  - Vessel 6 scheduled to ship to JLAB on 9/27/2021.

  - Vessel 7 scheduled to ship to JLAB on 10/11/2021.

Production:

- Cavity Status:

PPU-08 tanked cavity successfully RF tested after HV tanking. This is first cavity for CM-2

PPU17 is preparation for RF test as received from vendor

PPU-06 cavity is being prepared for RF test next week. The cavity initially FE limited after HV welding.

- Cryomodule Status:

First string is in cold mass assembly.

    - Coupler cooling lines mocked up

    - Tuner installation on-going

    - Some MLI installed

    - Preparing for 2K process piping leak check

- PPU-13 HV welding in process (string #3), nearly complete

- PPU-11 HV Tacking I.P.

- SEC 2 and 3 inspections on-going

- Spaceframe/thermal shield disassembled to install MLI

- FPCs:

  - Six FPCs have been cleaned and transferred in the clean room and are ready for incoming inspections / preparation for SNSPPU CM02 / ORNL visit.

Project Management:

- Finished BCR 21-005 and associated work authorization documents

- Collected April status

- Sent accrual to ORNL

- Issued mid-month manpower reports

- Updated Responsibility Assignment Matrix

Quality Assurance:

- Space Frame / Thermal Shield PFMEA team conducted its first working session this week. The team analyzed process steps from the Space Frame/Thermal Shield procedure/traveler for potential failure modes. Team will continue identifying failure modes for the remaining process steps in its next session.

- SRF Ops Customer Satisfaction Survey sent to ORNL.

- Improvements to the NCR program are in progress.