Weekly Reporting SNS PPU

WBS P.02.03 Cryomodule Integration (JLab Scope)

February 10, 2023

Issues:  None

Accomplishments this week:

Management:

- PPU activities are continuing with cryomodule assembly and receipt inspection of components.

- Off-site work efforts continue in the procurement area on end cans.

Engineering & Design:

- Sustaining engineering activities are continuing in order to revise drawing packages based on feedback during the procurement phase.

- Plan for transmitting complete set of CM drawings – Doc Control Group is preparing drawing package.  Shared folder at ORNL is identified.  Discussing preferred CAD model formats with ORNL colleagues.

Procurement:

- On Feb 14, one JLab visitor will visit the end can vendor to witness REC 5 bridging tube leak test.

- Supply End Cans (SECs):

| S/N | Status | Estimated Delivery Date |
| --- | --- | --- |
| 01 | Installed on CM-03 | - |
| 02 | Installed on CM-04 | - |
| 03 | Installed on CM-01 | - |
| 04 | Welded onto CM-05 | - |
| 05 | Welded onto CM-06 | - |
| 06 | Delivered to JLab on 6/6. Uncrated, inspections started. Phase 1 dimensional inspection done. Bridge tube angle is off by ~5 degrees. JLAB will try installation of SEC 06 and exercise loosening the hardware at both ends of the elbow/bellows and see how well it corrects. Plan to use on PPU-07. | - |
| 07 | Installed on CM-02 | - |
| 08 | All parts and sub-assemblies done. Album 1 pictures uploaded to share folder. Estimate to ship 6 weeks after REC 7 is finished. | Apr 14 |

Return End Cans (RECs):

| S/N | Status | Estimated Delivery Date |
| --- | --- | --- |
| 01 | Installed on CM-03 |  |
| 02 | Installed on CM-01 |  |
| 03 | Installed on CM-05 |  |
| 04 | Installed on CM-02 |  |
| 05 | Started welding of fit up bridging tube section. First two welds on bridging is complete | Mar 3 |
| 06 | Installed on CM-04. |  |
| 07 | Vacuum shell welding has begun. Completing the GTAW root passes. Expect to begin FCAW 2/9. | Mar 17 |
| 08 | Top plate weldment complete. Finished the Relief Stack weldment. Working on sub-assemblies. Bayonets done; most of the relief stack is done. Check valve is done; needs LC. Estimate to finish 8 weeks after REC 7 is done | Apr 28 |

Production:

Cryomodule Status:

CM05: MLI/shields in REC I.P.; flow hood, BL work

CM06: Awaiting REC

CM07: Wheels being machined; re-install next week.

CM08: Process piping welding complete; cold shock I.P.

U-Tube status: 4 U-tubes PT’d; 2 PT i.p.; started large u-tubes (CVI pump-out location discussed)

Project Management:

- Provided Monthly Accrual Data to ORNL

- Updated Month End EV Reports

- Updated Month End Manpower

- Updated CAM Notebook

Quality Assurance:

- Continue to monitor quality data for possible trends.

- Continuing to gather data deliverables for CM05.

Project Photos:

CM05

CM08