Weekly Reporting SNS PPU

WBS P.02.03 Cryomodule Integration (JLab Scope)

March 3, 2023

Issues:  None

Accomplishments this week:

Management:

- PPU activities are continuing with cryomodule assembly and receipt inspection of components.

- Off-site work efforts continue in the procurement area on end cans.

Engineering & Design:

- Sustaining engineering activities are continuing in order to revise drawing packages based on feedback during the procurement phase.

- Plan for transmitting complete set of CM drawings – Doc Control Group is preparing drawing package.  Shared folder at ORNL is identified.  STEP file CAD models have been transferred.

Procurement:

- On March 7, two JLab employees will visit the end can vendor to witness another leak test.

- Supply End Cans (SECs):

| S/N | Status | Estimated Delivery Date |
| --- | --- | --- |
| 01 | Installed on CM-03 | - |
| 02 | Installed on CM-04 | - |
| 03 | Installed on CM-01 | - |
| 04 | Welded onto CM-05 | - |
| 05 | Welded onto CM-06 | - |
| 06 | Delivered to JLab on 6/6. Uncrated, inspections started. Phase 1 dimensional inspection done. Bridge tube angle is off by ~5 degrees. JLAB will try installation of SEC 06 and exercise loosening the hardware at both ends of the elbow/bellows and see how well it corrects. Plan to use on PPU-07. | - |
| 07 | Installed on CM-02 | - |
| 08 | All parts and sub-assemblies done. Album 1 pictures uploaded to share folder. Pulled components and is getting started setting up the final assembly. Working on welded assembly. | Apr 14 |

Return End Cans (RECs):

| S/N | Status | Estimated Delivery Date |
| --- | --- | --- |
| 01 | Installed on CM-03 |  |
| 02 | Installed on CM-01 |  |
| 03 | Installed on CM-05 |  |
| 04 | Installed on CM-02 |  |
| 05 | Started welding of fit up bridging tube section. First two welds on bridging is complete. Final testing expected to happen next week. | Mar 14 (JLab estimate) |
| 06 | Installed on CM-04. |  |
| 07 | Is progressing well with the vacuum shell being welded up by a welder. Working on the external structural this week. Then weld small components to the top plate. | Mar 31 (JLab estimate) |
| 08 | Top plate weldment complete. Finished the Relief Stack weldment. Spools are coming together, MTM is rebuilding a part that was machined incorrectly (Part of the return bayonet), and moving the sub-assemblies through cold-shock/leak test as they are able. Worked on sub-assembly in process leak testing and cleaning. | Apr 28 |

Production:

Cryomodule Status:

CM05: In CTMF and cold at 2K; Ins vac ~2e-7; turbo amp being logged.  Initial testing has begun.  Expect to warm up late next week.

CM06: Awaiting REC delivery in mid-March.

CM07: Cold mass raise to disengage wheel; alignment repeated, better.

CM08: Ion pump replacement complete.

Project Management:

- Held Progress Meeting

- Held Progress Analysis Meeting

- Provided Monthly Director’s Review Data

- Sent Monthly Schedule Data to ORNL

Quality Assurance:

- Continue to monitor quality data for possible trends.

- Continuing to gather data deliverables for CM05.

Project Photos:

CM05

CM07