Weekly Reporting SNS PPU

WBS P.02.03 Cryomodule Integration (JLab Scope)

April 14, 2023

Issues:  None

Accomplishments this week:

Management:

- PPU activities are continuing with cryomodule assembly.

- Off-site work efforts continue in the procurement area on end cans.

Engineering & Design:

- Sustaining engineering activities are continuing in order to revise drawing packages based on feedback during the procurement phase.

- Plan for transmitting complete set of CM drawings – Doc Control Group has prepared drawing package.  Shared folder at ORNL is identified.  SNS PPU lead designer is verifying drawing package completeness.

Procurement:

- One JLab visitor visited the end can vendor on April 14 to witness REC 7 final testing.  Unit pass all tests and was stamped by the AI.

- Supply End Cans (SECs):

| S/N | Status | Estimated Delivery Date |
| --- | --- | --- |
| 01 | Installed on CM-03 | - |
| 02 | Installed on CM-04 | - |
| 03 | Installed on CM-01 | - |
| 04 | Welded onto CM-05 | - |
| 05 | Welded onto CM-06 | - |
| 06 | Delivered to JLab on 6/6. Uncrated, inspections started. Phase 1 dimensional inspection done. Bridge tube angle is off by ~5 degrees. Welded onto PPU-07. The support block is machined, bridge tube bellows is largely skewed due to dimensional deviations on the SEC 06. See photo. | - |
| 07 | Installed on CM-02 | - |
| 08 | At the vendor. Vendor worked on spools to thermal shield. Will set up for test of spools Friday with JLab visitor. | May 26 |

Return End Cans (RECs):

| S/N | Status | Estimated Delivery Date |
| --- | --- | --- |
| 01 | Installed on CM-03 |  |
| 02 | Installed on CM-01 |  |
| 03 | Installed on CM-05 |  |
| 04 | Installed on CM-02 |  |
| 05 | Delivered to JLab on 3/31. Inspection near completion. REC 5 is being aligned to PPU-06. Initial misalignment is quite large. Bridge tube bellows is expected to absorb large displacements if it can still maintain integrity, see photo. |  |
| 06 | Installed on CM-04 |  |
| 07 | Vendor is working on it. Vacuum boundary test complete. Set up and starting (4/13) cold flow tests. AI and JLab visit on Friday 4/14 resulted in approval as unit pass all tests. | Apr 26 from MTM |
| 08 | Album 1 submitted but missing photos of critical welds. Start set up for welded assembly. | June 9 |

Production:

Cryomodule Status:

CM05: At ORNL awaiting high power testing.

CM06: REC R.I. complete; install I.P.

CM07: SEC installed; process piping welding in progress

CM08: HV Mu shields on order; SF/VV on tooling; align crew fiducializing today. Coupler line welding issues, braze. Couple of attempts; leak tight. Cold shocking in progress.

Project Management:

- Updated March Monthly EV Data

- Provided March Month End Manpower Data

- Distributed VARs for Updates

- Updated the CAM Notebook

Quality Assurance:

- Data deliverables for CM05 were uploaded to the SharePoint site.

- Continue to monitor quality data for possible trends.

Project Photos:

REC-05 to PPU-06

SEC-06 welded to PPU-07

SEC-06 bellows skewed

CM-06

CM-07

CM-08 Coupler line welding issue being addressed