Weekly Reporting SNS PPU

WBS P.02.03 Cryomodule Integration (JLab Scope)

October 27, 2023

**Issues:** None.

**Accomplishments this week:**

Management:

* PPU activities are continuing with cryomodule assembly.
* Preparing presentations for Director’s Review.

Engineering & Design:

* Sustaining engineering activities are continuing in order to revise drawing packages based on feedback during the procurement phase with a focus on end can drawing packages. Work planned to be complete by the end of October.

Procurement:

* Closing out remaining major contracts.

Production:

* CM-08 Status:
  + SEC08 piping welding completed.
  + REC08 was delivered to ORNL.
  + Shipping date TBD based on REC inspection and repair at ORNL.

Project Management:

* Submitted VARs for Signature
* Sent out Progress Sheets
* Updated Mid-month Manpower Charts

Quality Assurance:

* Continue to monitor quality data for possible trends
* Reported on Open NCRs, Travelers and CAPAs at bi-weekly meeting

Project Photos: None