Weekly Reporting SNS PPU

WBS P.02.03 Cryomodule Integration (JLab Scope)

November 10, 2023

**Issues:** None.

**Accomplishments this week:**

Management:

* PPU activities are continuing with cryomodule assembly.
* Final preparations completed for Director’s Review at ORNL.

Engineering & Design:

* Sustaining engineering activities are continuing in order to revise drawing packages based on feedback during the procurement phase with a focus on end can drawing packages.

Procurement:

* Closing out remaining major contracts.

Production:

* CM-08 Status:
  + SEC08 piping welding completed.
  + REC08 was delivered to ORNL. REC08 is estimated to return to JLab the week of 11/13.
  + Shipping date forecast is 1/22/2024 pending successfully end can repair.

Project Management:

* Completed EV Reports
* Sent Cost Package to ORNL
* Updated CAM Notebook

Quality Assurance:

* Continue to monitor quality data for possible trends
* Reported on Open NCRs, Travelers and CAPAs at bi-weekly meeting

Project Photos: None