Weekly Reporting SNS PPU

WBS P.02.03 Cryomodule Integration (JLab Scope)

November 17, 2023

**Issues: Have a Happy Thanksgiving!**

**Accomplishments this week:**

Management:

* PPU activities are continuing with cryomodule assembly.
* Participated in Director’s Review at ORNL.

Engineering & Design:

* Sustaining engineering activities are continuing in order to revise drawing packages based on feedback during the procurement and assembly phases.

Procurement:

* Closing out remaining major contracts.

Production:

* CM-08 Status:
  + REC 08 has been reworked and shipped back to JLAB. Inspection on REC 08 will commence week of 11/20.
  + Shipping date forecast is 1/22/2024.

Project Management:

* Sent out VARs
* Provided support for the Director’s Review
* Updated CAM Notebook
* Participated in Director’s Review at ORNL.

Quality Assurance:

* Continue to monitor quality data for possible trends
* Reported on Open NCRs, Travelers and CAPAs at bi-weekly meeting
* Participated in Director’s Review at ORNL.

Project Photos: None